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	Quotation Estimate No.:
	QTE/2025/00412

	Date of Issue:
	12 June 2025

	Project Location:
	Uttara Industrial Zone, Dhaka, Bangladesh

	Project Title:
	Complete Electrical Infrastructure Design, Installation & Commissioning

	Validity Period:
	30 days from date of issue

	Currency:
	Bangladeshi Taka (BDT / ৳)


1. Scope of Work — Electrical Engineer Services
This Quotation Estimate is issued by Delta Power & Electrical Consultants Ltd. to provide comprehensive Electrical Engineer services for the design, installation, testing, and commissioning of the complete electrical infrastructure at the GreenTech Industries Ltd. manufacturing facility located in Uttara, Bangladesh Dhaka. The scope encompasses all phases of electrical engineering work as detailed below, performed by a licensed and certified Electrical Engineer team registered with the Bangladesh Council of Engineers (BCE).
2. Itemized Cost Breakdown
	S/N
	Description of Electrical Engineer Service
	Quantity
	Unit Rate (BDT)
	Amount (BDT)

	1
	Site survey, load calculation, and single-line diagram preparation by a senior Electrical Engineer in Bangladesh Dhaka
	01 Lot
	85,000
	85,000

	2
	Complete electrical design including power distribution, lighting layout, earthing & lightning protection system design
	01 Lot
	220,000
	220,000

	3
	Supply and installation of 3-phase 415V main distribution board (MDB) and 12 sub-distribution boards (SDBs)
	13 Units
	48,500
	630,500

	4
	Installation of 2,500 m of armoured power cables (3C x 16mm² and 3C x 25mm²) with cable trays and conduits
	2,500 m
	385
	962,500

	5
	Supply and installation of 450 LED high-bay and panel lighting fixtures with emergency lighting backup
	450 Units
	2,850
	1,282,500

	6
	Installation of 2 x 500 kVA three-phase transformers with associated switchgear and protection relays
	02 Units
	1,850,000
	3,700,000

	7
	Earthing system installation including earth pits, GI pipes, copper strips, and earth resistance testing
	01 Lot
	175,000
	175,000

	8
	Lightning protection system (air terminals, down conductors, and bonding) as per IEC 62305
	01 Lot
	145,000
	145,000

	9
	Installation of 120 power and data outlets, socket outlets, and control panels across 3 floors
	120 Units
	3,200
	384,000

	10
	Testing, commissioning, and load balancing by a certified Electrical Engineer with full documentation
	01 Lot
	120,000
	120,000

	11
	Preparation of as-built drawings, operation & maintenance manuals, and handover documentation
	01 Lot
	65,000
	65,000

	12
	One-year post-commissioning warranty and 4 scheduled maintenance visits by the Electrical Engineer team
	01 Lot
	95,000
	95,000

	Subtotal
	7,664,500

	VAT @ 15% (as applicable in Bangladesh)
	1,149,675

	Grand Total (BDT)
	8,814,175


Grand Total in words: Eight Million Eight Hundred Fourteen Thousand One Hundred Seventy-Five Taka Only.
3. Project Timeline
The Electrical Engineer team from Delta Power & Electrical Consultants Ltd. estimates a total project duration of 14 weeks from the date of work order confirmation. The schedule includes 2 weeks for design and approval, 9 weeks for material procurement and installation in Bangladesh Dhaka, and 3 weeks for testing, commissioning, and final handover. A detailed Gantt chart will be submitted within 5 working days of contract signing.
4. Terms and Conditions
1. This Quotation Estimate is valid for 30 calendar days from the date of issue. After expiry, prices may be revised due to fluctuating material costs in the Bangladesh Dhaka market.
1. Payment terms: 30% advance upon signing, 40% upon completion of installation, and 30% upon successful commissioning and handover.
1. All work shall be carried out in strict compliance with the Bangladesh National Building Code (BNBC), Bangladesh Electricity Board (BEE) regulations, and applicable IEC standards.
1. The Electrical Engineer responsible for this project shall hold a valid BCE registration and a minimum of 10 years of experience in industrial electrical projects in Bangladesh.
1. All materials and equipment shall be of approved brand and shall carry the Bangladesh Standards and Testing Institution (BSTI) certification where applicable.
1. The client shall provide necessary access to the site, temporary power supply, and coordination with the local utility provider (DPDC) for connection approval in Dhaka.
1. Any variation or change order beyond the scope defined in this Quotation Estimate shall be subject to a separate written amendment and additional cost assessment.
1. Disputes arising from this engagement shall be resolved through arbitration in Dhaka, Bangladesh, in accordance with the Arbitration Act of Bangladesh.
1. This Quotation Estimate does not constitute a binding contract until a formal work order or service agreement is executed by both parties.
5. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate for Electrical Engineer services in Bangladesh Dhaka and agrees to the terms and conditions outlined herein. This acceptance does not obligate either party to enter into a formal contract until a separate agreement is executed.
For and on behalf of
Delta Power & Electrical Consultants Ltd.
Engr. Rafiqul Islam
Chief Electrical Engineer (BCE Reg. No. 4521)
Signature & Company Seal
For and on behalf of
GreenTech Industries Ltd.
Mr. Abdul Karim Chowdhury
Managing Director
Signature & Company Seal
Note: This Quotation Estimate is prepared exclusively for the client named above and is not transferable. All prices are quoted in Bangladeshi Taka (BDT) and are exclusive of any additional taxes or levies that may be imposed by the Government of Bangladesh after the date of issue. The Electrical Engineer services described herein are to be performed at the project site in Bangladesh Dhaka unless otherwise agreed in writing.
