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Quotation Details
Quotation No.: QTE-2025-AA-01147
Date Issued: 14 June 2025
Valid Until: 14 July 2025
Project Location: Ethiopia Addis Ababa
Client: [Client Name / Organization]
Project Ref: EEP-2025-0093
1. Scope of Work — Electrical Engineer Services
This Quotation Estimate is issued by the undersigned Electrical Engineer to provide comprehensive professional services for the design, review, and commissioning of electrical infrastructure at the client's facility located in Ethiopia Addis Ababa. The scope encompasses all phases of electrical engineering work as detailed below, in full compliance with the Ethiopian National Building Code, the Ethiopian Electric Utility (EEU) interconnection standards, and the International Electrotechnical Commission (IEC) guidelines adopted for use in Ethiopia.
The Electrical Engineer shall be responsible for producing all technical drawings, load calculations, single-line diagrams, cable schedule documentation, and coordination with the local electrical authority in Addis Ababa to secure the necessary permits and approvals prior to the commencement of any physical installation work.
2. Itemized Cost Breakdown
	No.
	Description of Electrical Engineer Service
	Unit
	Qty
	Unit Price (ETB)
	Total (ETB)

	1
	Site survey and load assessment at the project premises in Ethiopia Addis Ababa
	Lump Sum
	1
	45,000
	45,000

	2
	Preparation of complete electrical design package (schematics, SLD, cable schedules, lighting layout, power distribution plan)
	Lump Sum
	1
	185,000
	185,000

	3
	Structural and thermal analysis of switchgear, transformers, and distribution panels
	Hour
	32
	3,500
	112,000

	4
	Coordination and submission of design documents to the Addis Ababa City Electrical Permit Office
	Lump Sum
	1
	28,000
	28,000

	5
	On-site supervision of electrical installation works (cable pulling, panel mounting, earthing, and termination)
	Day
	22
	6,500
	143,000

	6
	Testing, commissioning, and final inspection of all electrical systems prior to handover
	Lump Sum
	1
	62,000
	62,000

	7
	Preparation of as-built documentation, operation & maintenance manuals, and warranty certificates
	Lump Sum
	1
	35,000
	35,000

	8
	Post-commissioning support and one (1) free revisit within 90 days of project completion
	Lump Sum
	1
	20,000
	20,000

	Subtotal
	630,000

	VAT (15% — Ethiopian Tax Authority)
	94,500

	GRAND TOTAL (ETB)
	724,500


Note: All prices in this Quotation Estimate are quoted in Ethiopian Birr (ETB) and are inclusive of the Electrical Engineer's professional fees, travel within Addis Ababa, and standard engineering software licensing. Any work outside the defined scope or requiring travel beyond the Addis Ababa city boundary shall be billed separately at a rate of ETB 2,500 per hour plus actual transportation costs.
3. Payment Terms
3.1 — A mobilization advance of 30% of the total Quotation Estimate value (ETB 217,350) shall be due upon signing of the service agreement and issuance of this Quotation Estimate in Ethiopia Addis Ababa.
3.2 — A progress payment of 40% (ETB 289,800) shall be due upon completion and client approval of the full electrical design package.
3.3 — The remaining balance of 30% (ETB 217,350) shall be due upon successful commissioning, final inspection sign-off, and delivery of all as-built documentation.
3.4 — All payments shall be made via bank transfer to the Electrical Engineer's designated account at Commercial Bank of Ethiopia, Bole Branch, Addis Ababa.
4. Project Timeline
The Electrical Engineer commits to completing all deliverables within a total duration of twelve (12) working weeks from the date of the signed agreement. The site survey and load assessment shall be completed within the first week. The full design package shall be delivered by the end of Week 4. On-site supervision and installation coordination shall span Weeks 5 through 10. Testing, commissioning, and final documentation shall be completed by Week 12. This timeline assumes timely client feedback and unobstructed access to the project site in Ethiopia Addis Ababa.
5. Terms and Conditions
5.1 — This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, the Electrical Engineer reserves the right to revise pricing due to material cost fluctuations or changes in the Ethiopian exchange rate.
5.2 — The Electrical Engineer shall maintain professional indemnity insurance with a minimum coverage of ETB 5,000,000 throughout the duration of the project.
5.3 — All intellectual property rights in the design documents, calculations, and engineering reports produced under this Quotation Estimate shall vest in the client upon full and final payment.
5.4 — The Electrical Engineer shall comply with all applicable labor laws, safety regulations, and environmental standards enforced by the Ethiopian Ministry of Urban and Infrastructure Development and the Addis Ababa City Administration.
5.5 — Any dispute arising from this Quotation Estimate shall be resolved through amicable negotiation. Should negotiation fail, the matter shall be referred to the Ethiopian Arbitration and Conciliation Commission in Addis Ababa.
5.6 — This Quotation Estimate does not constitute a binding contract until countersigned by both parties and the mobilization advance has been received.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Electrical Engineer services in Ethiopia Addis Ababa and agrees to the terms, conditions, pricing, and timeline set forth herein.
Prepared and Issued By:
Abel Tesfaye, M.Sc.
Licensed Electrical Engineer
Signature & Date
Accepted and Authorized By (Client):
[Client Representative Name]
[Title / Position]
Signature & Date
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