# Quotation Estimate - Electrical Engineer Services - Ethiopia Addis Ababa

# Quotation Estimate

Professional Electrical Engineer Services — Ethiopia Addis Ababa

### Prepared By

Abel Tesfaye, M.Sc. Electrical Engineering

Licensed Electrical Engineer — Ethiopian Engineering Society

License No.: EE-2019-04872

Bole Sub-City, Woreda 03, Addis Ababa, Ethiopia

Tel: +251-911-456-789 | Email: a.tesfaye@eepower.et

### Quotation Details

Quotation No.: QTE-2025-AA-01147

Date Issued: 14 June 2025

Valid Until: 14 July 2025

Project Location: Ethiopia Addis Ababa

Client: [Client Name / Organization]

Project Ref: EEP-2025-0093

## 1. Scope of Work — Electrical Engineer Services

This Quotation Estimate is issued by the undersigned Electrical Engineer to provide comprehensive professional services for the design, review, and commissioning of electrical infrastructure at the client's facility located in Ethiopia Addis Ababa. The scope encompasses all phases of electrical engineering work as detailed below, in full compliance with the Ethiopian National Building Code, the Ethiopian Electric Utility (EEU) interconnection standards, and the International Electrotechnical Commission (IEC) guidelines adopted for use in Ethiopia.

The Electrical Engineer shall be responsible for producing all technical drawings, load calculations, single-line diagrams, cable schedule documentation, and coordination with the local electrical authority in Addis Ababa to secure the necessary permits and approvals prior to the commencement of any physical installation work.

## 2. Itemized Cost Breakdown

| No. | Description of Electrical Engineer Service | Unit | Qty | Unit Price (ETB) | Total (ETB) |
| --- | --- | --- | --- | --- | --- |
| 1 | Site survey and load assessment at the project premises in Ethiopia Addis Ababa | Lump Sum | 1 | 45,000 | 45,000 |
| 2 | Preparation of complete electrical design package (schematics, SLD, cable schedules, lighting layout, power distribution plan) | Lump Sum | 1 | 185,000 | 185,000 |
| 3 | Structural and thermal analysis of switchgear, transformers, and distribution panels | Hour | 32 | 3,500 | 112,000 |
| 4 | Coordination and submission of design documents to the Addis Ababa City Electrical Permit Office | Lump Sum | 1 | 28,000 | 28,000 |
| 5 | On-site supervision of electrical installation works (cable pulling, panel mounting, earthing, and termination) | Day | 22 | 6,500 | 143,000 |
| 6 | Testing, commissioning, and final inspection of all electrical systems prior to handover | Lump Sum | 1 | 62,000 | 62,000 |
| 7 | Preparation of as-built documentation, operation & maintenance manuals, and warranty certificates | Lump Sum | 1 | 35,000 | 35,000 |
| 8 | Post-commissioning support and one (1) free revisit within 90 days of project completion | Lump Sum | 1 | 20,000 | 20,000 |
| Subtotal |  |  |  |  | 630,000 |
| VAT (15% — Ethiopian Tax Authority) |  |  |  |  | 94,500 |
| GRAND TOTAL (ETB) |  |  |  |  | 724,500 |

Note: All prices in this Quotation Estimate are quoted in Ethiopian Birr (ETB) and are inclusive of the Electrical Engineer's professional fees, travel within Addis Ababa, and standard engineering software licensing. Any work outside the defined scope or requiring travel beyond the Addis Ababa city boundary shall be billed separately at a rate of ETB 2,500 per hour plus actual transportation costs.

## 3. Payment Terms

3.1 — A mobilization advance of 30% of the total Quotation Estimate value (ETB 217,350) shall be due upon signing of the service agreement and issuance of this Quotation Estimate in Ethiopia Addis Ababa.
3.2 — A progress payment of 40% (ETB 289,800) shall be due upon completion and client approval of the full electrical design package.
3.3 — The remaining balance of 30% (ETB 217,350) shall be due upon successful commissioning, final inspection sign-off, and delivery of all as-built documentation.
3.4 — All payments shall be made via bank transfer to the Electrical Engineer's designated account at Commercial Bank of Ethiopia, Bole Branch, Addis Ababa.

## 4. Project Timeline

The Electrical Engineer commits to completing all deliverables within a total duration of twelve (12) working weeks from the date of the signed agreement. The site survey and load assessment shall be completed within the first week. The full design package shall be delivered by the end of Week 4. On-site supervision and installation coordination shall span Weeks 5 through 10. Testing, commissioning, and final documentation shall be completed by Week 12. This timeline assumes timely client feedback and unobstructed access to the project site in Ethiopia Addis Ababa.

## 5. Terms and Conditions

5.1 — This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, the Electrical Engineer reserves the right to revise pricing due to material cost fluctuations or changes in the Ethiopian exchange rate.
5.2 — The Electrical Engineer shall maintain professional indemnity insurance with a minimum coverage of ETB 5,000,000 throughout the duration of the project.
5.3 — All intellectual property rights in the design documents, calculations, and engineering reports produced under this Quotation Estimate shall vest in the client upon full and final payment.
5.4 — The Electrical Engineer shall comply with all applicable labor laws, safety regulations, and environmental standards enforced by the Ethiopian Ministry of Urban and Infrastructure Development and the Addis Ababa City Administration.
5.5 — Any dispute arising from this Quotation Estimate shall be resolved through amicable negotiation. Should negotiation fail, the matter shall be referred to the Ethiopian Arbitration and Conciliation Commission in Addis Ababa.
5.6 — This Quotation Estimate does not constitute a binding contract until countersigned by both parties and the mobilization advance has been received.

## 6. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate for Electrical Engineer services in Ethiopia Addis Ababa and agrees to the terms, conditions, pricing, and timeline set forth herein.

Prepared and Issued By:

Abel Tesfaye, M.Sc.

Licensed Electrical Engineer

Signature & Date

Accepted and Authorized By (Client):

[Client Representative Name]

[Title / Position]

Signature & Date

Quotation Estimate No. QTE-2025-AA-01147 — Electrical Engineer Professional Services — Ethiopia Addis Ababa

This document is the property of the issuing Electrical Engineer. Unauthorized reproduction or distribution is prohibited under Ethiopian Intellectual Property Law (Proclamation No. 1260/2021).

Page 1 of 1 — Generated: 14 June 2025