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1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Golden Circuit Engineering Co., Ltd. to provide a comprehensive and itemized cost breakdown for the professional services of a licensed Electrical Engineer to be deployed at the Sule Tower commercial development project located in the heart of Myanmar Yangon. This document serves as a formal Quotation Estimate outlining all deliverables, labor costs, equipment charges, and associated expenses for the electrical design, installation supervision, and commissioning phases of the project. The Electrical Engineer engaged under this Quotation Estimate shall hold a valid Myanmar Engineering Council (MEC) license and possess a minimum of fifteen (15) years of experience in commercial and high-rise building electrical systems within Myanmar Yangon and the broader Myanmar region.
2. Detailed Line Items – Quotation Estimate Breakdown
	No.
	Description of Service / Item
	Quantity
	Unit
	Unit Price (MMK)
	Total Price (MMK)

	1
	Senior Electrical Engineer – Full-time on-site supervision for electrical design review, load calculations, and single-line diagram preparation for the 18-story Sule Tower project in Myanmar Yangon
	1
	Person
	4,500,000
	4,500,000

	2
	Electrical Engineer – Design of low-voltage distribution system, lighting circuits, power outlets, and emergency backup generator interconnection per Myanmar Electrical Code and IEC standards
	1
	Lump Sum
	12,000,000
	12,000,000

	3
	Electrical Engineer – Fire alarm system, emergency lighting, and smoke detection system design and coordination with civil and mechanical engineering teams in Myanmar Yangon
	1
	Lump Sum
	8,500,000
	8,500,000

	4
	Electrical Engineer – Commissioning, testing, and certification of all electrical installations including insulation resistance testing, earth continuity testing, and thermal imaging survey
	1
	Lump Sum
	6,800,000
	6,800,000

	5
	Electrical Engineer – Preparation of as-built drawings, operation and maintenance manuals, and final compliance report for submission to Yangon City Development Committee
	1
	Lump Sum
	3,200,000
	3,200,000

	6
	Specialized testing equipment rental (megger, thermal camera, power quality analyzer) for the duration of the project in Myanmar Yangon
	4
	Months
	1,200,000
	4,800,000

	7
	Travel, accommodation, and per diem allowance for the Electrical Engineer and two (2) assistant technicians stationed at the Myanmar Yangon project site
	4
	Months
	2,500,000
	10,000,000

	8
	Project management, coordination meetings, and progress reporting (bi-weekly) to the client in Myanmar Yangon
	1
	Lump Sum
	2,000,000
	2,000,000

	SUBTOTAL
	51,800,000

	VAT (5% – Myanmar Standard Rate)
	2,590,000

	GRAND TOTAL (Quotation Estimate)
	54,390,000 MMK


3. Terms and Conditions of This Quotation Estimate
· This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Any request for services beyond this validity period shall require a revised Quotation Estimate from Golden Circuit Engineering Co., Ltd.
· Payment shall be made in Myanmar Kyat (MMK) via bank transfer to the company account at CB Bank, Hledan Branch, Myanmar Yangon. Payment schedule: 30% advance upon contract signing, 40% upon completion of design and installation supervision, and 30% upon final commissioning and handover.
· The Electrical Engineer assigned to this project shall report to the client's site manager five (5) days per week, from 8:00 AM to 5:00 PM, Monday through Friday, in accordance with standard working hours in Myanmar Yangon.
· All electrical designs and engineering deliverables shall comply with the Myanmar Electrical Code, Myanmar Building Code, and applicable International Electrotechnical Commission (IEC) standards. The Electrical Engineer shall ensure full compliance with regulations set by the Ministry of Electric Power and Energy, Republic of the Union of Myanmar.
· Any changes in scope, additional work orders, or modifications to the original project specifications in Myanmar Yangon shall be subject to a supplementary Quotation Estimate and written approval from both parties before execution.
· The Electrical Engineer and all supporting personnel shall be covered under the company's professional indemnity insurance and workers' compensation policy as mandated by Myanmar labor law.
· Confidentiality: All project data, architectural drawings, and proprietary information shared in connection with this Quotation Estimate and subsequent contract shall be treated as strictly confidential by both parties.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through amicable negotiation. If unresolved, the matter shall be referred to arbitration under the Myanmar Arbitration Law in Myanmar Yangon.
4. Project Timeline
	Phase
	Duration
	Key Deliverable

	Design & Load Calculation
	Weeks 1–4
	Approved electrical design package by the Electrical Engineer

	Installation Supervision
	Weeks 5–12
	Weekly progress reports and site inspection logs

	Commissioning & Testing
	Weeks 13–16
	Test certificates and commissioning report

	Handover & Documentation
	Week 17
	As-built drawings, O&M manuals, and final compliance certificate


Note: This Quotation Estimate is a non-binding document until a formal service agreement is executed by both parties. The Electrical Engineer services described herein are specific to the Sule Tower project in Myanmar Yangon and cannot be transferred or applied to any other project or location without a new Quotation Estimate. All prices are quoted in Myanmar Kyat (MMK) and are subject to adjustment in the event of significant changes in material costs, exchange rates, or government regulations in Myanmar.
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Mr. Aung Kyaw Min
Director
TIN: _______________
Date: _______________
