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Quotation Estimate
Professional Electrical Engineer Services — Nigeria Abuja
	Prepared For:
	Mr. Chukwuma Okafor, Procurement Manager, Federal Capital Development Authority (FCDA), Abuja, Nigeria

	Project Reference:
	FCDA/ELC/2025/0892 — Electrical Infrastructure Upgrade, Wuse 2 District

	Service Category:
	Electrical Engineer Consulting, Design, and Commissioning Services

	Project Location:
	Wuse 2, Abuja, FCT, Nigeria

	Estimated Duration:
	14 Weeks (from commencement date)


1. Scope of Work — Electrical Engineer Services
This Quotation Estimate is issued by PowerCore Engineering & Solutions Ltd. in response to the request for professional Electrical Engineer services for the electrical infrastructure upgrade project located in Wuse 2, Abuja, Nigeria. The scope of work encompasses the following deliverables and professional engagements:
· Site Survey and Assessment: A comprehensive on-site inspection of the existing electrical infrastructure in the Wuse 2 district, including load analysis, cable condition evaluation, transformer capacity review, and identification of non-compliant installations in accordance with Nigerian Electricity Regulatory Commission (NERC) standards.
· System Design and Engineering: Full electrical system design by a licensed Electrical Engineer, including single-line diagrams, load flow analysis, power factor correction calculations, earthing and lightning protection design, and cable sizing for the proposed upgrade.
· Regulatory Compliance and Permitting: Preparation and submission of all necessary documentation to the Abuja Electricity Distribution Company (AEDC), the Federal Capital Territory (FCT) Ministry of Works, and the Nigerian Institute of Electrical and Electronics Engineers (NIEE) for regulatory approval.
· Procurement Support: Technical specification preparation for all electrical equipment, including switchgear, transformers, distribution boards, cabling, and protective devices, ensuring compliance with IEC and Nigerian Standards (NS) requirements.
· Supervision and Commissioning: On-site supervision of installation works by a qualified Electrical Engineer, followed by full commissioning, testing, and handover documentation including as-built drawings and operation manuals.
· Training and Handover: A two-day training session for the client's facility management team on the operation, maintenance, and safety protocols of the upgraded electrical systems.
2. Itemized Cost Breakdown
	S/N
	Description of Service
	Duration
	Unit Cost (NGN)
	Total (NGN)

	1
	Site Survey, Load Analysis & Condition Assessment (Wuse 2, Abuja)
	2 Weeks
	1,850,000
	1,850,000

	2
	Electrical System Design & Engineering Documentation
	4 Weeks
	3,200,000
	3,200,000

	3
	Regulatory Compliance, Permitting & NIEE Certification
	3 Weeks
	1,450,000
	1,450,000

	4
	Technical Procurement Support & Equipment Specification
	2 Weeks
	980,000
	980,000

	5
	On-Site Installation Supervision by Electrical Engineer
	2 Weeks
	2,750,000
	2,750,000

	6
	Commissioning, Testing & Handover Documentation
	1 Week
	1,100,000
	1,100,000

	7
	Client Training & Knowledge Transfer (2 Days)
	2 Days
	650,000
	650,000

	Subtotal (NGN)
	11,980,000

	VAT @ 7.5% (Nigeria)
	898,500

	GRAND TOTAL (NGN)
	12,878,500


All prices are quoted in Nigerian Naira (NGN). This Quotation Estimate includes all professional fees, travel within Abuja FCT, and standard engineering software licensing. Equipment and material costs are excluded and will be procured separately by the client.
3. Terms and Conditions
3.1 Validity: This Quotation Estimate is valid for thirty (30) days from the date of issue. Beyond this period, prices may be subject to revision due to market fluctuations in Nigeria Abuja.
3.2 Payment Terms: 40% advance payment upon acceptance of this Quotation Estimate; 30% upon completion of design and regulatory approval; 30% upon successful commissioning and handover. All payments shall be made via bank transfer to the account specified on the official invoice.
3.3 Commencement: Work shall commence within five (5) business days of receipt of the advance payment and formal written approval from the client.
3.4 Professional Standards: All Electrical Engineer services shall be performed in strict compliance with the Nigerian Electricity Regulatory Commission (NERC) guidelines, the Nigerian Building and Road Research Institute (NBRRI) codes, and the standards of the Nigerian Institute of Electrical and Electronics Engineers (NIEE).
3.5 Insurance and Liability: PowerCore Engineering & Solutions Ltd. maintains professional indemnity insurance covering all Electrical Engineer services rendered in Nigeria Abuja. The client shall be responsible for third-party insurance on-site during installation works.
3.6 Dispute Resolution: Any disputes arising from this Quotation Estimate shall be resolved through arbitration in Abuja, FCT, Nigeria, in accordance with the Arbitration and Conciliation Act, Cap A18, Laws of the Federation of Nigeria 2004.
3.7 Confidentiality: All project data, design documents, and site information shared in connection with this engagement shall be treated as confidential by both parties.
4. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Electrical Engineer services in Nigeria Abuja and agrees to the terms, conditions, and pricing outlined herein. This document does not constitute a binding contract until a formal service agreement is executed by both parties.
For: PowerCore Engineering & Solutions Ltd.
Eng. Adewale B. Nwosu, M.Eng, NIEE
Lead Electrical Engineer / Managing Director
Date: ____________________
For: Federal Capital Development Authority (FCDA)
Mr. Chukwuma Okafor
Procurement Manager
Date: ____________________
Important Note: This Quotation Estimate is prepared exclusively for the project referenced above and is not transferable. All Electrical Engineer services described herein will be performed by licensed and certified professionals registered with the Nigerian Institute of Electrical and Electronics Engineers (NIEE) and the Council for the Regulation of Engineering in Nigeria (COREN). For queries regarding this Quotation Estimate, please contact our office in Nigeria Abuja at +234 (0) 803 555 7821 or info@powercoreng.com.
