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Quotation Estimate
Professional Electrical Engineer Services — Spain Valencia Region
Provider
Valencia Electrical Engineering Solutions S.L.
Av. del Cid, 142, 46003
Valencia, Spain
CIF: B-98765432
Tel: +34 963 456 789
Email: info@valencia-ees.com
Client
Construcciones Mediterráneas S.A.
C/ Colón, 87, 46004
Valencia, Spain
CIF: A-12345678
Tel: +34 963 111 222
Email: projects@constrmed.com
	Quotation Estimate No.:
	QTE-2025-VA-0047

	Date of Issue:
	15 June 2025

	Validity Period:
	30 calendar days from date of issue

	Project Location:
	Spain Valencia — Polígono Industrial de Paterna, Valencia Province

	Project Reference:
	Industrial Facility Electrical Installation & Compliance Audit


1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Valencia Electrical Engineering Solutions S.L. to Construcciones Mediterráneas S.A. in relation to the provision of comprehensive Electrical Engineer services for the industrial facility located in the Polígono Industrial de Paterna, within the Spain Valencia metropolitan area. This document outlines the full scope of professional engineering work, associated costs, payment terms, and conditions under which our firm will deliver the contracted services. All pricing and technical specifications contained within this Quotation Estimate are based on the current regulatory framework governing electrical installations in the autonomous community of Valencia and the broader Spanish national standards (IEC 60364, RD 842/2002, and the applicable CTE — Código Técnico de la Edificación).
2. Scope of Work — Electrical Engineer Services in Spain Valencia
Our team of licensed Electrical Engineer professionals will carry out the following activities at the designated site in Spain Valencia:
	Ref.
	Description of Service
	Duration
	Unit
	Amount (EUR)

	01
	Full-site electrical installation design and schematic drafting for the new 12,000 m² industrial warehouse, including power distribution, lighting, and emergency systems, prepared by a senior Electrical Engineer registered with the COIECV (Colegio Oficial de Ingenieros Eléctricos de la Comunidad Valenciana).
	45 working days
	1 lot
	18,500.00

	02
	On-site supervision and technical direction of the electrical works, ensuring compliance with all Spain Valencia municipal building regulations and national electrical codes. Includes weekly progress reports and coordination meetings with the general contractor.
	90 working days
	1 lot
	22,000.00

	03
	Comprehensive electrical compliance audit and certification preparation (Boletín Eléctrico) for the existing 8,500 m² annex building. The Electrical Engineer will perform thermographic inspections, insulation resistance testing, and earthing continuity verification.
	10 working days
	1 lot
	6,800.00

	04
	Design and specification of the photovoltaic solar energy system (250 kWp) to be installed on the warehouse roof, including grid-connection documentation for the local distribution operator (Endesa) and the Spain Valencia regional energy authority (AVEM).
	30 working days
	1 lot
	9,200.00

	05
	Preparation of the complete technical dossier for the municipal building permit (Licencia de Obra Mayor) submission to the Ayuntamiento de Paterna, including all electrical plans, load calculations, and safety assessments required under Spain Valencia urban planning regulations.
	15 working days
	1 lot
	4,500.00

	06
	Post-completion testing, commissioning, and final as-built documentation. The responsible Electrical Engineer will issue the final technical report and sign the certificate of conformity (Certificado de Instalación Eléctrica) as mandated by Spanish law.
	7 working days
	1 lot
	3,800.00

	Subtotal (Excluding VAT)
	64,800.00

	VAT (IVA) — 21%
	13,608.00

	Total Amount Due (Including VAT)
	78,408.00


3. Payment Terms
Payment for the services described in this Quotation Estimate shall be made in the following instalments: 30% upon signing of the service contract, 40% upon completion of the design and audit phases (Items 01, 03, and 04), and the remaining 30% upon delivery of the final commissioning report and certificate of conformity (Item 06). All payments shall be made by bank transfer to the account of Valencia Electrical Engineering Solutions S.L. within 30 days of invoice receipt. Late payments shall accrue interest at the rate established by the Spanish Ley 3/2004 on late payment in commercial transactions.
4. Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, prices and availability may be subject to revision.
1. All Electrical Engineer services shall be performed in strict accordance with the Spanish Electrical Regulations (Reglamento Electrotécnico de Baja Tensión — REBT), the applicable CTE documents, and the specific urban planning norms of the Spain Valencia region.
1. The client shall provide full access to the site in Spain Valencia and all existing technical documentation necessary for the execution of the works. Delays caused by the client's failure to provide access or information shall extend the project timeline accordingly without additional cost to the provider.
1. Any variation in scope beyond the items listed in this Quotation Estimate shall be subject to a supplementary written agreement and a revised cost assessment prior to commencement of the additional work.
1. The Electrical Engineer responsible for this project holds a valid professional registration with the COIECV and carries professional liability insurance with a coverage of no less than 1,000,000 EUR, as required by Spanish professional practice regulations.
1. All intellectual property rights in the design documents, schematics, and technical reports produced under this contract shall vest in the client upon full payment of the total amount specified in this Quotation Estimate.
1. Disputes arising from this agreement shall be resolved through the competent courts of Valencia, Spain, in accordance with the applicable provisions of the Spanish Civil Code and the Ley de Arrendamientos Urbanos where relevant.
1. This Quotation Estimate does not constitute a binding contract until both parties have executed a formal service agreement incorporating the terms herein.
5. Acceptance and Signatures
By signing below, both parties acknowledge that they have read, understood, and agree to the terms set forth in this Quotation Estimate for Electrical Engineer services to be carried out in Spain Valencia.
For Valencia Electrical Engineering Solutions S.L.
Name: Ing. Carlos Martínez Sánchez
Title: Lead Electrical Engineer / Director
Date: ______________________
For Construcciones Mediterráneas S.A.
Name: ______________________
Title: ______________________
Date: ______________________
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