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QUOTATION ESTIMATE
Professional Electrical Engineer Services — Switzerland Zurich Region
Prepared For (Client)
Name: Zürichsee Properties GmbH
Address: Seefeldstrasse 18, 8008 Zurich, Switzerland
Contact: Mr. Thomas Keller, Facility Director
Email: t.keller@zuerichsee-props.ch
Prepared By (Provider)
Name: Dr. Markus Steiner, Lead Electrical Engineer
Company: Helvetia Electrical Engineering AG
Address: Bahnhofstrasse 42, 8001 Zurich, Switzerland
License: SIA Certified Electrical Engineer, Canton of Zurich
1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Helvetia Electrical Engineering AG to provide a comprehensive and transparent cost breakdown for the professional services of a licensed Electrical Engineer engaged to perform a full-scale electrical infrastructure assessment, modernization planning, and regulatory compliance audit for the client's commercial property portfolio located in Switzerland Zurich. This document serves as a formal estimate of all anticipated costs, deliverables, and timelines associated with the engagement, and is valid for a period of thirty (30) calendar days from the date of issue.
The scope of work encompasses the complete electrical systems review of three (3) commercial buildings situated in the city of Zurich, including but not limited to the main distribution panels, sub-distribution boards, emergency lighting systems, fire alarm wiring, HVAC electrical controls, and the building's connection to the local Swissgrid distribution network. All work will be conducted in strict accordance with the Swiss Electrical Installation Regulations (SEV/BS 71), the Canton of Zurich building codes, and the applicable SIA (Swiss Society of Engineers) standards.
2. Detailed Cost Breakdown
	Item No.
	Description of Service
	Duration / Qty
	Unit Rate (CHF)
	Amount (CHF)

	01
	On-site electrical inspection and diagnostic assessment by a senior Electrical Engineer at all three Zurich locations
	3 days
	1,200.00
	3,600.00

	02
	Thermal imaging survey of all main and sub-distribution panels
	2 days
	950.00
	1,900.00

	03
	Preparation of detailed as-built electrical drawings and single-line diagrams
	5 days
	850.00
	4,250.00

	04
	Regulatory compliance audit against SEV/BS 71 and Canton of Zurich electrical codes
	3 days
	1,100.00
	3,300.00

	05
	Modernization and upgrade planning report with phased implementation roadmap
	4 days
	1,050.00
	4,200.00

	06
	Energy efficiency analysis and Swissgrid integration optimization study
	2 days
	1,300.00
	2,600.00

	07
	Client presentation, Q&A session, and final report delivery in Zurich
	1 day
	750.00
	750.00

	08
	Travel, accommodation, and local transport within the Switzerland Zurich metropolitan area
	Flat rate
	—
	1,200.00

	Subtotal (excl. VAT)
	21,800.00

	VAT (7.7% – Swiss standard rate)
	1,678.60

	TOTAL ESTIMATED COST (incl. VAT)
	23,478.60


3. Project Timeline
The Electrical Engineer team will mobilize on-site in Switzerland Zurich within ten (10) business days of written acceptance of this Quotation Estimate. The total estimated project duration is twenty (20) business days, with the final deliverable package (comprising all reports, drawings, and the compliance certificate) to be submitted to the client no later than the end of the engagement period. A detailed Gantt chart and milestone schedule will be provided as an annex upon contract signing.
4. Terms and Conditions
1. This Quotation Estimate is a non-binding estimate of costs and does not constitute a contractual obligation until a formal service agreement is executed by both parties.
1. All rates are quoted in Swiss Francs (CHF) and are inclusive of the applicable 7.7% Swiss Value Added Tax (VAT) as indicated in the cost breakdown above.
1. The Electrical Engineer services described herein are to be performed exclusively within the canton and city of Switzerland Zurich. Any work extending beyond this geographic scope will be subject to a separate supplementary estimate.
1. Payment terms: 30% advance payment upon acceptance of this Quotation Estimate, 40% upon completion of the on-site inspection phase, and the remaining 30% upon delivery and acceptance of the final report package.
1. All invoices are payable within thirty (30) days of the invoice date. Late payments shall accrue interest at the rate of 5% per annum in accordance with Swiss Code of Obligations (OR) Article 104.
1. The client agrees to provide reasonable access to all three properties, including locked electrical rooms, during the agreed working hours (Monday to Friday, 08:00–17:00 CET).
1. Helvetia Electrical Engineering AG shall maintain full professional liability insurance (minimum CHF 5,000,000) and professional indemnity coverage throughout the duration of the engagement in Switzerland Zurich.
1. Any changes to the scope of work requested by the client after the initial acceptance will be documented in a written change order and may result in an amended Quotation Estimate.
1. This Quotation Estimate shall be governed by and construed in accordance with the laws of the Swiss Confederation, with jurisdiction vested in the courts of the Canton of Zurich.
1. Confidentiality: All data, drawings, and findings generated during the engagement shall be treated as strictly confidential and shall not be disclosed to third parties without prior written consent from the client.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and confirms that the scope, costs, and terms outlined herein are understood and accepted. The engagement of the Electrical Engineer services in Switzerland Zurich shall commence upon receipt of the advance payment and a signed service agreement.
For Helvetia Electrical Engineering AG
Dr. Markus Steiner
Lead Electrical Engineer
Date: ____________________
For Zürichsee Properties GmbH (Client)
Mr. Thomas Keller
Facility Director
Date: ____________________
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