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	Quotation Estimate No.
	QE-ELE-2025-04782
	Date of Issue
	15 June 2025

	Valid Until
	15 July 2025 (30 calendar days)
	Currency
	United Arab Emirates Dirham (AED)

	Prepared By
	Eng. Khalid Al Mansoori, P.E. — Lead Electrical Engineer
	Company
	Gulf Electrical Engineering Consultants LLC, Abu Dhabi, UAE

	Client / Recipient
	Al Noor Development Group, Al Reem Island, Abu Dhabi, United Arab Emirates
	Project Site
	Al Reem Island, Abu Dhabi, United Arab Emirates


1. Scope of Work — Electrical Engineer Services
This Quotation Estimate is issued by Gulf Electrical Engineering Consultants LLC to provide comprehensive Electrical Engineer professional services for the Al Noor Residential Tower project located in Abu Dhabi, United Arab Emirates. The scope encompasses all phases of electrical design, coordination, site supervision, and commissioning support in full compliance with Abu Dhabi Municipal Authority (ADMA) regulations, the Abu Dhabi Electricity & Water Authority (ADEWA) codes, and the International Electrotechnical Commission (IEC) standards adopted across the United Arab Emirates.
The Electrical Engineer team assigned to this project will deliver end-to-end technical oversight, ensuring that all electrical infrastructure meets the highest safety, efficiency, and sustainability benchmarks required for commercial and residential developments in Abu Dhabi, United Arab Emirates.
2. Itemised Cost Breakdown
	Ref
	Description of Electrical Engineer Service
	Duration / Qty
	Unit Rate (AED)
	Amount (AED)

	01
	Conceptual electrical design and load calculation for a 32-storey residential tower, including single-line diagrams, power distribution layout, and lighting design. Performed by a senior Electrical Engineer registered with the Abu Dhabi Department of Municipalities.
	1 Lot
	185,000.00
	185,000.00

	02
	Detailed electrical engineering design package: low-voltage (LV) and medium-voltage (MV) switchgear schedules, cable sizing, earthing and lightning protection design, fire alarm and emergency lighting systems, and building management system (BMS) integration. All drawings prepared to ADMA and ADEWA specifications for Abu Dhabi, United Arab Emirates.
	1 Lot
	320,000.00
	320,000.00

	03
	Coordination with mechanical, civil, and architectural disciplines; clash detection using BIM (Building Information Modelling) software; and preparation of as-built documentation. The Electrical Engineer will attend weekly coordination meetings at the client’s office in Abu Dhabi.
	12 Months
	45,000.00
	540,000.00

	04
	Site supervision and quality assurance: daily inspection of electrical installations, verification of cable pulling, termination, and testing of all electrical equipment. The supervising Electrical Engineer will be present on-site in Abu Dhabi, United Arab Emirates, for a minimum of 5 days per week throughout the construction phase.
	18 Months
	38,000.00
	684,000.00

	05
	Commissioning and handover support: performance testing of all electrical systems, preparation of test and inspection reports, defect rectification tracking, and final handover documentation submission to Abu Dhabi Municipality and ADEWA for occupancy permit issuance in the United Arab Emirates.
	3 Months
	52,000.00
	156,000.00

	06
	Energy efficiency audit and sustainability consulting: preparation of an energy performance report aligned with the Abu Dhabi 2030 Urban Planning Strategy and the UAE Net Zero 2050 initiative. Includes recommendations for LED retrofitting, smart metering, and renewable energy integration.
	1 Lot
	75,000.00
	75,000.00

	07
	Regulatory liaison and permit processing: submission of all electrical design packages to Abu Dhabi Municipality, ADEWA, and Civil Defence; attendance at inspection meetings; and management of approval workflows specific to the United Arab Emirates Abu Dhabi jurisdiction.
	1 Lot
	48,000.00
	48,000.00


	Subtotal
	AED 1,008,000.00

	VAT (5% — UAE Federal Tax Authority)
	AED 50,400.00

	Applicable Municipal Fees (Abu Dhabi)
	AED 22,160.00

	Grand Total
	AED 1,080,560.00


3. Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on prevailing market conditions in the United Arab Emirates Abu Dhabi construction sector.
1. All Electrical Engineer services described herein shall be performed by qualified professionals holding valid engineering licences issued by the Abu Dhabi Department of Municipalities and Transport (DMT) and registered with the UAE Council of Engineers.
1. Payment terms: 30% advance upon acceptance of this Quotation Estimate, 40% upon completion of the detailed design phase, 20% upon completion of site supervision, and 10% upon final handover and issuance of the occupancy permit in Abu Dhabi, United Arab Emirates.
1. All invoices shall be payable within twenty-one (21) days of receipt. Late payments shall attract interest at the rate of 1.5% per month as per UAE commercial law.
1. The Electrical Engineer team shall maintain full professional indemnity insurance with a minimum coverage of AED 5,000,000, valid throughout the project duration in Abu Dhabi, United Arab Emirates.
1. Any variation or change order to the scope of work must be agreed in writing by both parties before execution. The Quotation Estimate does not include works outside the defined scope unless explicitly amended.
1. This Quotation Estimate and all associated services shall be governed by and construed in accordance with the laws of the United Arab Emirates, with jurisdiction vested in the courts of Abu Dhabi.
1. All intellectual property, design documents, and engineering drawings produced under this engagement shall become the property of the client upon full payment.
1. The Electrical Engineer services are subject to the client providing timely access to the project site in Abu Dhabi, United Arab Emirates, and furnishing all necessary architectural and structural drawings within the agreed timelines.
4. Acceptance and Authorisation
For and on behalf of:
Gulf Electrical Engineering Consultants LLC
Abu Dhabi, United Arab Emirates
Name: Eng. Khalid Al Mansoori, P.E.
Title: Lead Electrical Engineer / Managing Director
Signature & Company Stamp: _________________________
Date: _________________________
Accepted by (Client):
Al Noor Development Group
Al Reem Island, Abu Dhabi, UAE
Name: _________________________
Title: _________________________
Signature & Company Stamp: _________________________
Date: _________________________
Important Note: This Quotation Estimate constitutes a formal offer for Electrical Engineer professional services in Abu Dhabi, United Arab Emirates. It does not constitute a binding contract until countersigned by both parties. All figures are quoted in United Arab Emirates Dirhams (AED) and are inclusive of the applicable 5% Value Added Tax (VAT) as mandated by the Federal Tax Authority of the UAE. For queries regarding this Quotation Estimate, please contact our office at +971-2-555-0147 or email estimates@gulf-electrical-ae.com. We look forward to delivering excellence in electrical engineering for your project in the United Arab Emirates Abu Dhabi.
