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QTE-2025-0047 Valid: 30 Days
Provider:
Gulf Electrical Engineering Solutions LLC
Office 1204, Level 12, Burj Khalifa
Downtown Dubai, United Arab Emirates
Tel: +971 4 555 0192
Email: quotations@gulf-electrical-ae.com
Trade License No: 1048723
VAT Registration No: 100487230000005
Client:
Al Noor Development Group FZ
Plot 45, Industrial Area 3
Jebel Ali Free Zone, Dubai
United Arab Emirates
Contact: Mr. Khalid Al Mansoori
Tel: +971 50 778 3341
Email: k.mansoori@alnoor-dev.ae
1. Quotation Estimate Summary
This Quotation Estimate is issued by Gulf Electrical Engineering Solutions LLC for the provision of comprehensive Electrical Engineer consulting, design, and supervision services to be executed within the jurisdiction of United Arab Emirates Dubai. This document outlines the full scope of professional services, associated costs, project timelines, and contractual terms governing the engagement. All pricing is quoted in United Arab Emirates Dirhams (AED) and is subject to the applicable 5% Value Added Tax (VAT) as mandated by the Federal Tax Authority of the United Arab Emirates.
2. Scope of Work — Electrical Engineer Services
The Electrical Engineer team assigned to this project shall deliver the following professional services in full compliance with the Dubai Electricity and Water Authority (DEWA) regulations, the Emirates Building Code (EBC), and all applicable standards of the United Arab Emirates Ministry of Energy and Infrastructure:
· Electrical Load Assessment & Feasibility Study: Complete analysis of existing and projected electrical loads for the client's commercial facility located in Dubai Internet City, United Arab Emirates Dubai. This includes demand forecasting, power factor analysis, and single-line diagram preparation.
· Electrical System Design & Engineering: Detailed design of the low-voltage (LV) and medium-voltage (MV) distribution systems, including transformer sizing, switchgear selection, cable routing, and earthing/grounding architecture. All designs shall conform to IEC 60364, BS 7671, and DEWA technical specifications.
· Power Distribution & Protection Engineering: Design of main and sub-distribution boards, circuit protection coordination studies, and selective tripping calculations to ensure maximum system reliability and personnel safety.
· Lighting & Power Outlet Design: Comprehensive lighting layout design incorporating energy-efficient LED solutions, emergency lighting, and power outlet distribution in accordance with Dubai Municipality building regulations.
· Earthing, Lightning Protection & Surge Protection: Engineering of the earthing grid, lightning protection system (LPS) per IEC 62305, and surge protective device (SPD) coordination for all critical electrical infrastructure.
· DEWA Connection & Compliance Documentation: Preparation and submission of all necessary technical documentation, as-built drawings, and compliance certificates required for DEWA power connection approval in United Arab Emirates Dubai.
· Site Supervision & Commissioning Support: On-site supervision by a qualified Electrical Engineer during installation, testing, and commissioning phases, including preparation of test reports and punch-list resolution.
3. Itemized Cost Breakdown
	Ref
	Description of Electrical Engineer Service
	Quantity
	Unit (AED)
	Amount (AED)
	Duration

	01
	Electrical Load Assessment & Feasibility Study Report
	1 Lot
	18,500.00
	18,500.00
	10 Working Days

	02
	MV & LV Electrical System Design (including AutoCAD drawings, load schedules, and cable schedules)
	1 Lot
	42,000.00
	42,000.00
	20 Working Days

	03
	Power Distribution & Protection Coordination Study
	1 Lot
	15,750.00
	15,750.00
	8 Working Days

	04
	Lighting Design & Energy Efficiency Analysis (DIALux / Relux)
	1 Lot
	12,300.00
	12,300.00
	7 Working Days

	05
	Earthing, LPS & SPD Engineering Design
	1 Lot
	9,800.00
	9,800.00
	5 Working Days

	06
	DEWA Application Support & Compliance Documentation Package
	1 Lot
	7,500.00
	7,500.00
	5 Working Days

	07
	On-Site Electrical Engineer Supervision (Installation & Commissioning Phase)
	25 Days
	1,200.00
	30,000.00
	25 Working Days

	08
	Testing, Commissioning Reports & As-Built Documentation
	1 Lot
	8,950.00
	8,950.00
	5 Working Days

	Subtotal (AED)
	144,800.00
	

	VAT @ 5% (AED)
	7,240.00
	

	TOTAL QUOTATION ESTIMATE (AED)
	152,040.00
	


4. Payment Terms
· 30% advance payment upon acceptance of this Quotation Estimate and execution of the service agreement.
· 40% upon completion and client approval of all design deliverables (Items 01–06).
· 30% upon successful commissioning, submission of as-built documents, and final DEWA approval.
· All payments shall be made via bank transfer to the provider's designated account in Dubai, United Arab Emirates. Invoices are payable within 14 calendar days of issue.
5. Terms & Conditions
· This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision due to material cost fluctuations or regulatory changes in United Arab Emirates Dubai.
· All Electrical Engineer services shall be performed by licensed and certified professionals registered with the Dubai Municipality and holding valid UAE professional practice certificates.
· The provider shall maintain comprehensive professional indemnity insurance with a minimum coverage of AED 5,000,000, valid throughout the project duration.
· Any changes to the scope of work beyond the originally agreed deliverables shall be subject to a separate variation order and additional Quotation Estimate.
· This engagement is governed by the laws of the United Arab Emirates, and any disputes shall be resolved through the Dubai Courts or, at the client's election, the Dubai International Arbitration Centre (DIAC).
· The provider reserves the right to withhold final deliverables until all outstanding invoices have been settled in full.
· All intellectual property rights in the design documents, calculations, and reports prepared by the Electrical Engineer team shall transfer to the client upon full payment of the total Quotation Estimate amount.
6. Project Timeline
The total estimated project duration from the date of commencement to final handover is approximately eight (8) calendar weeks, subject to timely client approvals, DEWA processing times, and availability of site access in United Arab Emirates Dubai. A detailed Gantt chart and milestone schedule shall be provided within five (5) working days of contract execution.
For and on behalf of:
Gulf Electrical Engineering Solutions LLC
Eng. Salem Al Rashidi
Lead Electrical Engineer / Project Director
UAE Professional License No: 2019-EE-44821
Date: _______________
Accepted by (Client):
Al Noor Development Group FZ
Mr. Khalid Al Mansoori
Project Manager
Date: _______________
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