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QUOTATION ESTIMATE
Professional Electrician Services
Ethiopia Addis Ababa | Bole Sub-City, Woreda 03
License No: ET-ELEC-2024-0847 | TIN: 0012345678
Quotation No: QTE-2025-0312
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Prepared By: Addis Electrical Solutions PLC
Contact: +251-11-662-3456
Email: info@addiselectrical.et
Prepared For: Mr. Tesfaye Alemu
Address: 4th Avenue, Bole, Addis Ababa
Project: Residential Electrical Installation
1. Introduction and Scope of Work
This Quotation Estimate is formally issued by Addis Electrical Solutions PLC, a licensed and registered Electrician service provider operating within Ethiopia Addis Ababa. This document outlines the comprehensive scope of electrical work, associated costs, timelines, and terms governing the proposed project for the client's residential property located in the Bole Sub-City area of Addis Ababa.
Our team of certified Electrician professionals has conducted a thorough site assessment of the property on 10 June 2025. Based on the findings, we have prepared this detailed Quotation Estimate to ensure full transparency regarding all costs, materials, and labor involved in the complete electrical installation and renovation project. All work will be performed in strict compliance with the Ethiopian National Electrical Code, the standards set by the Ethiopian Electric Utility (EEU), and the building regulations of the Addis Ababa City Administration.
2. Detailed Cost Breakdown
	Item No.
	Description of Work / Material
	Unit
	Quantity
	Unit Price (ETB)
	Total (ETB)

	1
	Removal of existing outdated wiring and electrical fixtures
	Lot
	1
	18,500
	18,500

	2
	Supply and installation of 2.5mm² copper wiring (Nigera brand)
	Roll (100m)
	4
	12,800
	51,200

	3
	Supply and installation of 4mm² copper wiring for main distribution
	Roll (100m)
	2
	22,400
	44,800

	4
	Installation of new 63A main distribution board with RCD protection
	Set
	1
	38,000
	38,000

	5
	Supply and installation of 16A MCB circuit breakers (Schneider Electric)
	Piece
	12
	3,200
	38,400

	6
	Installation of PVC conduit piping (25mm and 32mm diameter)
	Running meter
	180
	450
	81,000

	7
	Supply and installation of LED ceiling light fixtures (18W)
	Piece
	14
	2,800
	39,200

	8
	Installation of wall-mounted electrical sockets and switches (13A)
	Piece
	28
	1,150
	32,200

	9
	Installation of dedicated circuit for air conditioning units (2 units)
	Lot
	1
	28,500
	28,500

	10
	Earthing and grounding system installation (copper rod, 2.4m)
	Set
	1
	24,000
	24,000

	11
	Installation of surge protection device (SPD) at main panel
	Piece
	1
	15,500
	15,500

	12
	Electrical inspection, testing, and certification by licensed Electrician
	Lot
	1
	12,000
	12,000

	13
	Waste disposal and site cleanup
	Lot
	1
	5,500
	5,500

	SUBTOTAL
	388,800

	VAT (15% - Ethiopian Tax Authority)
	58,320

	GRAND TOTAL (ETB)
	447,120


3. Project Timeline
The estimated duration for the completion of all electrical works outlined in this Quotation Estimate is 12 to 15 working days, commencing from the date of contract signing and receipt of the initial payment. Our Electrician crew, consisting of four (4) skilled technicians and one (1) supervising master electrician, will be deployed on-site throughout the project duration. Work will be conducted Monday through Saturday, from 08:00 to 17:00 EAT (East Africa Time), in accordance with the labor regulations of Ethiopia Addis Ababa.
Phase 1 (Days 1–3): Removal of old wiring, demolition of existing fixtures, and preparation of conduit pathways.
Phase 2 (Days 4–8): Installation of new wiring, conduit piping, and distribution board.
Phase 3 (Days 9–12): Installation of all fixtures, sockets, switches, and dedicated circuits.
Phase 4 (Days 13–15): Earthing, surge protection, final inspection, testing, and handover.
4. Payment Terms
The total amount of ETB 447,120 (Four Hundred Forty-Seven Thousand One Hundred Twenty Ethiopian Birr) shall be paid as follows:
· 30% Advance Payment (ETB 134,136): Due upon signing of the service agreement and before commencement of work.
· 40% Progress Payment (ETB 178,848): Due upon completion of Phase 2 (wiring and distribution board installation).
· 30% Final Payment (ETB 134,136): Due upon successful completion, final inspection, and handover of the project.
All payments shall be made via bank transfer to Addis Electrical Solutions PLC, CBE Account No. 1001-XXXX-XXXX, or by certified bank draft. Cash payments exceeding ETB 50,000 are not accepted in compliance with Ethiopian financial regulations.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, prices may be subject to revision due to market fluctuations in material costs within Ethiopia Addis Ababa.
· All materials specified in this estimate are of premium quality and sourced from authorized distributors in Addis Ababa. Substitutions will only be made with prior written consent from the client.
· The Electrician services provided carry a warranty of two (2) years on workmanship and one (1) year on all installed materials, in accordance with Ethiopian consumer protection law.
· The client is responsible for obtaining all necessary building permits and electrical connection approvals from the Ethiopian Electric Utility (EEU) office in Addis Ababa prior to the start of work.
· Any additional work not specified in this Quotation Estimate will be billed separately at the standard hourly rate of ETB 2,500 per technician per hour, subject to a minimum charge of four (4) hours.
· In the event of force majeure (including but not limited to power outages exceeding 48 hours, natural disasters, or government-mandated shutdowns in Addis Ababa), the project timeline shall be extended accordingly without penalty to either party.
· All disputes arising from this agreement shall be resolved through mediation in accordance with the Ethiopian Commercial Code, with jurisdiction in the Addis Ababa City Courts.
6. Acceptance and Authorization
By signing below, the client acknowledges that they have read, understood, and accepted all terms, conditions, and pricing outlined in this Quotation Estimate for Electrician services to be performed in Ethiopia Addis Ababa. This signature constitutes a binding agreement between both parties.
For: Addis Electrical Solutions PLC
Name: Eng. Dawit Bekele
Title: Chief Electrician / Project Manager
Date: _______________
For: The Client
Name: Mr. Tesfaye Alemu
Title: Property Owner
Date: _______________
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