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Quotation Estimate
Professional Electrician Services — Senegal Dakar
Document Ref: QE-SEN-DKR-2025-0472
Provider:
SENELEC Électrique SARL
14, Avenue Cheikh Anta Diop
Plateau, Dakar, Senegal
Tel: +221 33 849 2210
Email: contact@senelec-electrique.sn
RC: SN-DKR-2019-44821
Client:
M. Ibrahima Ndiaye
Résidence Les Palmiers, Bât. C
Almadies, Dakar, Senegal
Tel: +221 77 654 3321
Email: i.ndiaye@email.sn
Quotation Estimate Details
	Quotation Estimate No.:
	QE-SEN-DKR-2025-0472
	Date Issued:
	15 June 2025

	Valid Until:
	15 July 2025 (30 days)
	Project Location:
	Almadies, Dakar, Senegal

	Electrician Lead:
	Mr. Ousmane Fall (Certified, N° 4421-SN)
	Est. Duration:
	12 working days


Scope of Work — Electrician Services in Senegal Dakar
This Quotation Estimate is issued by SENELEC Électrique SARL, a licensed and registered Electrician firm operating in Senegal Dakar, to provide comprehensive electrical installation, inspection, and maintenance services for the residential property located in Almadies, Dakar. All work shall comply with the Senegalese electrical code (Norme Sènégalaise — NS 04-001), the regulations of SENELEC (Société Nationale d'Electricité du Sénégal), and the applicable standards of the West African Economic and Monetary Union (WAEMU/UEMOA). The Electrician team assigned to this project in Senegal Dakar shall ensure full compliance with all local safety and regulatory requirements.
Itemized Quotation Estimate Breakdown
	#
	Description of Electrician Work
	Quantity
	Unit (XOF)
	Total (XOF)
	Duration

	1
	Complete electrical wiring inspection and diagnostic assessment of the 3-bedroom residence in Almadies, Dakar
	1 lot
	185,000
	185,000
	Day 1

	2
	Replacement of main electrical distribution panel (tableau électrique) with a 40A rated panel, including 12 new circuit breakers (disjoncteurs)
	1 set
	420,000
	420,000
	Days 2–3

	3
	Installation of 24 new electrical outlets (prises) and 18 light switches (interrupteurs) throughout the residence, including wall preparation
	42 units
	12,500
	525,000
	Days 4–7

	4
	Replacement of all internal electrical cabling (câblage) with 2.5mm² copper wire (type THHN) for lighting circuits and 4mm² for power circuits
	350 meters
	3,800
	1,330,000
	Days 5–9

	5
	Installation of 12 LED lighting fixtures (spots encastrés) in living room, kitchen, and 3 bedrooms, plus 4 ceiling fans with integrated lights
	16 units
	45,000
	720,000
	Days 8–10

	6
	Installation of a dedicated 3-phase power circuit for air conditioning units (2 split systems) with dedicated 32A breakers and 6mm² cabling
	2 circuits
	380,000
	760,000
	Days 9–11

	7
	Installation of a 63A main earthing and lightning protection system (parafoudre) compliant with Senegal Dakar coastal zone requirements
	1 system
	550,000
	550,000
	Days 10–11

	8
	Installation of a 5kVA inverter/UPS backup power system with 4x 200Ah deep-cycle batteries for essential circuits during SENELEC outages
	1 system
	1,850,000
	1,850,000
	Days 11–12

	9
	Final testing, commissioning, and submission of as-built electrical diagrams to the client and SENELEC inspection office in Dakar
	1 lot
	250,000
	250,000
	Day 12

	10
	Waste removal, site cleanup, and disposal of old electrical materials in accordance with Dakar municipal regulations
	1 lot
	120,000
	120,000
	Day 12

	Subtotal (XOF)
	6,910,000
	

	VAT (TVA) — 18% (Senegal)
	1,243,800
	

	TOTAL QUOTATION ESTIMATE (XOF)
	8,153,800
	


Terms and Conditions of This Quotation Estimate
· This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, the Electrician rates and material costs listed herein may be subject to revision due to market fluctuations in Senegal Dakar.
· Payment terms: 40% advance payment upon acceptance of this Quotation Estimate, 40% upon completion of cabling and panel installation (Day 9), and 20% upon final commissioning and handover (Day 12). All payments shall be made in West African CFA Francs (XOF) via bank transfer to SENELEC Électrique SARL, Bank of Africa (BOA), Dakar branch.
· The Electrician team shall work Monday through Saturday, 08:00 to 17:00, in accordance with standard working hours in Senegal Dakar. Any work required outside these hours or on public holidays shall be billed at 1.5x the standard rate.
· All materials specified in this Quotation Estimate shall be new, of certified quality, and sourced from approved suppliers in Dakar. The Electrician guarantees all workmanship for a period of twenty-four (24) months from the date of final acceptance.
· The client is responsible for obtaining any necessary permits from the Mairie de Dakar and SENELEC prior to the commencement of work. The Electrician shall provide all technical documentation required for such permits at no additional cost.
· Any additional work not included in this Quotation Estimate shall be subject to a separate written amendment signed by both parties before execution.
· This Quotation Estimate does not constitute a binding contract until formally accepted in writing by the client and countersigned by the authorized representative of SENELEC Électrique SARL.
Acceptance and Signatures
By signing below, the client acknowledges receipt of this Quotation Estimate for Electrician services in Senegal Dakar and agrees to the terms and conditions outlined above. The Electrician firm confirms its commitment to deliver all specified work in accordance with the scope, timeline, and quality standards described herein.
Client Signature & Date
M. Ibrahima Ndiaye
Electrician / Authorized Representative
Mr. Ousmane Fall
SENELEC Électrique SARL
SENELEC Électrique SARL — Professional Electrician Services in Senegal Dakar — Plateau, Dakar, Sénégal
This Quotation Estimate document QE-SEN-DKR-2025-0472 is issued exclusively for the client named above. All prices are in XOF (Franc CFA). © 2025 SENELEC Électrique SARL. All rights reserved.
