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Quotation Estimate
Professional Electrician Services — Madrid, Spain
Ref: QTE-MAD-2025-04782
Service Provider
Madrid Electric Solutions S.L.
Calle de Alcalá 124, 3ºB
28009 Madrid, Spain
Tel: +34 91 555 2347
Email: info@madridelectricsolutions.es
CIF: B-87654321
Col. Electricista: COEM-4521
Client Details
Don Alejandro Martínez Ruiz
Calle de Serrano 87, 5ºA
28006 Madrid, Spain
Tel: +34 612 345 678
Email: a.martinez@email.com
DNI: 12345678Z
Quotation Details
Date of Issue: 15 June 2025
Valid Until: 15 July 2025 (30 days)
Project Location: Calle de Serrano 87, 5ºA, 28006 Madrid
Estimated Start Date: 23 June 2025
Estimated Duration: 5 working days
Scope Summary
Complete electrical installation renovation and compliance upgrade for a residential apartment in the Salamanca district of Madrid, Spain, in accordance with the current Low Voltage Installations Regulation (Reglamento de Instalaciones Electrotécnicas de Baja Tensión — RIBT) and local Madrid municipal building codes.
1. Scope of Work — Electrician Services in Madrid, Spain
This Quotation Estimate covers the full scope of professional electrician work required to modernise, repair, and bring into full regulatory compliance the electrical installation of the client's residential property located in the heart of Madrid, Spain. All work will be performed by licensed electricians registered with the Colegio Oficial de Electricistas de Madrid (COEM) and will comply with the Spanish Low Voltage Installations Regulation (RIBT), the European harmonised standards (UNE-EN series), and the specific municipal electrical safety ordinances of the Ayuntamiento de Madrid. The electrician team will handle all aspects of the project, from initial diagnostic assessment through to final certification and handover of the electrical installation certificate (Boletín Eléctrico) required by the Madrid regional authorities.
2. Detailed Line Items — Quotation Estimate Breakdown
	Ref
	Description of Electrician Work
	Quantity
	Unit Rate (EUR)
	Subtotal (EUR)
	Estimated Hours

	01
	Full diagnostic inspection and thermal imaging survey of existing electrical installation in the Madrid apartment, including identification of non-compliant wiring, overloaded circuits, and degraded components.
	1
	350.00
	350.00
	4 hrs

	02
	Removal and safe disposal of existing electrical panels, outdated wiring (pre-2000 PVC-insulated copper cable), and non-compliant distribution boards in accordance with Madrid waste electrical equipment regulations (RAEE).
	1
	1,200.00
	1,200.00
	12 hrs

	03
	Supply and installation of new main distribution board (cuadro general de protección) with 24 modular positions, including main switch, differential protection (30 mA), and individual circuit breakers, installed in compliance with RIBT Chapter V.
	1
	2,850.00
	2,850.00
	10 hrs

	04
	Complete rewiring of the apartment (approx. 120 m²) using 2.5 mm² and 1.5 mm² copper conductor cable (H07V-K), including new conduit routing (tubos corrugados) through walls and ceilings of the Madrid residential property.
	1
	4,500.00
	4,500.00
	40 hrs

	05
	Installation of 32 new lighting points (luminaires) with LED-compatible fittings, 48 new socket outlets (enchufes Schuko 16A), and 6 dedicated circuits for kitchen appliances, in line with Madrid residential electrical standards.
	1
	3,200.00
	3,200.00
	24 hrs

	06
	Installation of dedicated circuit and reinforced protection for electric vehicle (EV) charging point (Wallbox 7.4 kW) in the building's parking area, including coordination with the community of owners (comunidad de propietarios) and compliance with Madrid's 2024 EV infrastructure ordinance.
	1
	1,800.00
	1,800.00
	8 hrs

	07
	Earthing and lightning protection system upgrade, including new earth electrode, equipotential bonding conductors, and verification of earth resistance below 10 ohms as mandated for Madrid residential installations.
	1
	950.00
	950.00
	6 hrs

	08
	Final testing, commissioning, and issuance of the Boletín Eléctrico (Electrical Installation Certificate) and the corresponding electrical installation report (informe de instalación) for submission to the Comunidad de Madrid and the building's community of owners in Madrid.
	1
	600.00
	600.00
	4 hrs

	09
	Site cleanup, removal of all construction debris from the Madrid apartment, and final quality inspection by the lead electrician engineer.
	1
	450.00
	450.00
	4 hrs

	Subtotal (before VAT)
	15,900.00
	112 hrs

	VAT (IVA) — 21% (Spanish standard rate for residential electrical works in Madrid)
	3,339.00
	—

	TOTAL AMOUNT DUE (EUR)
	19,239.00
	—


All prices are quoted in Euros (EUR) and include the applicable Spanish Value Added Tax (IVA) at the standard rate of 21% as governed by the Ley 37/1992 del IVA. No additional municipal taxes or Madrid city council fees are included unless expressly stated.
3. Terms and Conditions of This Quotation Estimate
3.1 Validity: This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, prices may be revised to reflect current market rates for electrical materials and labour in Madrid, Spain.
3.2 Payment Terms: A deposit of 30% (EUR 5,771.70) is due upon acceptance of this Quotation Estimate to secure the electrician team's schedule. A further 40% (EUR 7,695.60) is due upon completion of the rewiring and distribution board installation. The remaining 30% (EUR 5,771.70) is payable upon final sign-off and delivery of the Boletín Eléctrico. All payments shall be made by bank transfer to the account of Madrid Electric Solutions S.L.
3.3 Work Schedule: All electrician work will be carried out between the hours of 08:00 and 18:00, Monday through Friday, in compliance with Madrid municipal noise and construction regulations. No work will be performed on public holidays as declared by the Comunidad de Madrid.
3.4 Access and Coordination: The client agrees to provide the electrician team with full and uninterrupted access to the property at Calle de Serrano 87, 5ºA, Madrid. The client shall also facilitate any necessary coordination with the building's community of owners (comunidad de propietarios) and the building's main electrical installation (instalación eléctrica comunitaria) as required by Madrid building regulations.
3.5 Warranty: Madrid Electric Solutions S.L. provides a warranty of five (5) years on all labour performed by our electrician team and a warranty of two (2) years on all supplied electrical materials and components, in accordance with the Spanish Consumer Protection Law (Ley General para la Defensa de los Consumidores y Usuarios).
3.6 Insurance and Liability: The electrician contractor holds full professional liability insurance (seguro de responsabilidad civil profesional) with a coverage of EUR 1,000,000 per claim, as well as workers' compensation insurance (seguro de accidentes de trabajo) in compliance with Spanish labour law. The contractor assumes full responsibility for any damage to the property or third parties arising from the execution of the works described in this Quotation Estimate.
3.7 Regulatory Compliance: All electrical works described herein shall be executed in strict compliance with the Reglamento de Instalaciones Electrotécnicas de Baja Tensión (RIBT), the applicable UNE-EN European standards, the technical regulations of the Comunidad de Madrid, and the specific electrical safety ordinances of the Ayuntamiento de Madrid. The final installation shall be certified by a qualified electrician engineer (Ingeniero Técnico Industrial) registered with the relevant Madrid professional college.
3.8 Dispute Resolution: Any dispute arising from this Quotation Estimate shall be resolved in accordance with Spanish law. The parties agree to submit to the jurisdiction of the courts of Madrid, Spain, as the exclusive venue for any legal proceedings.
4. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate for electrician services in Madrid, Spain, and authorises Madrid Electric Solutions S.L. to proceed with the works as described herein, subject to the terms and conditions set out above. This signature constitutes a binding agreement between both parties under Spanish contract law (Código Civil, Articles 1254 et seq.).
For Madrid Electric Solutions S.L.
Lead Electrician / Engineer
Name: Ing. Carlos Vega Serrano
Date: _______________
Client (Don Alejandro Martínez Ruiz)
Signature and DNI
Name: _________________________
Date: _______________
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