Quotation Estimate - Electrician Services - Bangkok, Thailand
ThaiVolt Electrical Services Co., Ltd.
128/45 Sukhumvit Road, Khlong Toei, Bangkok 10110, Thailand
Tel: +66 (0) 2 255 8890 | Email: quotes@thaivolt.co.th
Tax ID: 0105559876543 | License No. ELC-TH-2019-04521
QUOTATION ESTIMATE
Ref: QTE-2025-0784
Date: 15 June 2025
Valid Until: 15 July 2025
Client Information
Client Name:
Mr. Somchai Prasert
Company:
Bangkok Riverside Commercial Building
Project Address:
88 Charoen Krung Road, Bang Rak, Bangkok 10500, Thailand
Contact Number:
+66 (0) 89 765 4321
Scope of Work – Electrician Services in Bangkok, Thailand
This Quotation Estimate is issued by ThaiVolt Electrical Services Co., Ltd. for the provision of comprehensive electrician services at the client's commercial premises located in the Bang Rak district of Bangkok, Thailand. The scope encompasses the full inspection, repair, upgrade, and installation of electrical systems in compliance with the Thai Electricity Act B.E. 2543 (2000) and all applicable regulations enforced by the Metropolitan Electricity Authority (MEA) of Bangkok. Our licensed electrician team will ensure that all work meets the Thai Industrial Standards Institute (TISI) requirements and local Bangkok municipal building codes.
Itemized Cost Breakdown (Thai Baht – THB)
	No.
	Description of Electrician Work
	Qty
	Unit Rate (THB)
	Amount (THB)
	Duration

	1
	Full electrical system inspection and diagnostic assessment of all 12 floors of the commercial building in Bangkok
	1
	18,500
	18,500
	2 days

	2
	Replacement of aging electrical wiring (copper, 6mm²) in the main distribution panel and sub-panels on floors 1–6
	1
	95,000
	95,000
	5 days

	3
	Installation of new 63A three-phase circuit breakers and RCD protection devices (TISI certified)
	8
	4,200
	33,600
	2 days

	4
	Upgrade of emergency lighting and fire alarm electrical circuits throughout the building per Bangkok Fire Safety Regulations
	1
	42,000
	42,000
	3 days

	5
	Installation of 24 new LED lighting fixtures (50W, IP65 rated) in common areas and parking levels
	24
	1,850
	44,400
	2 days

	6
	Earthing and grounding system upgrade to meet MEA Bangkok standards (copper rod, 25mm, 2.4m depth)
	6
	7,500
	45,000
	2 days

	7
	Installation of new 200A three-phase main service entrance panel with metering for MEA connection
	1
	68,000
	68,000
	3 days

	8
	Thermal imaging scan and insulation resistance testing of all electrical circuits (post-installation verification)
	1
	12,000
	12,000
	1 day

	9
	Submission of as-built electrical drawings and application for MEA Bangkok electrical permit and inspection
	1
	8,500
	8,500
	3 days

	10
	Waste disposal and site cleanup in accordance with Bangkok Metropolitan Administration (BMA) regulations
	1
	5,000
	5,000
	1 day

	Subtotal
	372,000
	

	VAT (7% – Thai Revenue Department)
	26,040
	

	GRAND TOTAL (THB)
	398,040
	


Note: This Quotation Estimate is specific to the electrician works described above at the stated Bangkok, Thailand location. All materials are TISI-certified. Prices are quoted in Thai Baht (THB) and are valid for 30 calendar days from the issue date. Any additional electrician work requested beyond this scope will be subject to a separate supplementary quotation.
Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) days from the date of issue. After the expiry date, prices may be adjusted to reflect current market rates for electrical materials and labor in Bangkok, Thailand.
2. Payment terms: 40% advance payment upon acceptance of this quotation, 40% upon completion of major installation works, and 20% upon final handover and successful MEA Bangkok inspection.
3. All electrician work shall be performed by licensed electricians holding valid Thai electrical work permits. Our team operates in full compliance with the Occupational Safety and Health Act B.E. 2554 (2011) of Thailand.
4. The project timeline is estimated at twenty (20) working days from the commencement date, subject to weather conditions and access availability at the Bangkok site.
5. A two-year warranty is provided on all labor and installed materials. This warranty covers defects in workmanship but excludes damage caused by misuse, natural disasters, or unauthorized modifications by third parties.
6. The client is responsible for obtaining all necessary building permits from the Bangkok Metropolitan Administration (BMA) prior to the commencement of structural electrical modifications.
7. Any changes to the scope of electrician work must be agreed upon in writing via a formal change order before additional work commences.
8. This quotation is governed by the laws of the Kingdom of Thailand. Any disputes shall be resolved through the Bangkok Commercial Court.
Prepared by:
Mr. Anan Chaiyasit
Senior Electrician & Project Manager
ThaiVolt Electrical Services Co., Ltd.
Signature: _________________________
Date: 15 June 2025
Accepted by (Client):
Mr. Somchai Prasert
Bangkok Riverside Commercial Building
Signature: _________________________
Date: _________________________
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