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Quotation Estimate
Professional Services of an Electronics Engineer | Argentina Buenos Aires
Client Information
Company: Industrial Solutions del Plata S.A.
Contact Person: Ing. María González
Address: Ruta 2, Km 42, Zona Industrial, San Isidro
City: Buenos Aires, Argentina
CUIT: 30-69876543-2
Project Reference
Project Name: PLC Control System Upgrade – Line 7
Location: Planta Industrial, San Isidro, Buenos Aires
Estimated Duration: 12 weeks
Start Date: 01 August 2025
End Date: 28 October 2025
1. Scope of Work – Electronics Engineer Services
This Quotation Estimate is issued by TecnoElectra Ingeniería S.R.L. to provide the professional services of a certified Electronics Engineer for the design, implementation, and commissioning of an upgraded Programmable Logic Controller (PLC) control system for Production Line 7 at the client's industrial facility located in Argentina Buenos Aires. The scope encompasses all technical activities required to modernize the existing control infrastructure, ensuring compliance with Argentine industrial safety standards (IRAM) and international IEC 61131-3 programming guidelines.
The Electronics Engineer assigned to this project will hold a minimum of ten (10) years of professional experience in industrial automation, embedded systems design, and power electronics. All work will be performed on-site in Argentina Buenos Aires during standard business hours (Monday to Friday, 08:00 to 17:00), with the possibility of extended hours during critical commissioning phases subject to prior written agreement.
2. Itemized Services and Pricing
	Item
	Description
	Qty
	Unit Price (ARS)
	Subtotal (ARS)

	01
	Site survey and technical assessment of existing PLC infrastructure at the Argentina Buenos Aires facility
	1
	185,000.00
	185,000.00

	02
	System architecture design and schematic documentation by the Electronics Engineer
	1
	420,000.00
	420,000.00

	03
	PLC programming (IEC 61131-3: Ladder, FBD, ST) – estimated 320 hours of engineering work
	320
	3,800.00
	1,216,000.00

	04
	HMI (Human-Machine Interface) panel design and configuration
	1
	275,000.00
	275,000.00

	05
	Power supply and signal conditioning circuit design (24VDC distribution, isolation transformers)
	1
	195,000.00
	195,000.00

	06
	On-site installation supervision and wiring verification in Argentina Buenos Aires
	18
	5,200.00
	93,600.00

	07
	System commissioning, functional testing, and performance validation
	1
	310,000.00
	310,000.00

	08
	Operator training sessions (4 sessions × 4 hours) for plant personnel
	4
	48,000.00
	192,000.00

	09
	Technical documentation package (as-built drawings, operation manual, maintenance guide)
	1
	145,000.00
	145,000.00

	10
	Post-commissioning technical support and warranty period (90 days)
	1
	120,000.00
	120,000.00

	TOTAL QUOTATION ESTIMATE (before IVA)
	3,051,600.00

	IVA (21% – Argentine Value Added Tax)
	640,836.00

	GRAND TOTAL (including IVA)
	3,692,436.00


3. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, prices may be adjusted to reflect current market conditions in Argentina Buenos Aires.
· All prices are quoted in Argentine Pesos (ARS) and are subject to the applicable IVA rate in force at the time of invoicing.
· The Electronics Engineer shall comply with all occupational health and safety regulations established by the Argentine Ministry of Labor and the local municipality of San Isidro, Buenos Aires.
· Payment terms: 30% advance upon contract signing, 40% upon completion of programming and HMI configuration, and 30% upon successful commissioning and handover of documentation.
· Any scope modifications or change orders must be approved in writing by both parties before additional work commences. Revised pricing will be issued as a supplementary Quotation Estimate.
· The Electronics Engineer guarantees a minimum of ninety (90) days of post-commissioning support, during which any defects in workmanship will be corrected at no additional cost.
· Intellectual property of all designs, code, and documentation produced under this engagement shall transfer to the client upon full payment.
· This agreement is governed by the laws of the Argentine Republic, with jurisdiction in the courts of the City of Buenos Aires.
Note: This Quotation Estimate does not include the cost of hardware components (PLC modules, I/O cards, HMI panels, cables, enclosures, and power supplies). A separate materials quotation will be provided upon request. All travel and accommodation costs for the Electronics Engineer within the Argentina Buenos Aires metropolitan area are included in the rates above.
TecnoElectra Ingeniería S.R.L.
Ing. Ricardo Fernández – Director Técnico
Electronics Engineer / Project Lead
Mat. Profesional: 12345-BA
Industrial Solutions del Plata S.A.
Ing. María González – Gerente de Operaciones
Authorized Representative
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