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Dear Mr. Kassenov,
Thank you for your inquiry regarding professional Electronics Engineer services for your upcoming industrial automation project in the Almaty region. This Quotation Estimate has been carefully prepared to outline the full scope of work, associated costs, and delivery timelines for the engagement of a senior Electronics Engineer to support your facility modernization initiative in Kazakhstan Almaty. We are pleased to present this detailed Quotation Estimate for your review and approval.
1. Scope of Work – Electronics Engineer Services
The following Quotation Estimate covers the comprehensive engagement of a certified Electronics Engineer specializing in industrial control systems, embedded electronics, and power distribution design. The Electronics Engineer will be based in Kazakhstan Almaty and will provide on-site and remote support throughout the project duration. The scope includes but is not limited to:
· Design and development of custom printed circuit boards (PCBs) for industrial sensor arrays and monitoring systems.
· Selection, integration, and commissioning of programmable logic controllers (PLCs) and human-machine interfaces (HMIs).
· Power supply architecture design, including UPS systems, voltage regulators, and surge protection for the Almaty facility.
· Wiring, cabling, and installation of electronic control panels in compliance with Kazakh national standards (GOST and SNiP).
· Testing, calibration, and performance verification of all electronic subsystems prior to handover.
· Preparation of technical documentation, schematics, and as-built drawings for the client's engineering records.
· Training of up to eight (8) in-house technicians on the operation and basic maintenance of installed electronic systems.
2. Itemized Cost Breakdown
	Item No.
	Description
	Unit
	Qty
	Unit Price (KZT)
	Total (KZT)

	01
	Senior Electronics Engineer – On-site design & consultation (Almaty, Kazakhstan)
	Hour
	120
	45,000
	5,400,000

	02
	Electronics Engineer – Remote support & technical review
	Hour
	40
	35,000
	1,400,000

	03
	Custom PCB design, prototyping & fabrication (4-layer, 6 units)
	Lot
	1
	2,800,000
	2,800,000

	04
	PLC & HMI integration package (Siemens S7-1500 series)
	Set
	2
	1,250,000
	2,500,000

	05
	Power distribution & UPS installation (3-phase, 40 kVA)
	Set
	1
	3,600,000
	3,600,000

	06
	Technical documentation, schematics & as-built drawings
	Lot
	1
	450,000
	450,000

	07
	On-site training for 8 technicians (2-day workshop, Almaty)
	Session
	2
	180,000
	360,000

	08
	Travel, accommodation & local transport within Kazakhstan Almaty region
	Lot
	1
	320,000
	320,000

	Subtotal (KZT)
	16,830,000

	VAT (12% – Kazakhstan)
	2,019,600

	GRAND TOTAL (KZT)
	18,849,600

	GRAND TOTAL (USD – approx. at 450 KZT/USD)
	41,888.00


3. Project Timeline
	Phase
	Activity
	Duration
	Target Completion

	Phase 1
	Site survey, requirements gathering & system design (Electronics Engineer on-site, Almaty)
	3 weeks
	05 July 2025

	Phase 2
	PCB fabrication, component procurement & panel assembly
	4 weeks
	02 August 2025

	Phase 3
	Installation, wiring & integration at client facility, Kazakhstan Almaty
	3 weeks
	23 August 2025

	Phase 4
	Testing, calibration, documentation & staff training
	2 weeks
	06 September 2025


4. Terms & Conditions of This Quotation Estimate
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be subject to revision due to fluctuating component costs and exchange rates in the Kazakhstan Almaty market.
· Payment terms: 40% advance upon acceptance of this Quotation Estimate, 40% upon completion of Phase 3 (installation), and 20% upon final acceptance and handover of documentation.
· All payments shall be made in Kazakhstani Tenge (KZT) via bank transfer to the account of Almaty Electronics Engineering Solutions LLP, or in US Dollars (USD) at the National Bank of Kazakhstan's official exchange rate on the day of invoicing.
· The Electronics Engineer assigned to this project holds a valid professional license issued by the Ministry of Industry and Construction of the Republic of Kazakhstan and carries professional liability insurance with a coverage of 50,000,000 KZT.
· All work shall comply with the applicable regulations of Kazakhstan, including GOST standards for electrical installations, SNiP 3.05.06-85 for electrical equipment, and local Almaty municipal building codes.
· A warranty period of twelve (12) months shall apply to all electronic components, PCBs, and installed systems from the date of final acceptance. The Electronics Engineer will provide remote troubleshooting support throughout the warranty period at no additional cost.
· Any changes to the scope of work beyond what is described in this Quotation Estimate will require a written change order signed by both parties and may result in adjusted pricing and timeline.
· Confidentiality: All technical data, schematics, and proprietary information shared during the engagement shall be treated as confidential by the Electronics Engineer and the service provider in accordance with Kazakhstan's Law on Commercial Secrets.
Note: This Quotation Estimate is prepared specifically for the client named above and for the project location in Kazakhstan Almaty. It is non-transferable. The Electronics Engineer services described herein are tailored to the specific industrial requirements of the Turkistan Industrial Holdings facility and cannot be applied to other projects without a revised estimate.
5. Acceptance & Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, pricing, and timeline outlined above for the engagement of the Electronics Engineer in Kazakhstan Almaty.
For: Almaty Electronics Engineering Solutions LLP
Name: Aigerim Nurlanova
Title: Chief Electronics Engineer / Project Director
Signature & Date: _________________________
For: Turkistan Industrial Holdings
Name: Dauren Kassenov
Title: Director of Engineering
Signature & Date: _________________________
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