# Quotation Estimate - Electronics Engineer Services - Morocco Casablanca

# QUOTATION ESTIMATE

Professional Electronics Engineer Services

Morocco Casablanca | Official Document

Quotation Estimate No.: QE-2025-CAS-0472 Date of Issue: 15 June 2025 Valid Until: 15 July 2025

Prepared By: Atlas Electronics Engineering SARL Address: 45 Boulevard Zerktouni, Casablanca 20250, Morocco Contact: +212 522-345-678 | info@atlas-electronics.ma

## 1. Client Information

| Client Name: | Industrial Manufacturing Group – Casablanca Division |
| --- | --- |
| Project Location: | Industrial Zone, Morocco Casablanca, 20100 |
| Project Reference: | IMC-2025-Automation-Phase II |
| Point of Contact: | Mr. Youssef El Amrani – Operations Director |

## 2. Scope of Work – Electronics Engineer Services

This Quotation Estimate is issued by Atlas Electronics Engineering SARL to provide comprehensive professional services delivered by a certified Electronics Engineer for the client's industrial automation project located in Morocco Casablanca. The scope encompasses the full lifecycle of electronic system design, implementation, testing, and commissioning as detailed below.

The designated Electronics Engineer holds a Master's degree in Electronic Engineering from the École Nationale Supérieure d'Électricité et de Mécanique (ENSEM) in Rabat, Morocco, and possesses over twelve years of hands-on experience in industrial electronics, embedded systems, and PLC-based automation. All work will be conducted in strict compliance with Moroccan industrial regulations, IEC 61508 functional safety standards, and the specific technical requirements outlined in the client's project brief.

## 3. Itemized Cost Breakdown

| Item No. | Description of Electronics Engineer Service | Duration | Unit Rate (MAD) | Total (MAD) |
| --- | --- | --- | --- | --- |
| 01 | Initial site survey and feasibility assessment at the Morocco Casablanca industrial facility. The Electronics Engineer will evaluate existing electrical infrastructure, identify integration points, and produce a preliminary technical report. | 3 days | 4,500 | 13,500 |
| 02 | System architecture design and schematic development. The Electronics Engineer will produce complete circuit schematics, PCB layout files, and BOM documentation for the new automation control panels. | 15 days | 5,200 | 78,000 |
| 03 | Firmware and embedded software development for microcontroller-based sensor nodes. Includes C/C++ programming, real-time operating system configuration, and unit testing. | 20 days | 5,800 | 116,000 |
| 04 | PLC programming and HMI interface design. The Electronics Engineer will configure Siemens S7-1500 PLCs, develop SCADA integration protocols (Modbus TCP, Profinet), and design operator interface screens. | 18 days | 6,000 | 108,000 |
| 05 | On-site installation, wiring, and hardware commissioning at the Morocco Casablanca plant. Includes panel assembly, cable routing, grounding verification, and power supply validation. | 10 days | 5,500 | 55,000 |
| 06 | System integration testing, performance validation, and load testing. The Electronics Engineer will conduct 72-hour continuous operation trials and document all test results. | 5 days | 6,500 | 32,500 |
| 07 | Technical documentation package: as-built drawings, operation manuals, maintenance guides, and training materials for client personnel in Morocco Casablanca. | 5 days | 4,800 | 24,000 |
| 08 | On-site operator and maintenance staff training (2 sessions, 8 hours each). Delivered by the Electronics Engineer at the client's Casablanca facility. | 2 days | 7,000 | 14,000 |
| 09 | Post-commissioning support and warranty period (90 days). Remote and on-call support by the Electronics Engineer for any defects or performance issues. | 90 days | — | 25,000 |
| SUBTOTAL (MAD) |  |  |  | 466,000 |
| VAT (20% – Moroccan Tax Authority) |  |  |  | 93,200 |
| GRAND TOTAL (MAD) |  |  |  | 559,200 |

## 4. Payment Terms

- 30% Advance Payment: MAD 167,760 due upon acceptance of this Quotation Estimate and signing of the service contract.

- 40% Milestone Payment: MAD 223,680 due upon completion of design, firmware development, and PLC programming phases (Items 02–04).

- 30% Final Payment: MAD 167,760 due upon successful commissioning, delivery of documentation, and completion of training sessions.

- All payments shall be made via bank transfer to the account of Atlas Electronics Engineering SARL, Bank of Africa, Casablanca, Morocco. IBAN: MA64 4002 1000 0123 4567 8901 2345.

## 5. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be subject to revision due to market fluctuations in electronic components and labor costs in Morocco Casablanca.

- The Electronics Engineer assigned to this project shall not be reassigned without prior written consent from the client. In the event of unavoidable absence, a substitute of equivalent or superior qualification will be provided.

- All intellectual property rights in designs, firmware, and documentation produced under this engagement shall transfer to the client upon full payment.

- The Electronics Engineer and Atlas Electronics Engineering SARL shall maintain professional liability insurance with a minimum coverage of MAD 5,000,000 throughout the duration of the project.

- Work will be performed in accordance with Moroccan labor law, occupational health and safety regulations, and the specific site safety protocols of the client's Morocco Casablanca facility.

- Any changes to the scope of work beyond the parameters described in this Quotation Estimate will be subject to a formal change order and additional cost assessment.

- Disputes arising from this engagement shall be resolved through amicable negotiation. Failing resolution within thirty days, matters shall be submitted to the competent commercial courts of Casablanca, Morocco.

## 6. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the Electronics Engineer services to be delivered in Morocco Casablanca.

For Atlas Electronics Engineering SARL
Name: Dr. Karim Benjelloun
Title: Lead Electronics Engineer / Director
Signature & Date: _________________________

For the Client
Name: Mr. Youssef El Amrani
Title: Operations Director
Signature & Date: _________________________

Atlas Electronics Engineering SARL | RC: 456789 | ICE: 002345678000091 | IF: 45678900 | CNSS: 1234567
45 Boulevard Zerktouni, Casablanca 20250, Morocco | Tel: +212 522-345-678 | Email: info@atlas-electronics.ma
This Quotation Estimate is a controlled document. Unauthorized reproduction or distribution is prohibited.