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1. Client Information
	Client Name:
	Industrial Manufacturing Group – Casablanca Division

	Project Location:
	Industrial Zone, Morocco Casablanca, 20100

	Project Reference:
	IMC-2025-Automation-Phase II

	Point of Contact:
	Mr. Youssef El Amrani – Operations Director


2. Scope of Work – Electronics Engineer Services
This Quotation Estimate is issued by Atlas Electronics Engineering SARL to provide comprehensive professional services delivered by a certified Electronics Engineer for the client's industrial automation project located in Morocco Casablanca. The scope encompasses the full lifecycle of electronic system design, implementation, testing, and commissioning as detailed below.
The designated Electronics Engineer holds a Master's degree in Electronic Engineering from the École Nationale Supérieure d'Électricité et de Mécanique (ENSEM) in Rabat, Morocco, and possesses over twelve years of hands-on experience in industrial electronics, embedded systems, and PLC-based automation. All work will be conducted in strict compliance with Moroccan industrial regulations, IEC 61508 functional safety standards, and the specific technical requirements outlined in the client's project brief.
3. Itemized Cost Breakdown
	Item No.
	Description of Electronics Engineer Service
	Duration
	Unit Rate (MAD)
	Total (MAD)

	01
	Initial site survey and feasibility assessment at the Morocco Casablanca industrial facility. The Electronics Engineer will evaluate existing electrical infrastructure, identify integration points, and produce a preliminary technical report.
	3 days
	4,500
	13,500

	02
	System architecture design and schematic development. The Electronics Engineer will produce complete circuit schematics, PCB layout files, and BOM documentation for the new automation control panels.
	15 days
	5,200
	78,000

	03
	Firmware and embedded software development for microcontroller-based sensor nodes. Includes C/C++ programming, real-time operating system configuration, and unit testing.
	20 days
	5,800
	116,000

	04
	PLC programming and HMI interface design. The Electronics Engineer will configure Siemens S7-1500 PLCs, develop SCADA integration protocols (Modbus TCP, Profinet), and design operator interface screens.
	18 days
	6,000
	108,000

	05
	On-site installation, wiring, and hardware commissioning at the Morocco Casablanca plant. Includes panel assembly, cable routing, grounding verification, and power supply validation.
	10 days
	5,500
	55,000

	06
	System integration testing, performance validation, and load testing. The Electronics Engineer will conduct 72-hour continuous operation trials and document all test results.
	5 days
	6,500
	32,500

	07
	Technical documentation package: as-built drawings, operation manuals, maintenance guides, and training materials for client personnel in Morocco Casablanca.
	5 days
	4,800
	24,000

	08
	On-site operator and maintenance staff training (2 sessions, 8 hours each). Delivered by the Electronics Engineer at the client's Casablanca facility.
	2 days
	7,000
	14,000

	09
	Post-commissioning support and warranty period (90 days). Remote and on-call support by the Electronics Engineer for any defects or performance issues.
	90 days
	—
	25,000

	SUBTOTAL (MAD)
	466,000

	VAT (20% – Moroccan Tax Authority)
	93,200

	GRAND TOTAL (MAD)
	559,200


4. Payment Terms
· 30% Advance Payment: MAD 167,760 due upon acceptance of this Quotation Estimate and signing of the service contract.
· 40% Milestone Payment: MAD 223,680 due upon completion of design, firmware development, and PLC programming phases (Items 02–04).
· 30% Final Payment: MAD 167,760 due upon successful commissioning, delivery of documentation, and completion of training sessions.
· All payments shall be made via bank transfer to the account of Atlas Electronics Engineering SARL, Bank of Africa, Casablanca, Morocco. IBAN: MA64 4002 1000 0123 4567 8901 2345.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be subject to revision due to market fluctuations in electronic components and labor costs in Morocco Casablanca.
· The Electronics Engineer assigned to this project shall not be reassigned without prior written consent from the client. In the event of unavoidable absence, a substitute of equivalent or superior qualification will be provided.
· All intellectual property rights in designs, firmware, and documentation produced under this engagement shall transfer to the client upon full payment.
· The Electronics Engineer and Atlas Electronics Engineering SARL shall maintain professional liability insurance with a minimum coverage of MAD 5,000,000 throughout the duration of the project.
· Work will be performed in accordance with Moroccan labor law, occupational health and safety regulations, and the specific site safety protocols of the client's Morocco Casablanca facility.
· Any changes to the scope of work beyond the parameters described in this Quotation Estimate will be subject to a formal change order and additional cost assessment.
· Disputes arising from this engagement shall be resolved through amicable negotiation. Failing resolution within thirty days, matters shall be submitted to the competent commercial courts of Casablanca, Morocco.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the Electronics Engineer services to be delivered in Morocco Casablanca.
For Atlas Electronics Engineering SARL
Name: Dr. Karim Benjelloun
Title: Lead Electronics Engineer / Director
Signature & Date: _________________________
For the Client
Name: Mr. Youssef El Amrani
Title: Operations Director
Signature & Date: _________________________
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