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ElectroTech Solutions Pvt. Ltd.
Professional Electronics Engineering & Technical Services
Plot No. 42, New Baneshwor, Kathmandu, Nepal
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Quotation Estimate
Quotation Details
Quotation No.: QTE-2025-0347
Date of Issue: 15 June 2025
Validity Period: 30 days from date of issue
Prepared By: Ramesh Shrestha, Senior Electronics Engineer
Client Information
Client Name: Himalayan Industrial Systems (P) Ltd.
Address: Industrial Area, Bhaktapur, Nepal Kathmandu Valley
Contact Person: Mr. Suresh Adhikari
Phone: +977-9841234567
This Quotation Estimate is prepared by ElectroTech Solutions Pvt. Ltd. to provide comprehensive professional services of a qualified Electronics Engineer for the design, development, testing, and deployment of electronic systems at the client's facility located in the Nepal Kathmandu metropolitan area. The scope of work outlined below reflects the full technical engagement as discussed during the preliminary consultation held on 28 May 2025 at our Kathmandu office.
Scope of Work & Itemized Cost Breakdown
	S.No.
	Description of Service
	Duration / Qty
	Unit Rate (NPR)
	Amount (NPR)

	1
	On-site assessment and feasibility study of existing electronic infrastructure at the client's manufacturing unit in Nepal Kathmandu
	3 working days
	12,000
	36,000

	2
	Design and schematic development of a custom PCB-based control system (4-layer board, 120 sq. inch area) by a senior Electronics Engineer
	15 working days
	25,000
	375,000

	3
	Firmware development and embedded programming (ARM Cortex-M4 based microcontroller platform) including real-time monitoring modules
	20 working days
	18,000
	360,000

	4
	Prototyping, bench testing, and iterative debugging of the Electronics Engineer-designed hardware prototype (3 iterations included)
	10 working days
	15,000
	150,000

	5
	Electromagnetic compatibility (EMC) and environmental stress testing per IEC 61000 and IEC 60068 standards at our Kathmandu laboratory
	5 working days
	20,000
	100,000

	6
	On-site installation, calibration, and commissioning of the final electronic system at the client's facility in Nepal Kathmandu
	4 working days
	14,000
	56,000

	7
	Preparation of complete technical documentation including circuit diagrams, BOM, test reports, user manuals, and maintenance guides
	5 working days
	10,000
	50,000

	8
	Training session for client's technical staff (up to 8 personnel) on operation, troubleshooting, and basic maintenance of the installed system
	2 working days
	12,000
	24,000

	9
	Post-deployment technical support and warranty service (12 months) provided by the assigned Electronics Engineer team
	12 months
	8,000
	96,000

	10
	Procurement of critical electronic components, ICs, sensors, and passive components as per the approved BOM (sourced from authorized distributors in Nepal Kathmandu and international suppliers)
	As per BOM
	—
	485,000

	Subtotal (NPR)
	1,732,000

	Applicable VAT (13% as per Nepal tax regulations)
	225,160

	Grand Total (NPR)
	1,957,160


Note: All rates quoted in this Quotation Estimate are in Nepalese Rupees (NPR). Component costs (Item 10) are estimated based on current market prices in Nepal Kathmandu and may vary by up to 5% depending on availability and exchange rate fluctuations. Any change in scope beyond the defined parameters will be subject to a revised Quotation Estimate issued separately.
Payment Schedule
	Milestone
	Percentage
	Amount (NPR)
	Due Date

	Advance payment upon acceptance of this Quotation Estimate
	30%
	587,148
	Within 7 days of acceptance

	Upon completion of design and prototype approval
	30%
	587,148
	Upon milestone sign-off

	Upon successful installation and commissioning in Nepal Kathmandu
	30%
	587,148
	Within 14 days of commissioning

	Final payment after 30-day performance verification
	10%
	195,716
	End of month 1 post-deployment


Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, pricing—particularly for electronic components—may be revised to reflect current market conditions in Nepal Kathmandu.
1. The assigned Electronics Engineer and supporting technical team shall adhere to all applicable standards of the Nepal Electricity Authority (NEA), Department of Industry (DoI), and relevant international engineering codes.
1. All intellectual property rights pertaining to the custom-designed circuits, firmware, and documentation developed under this engagement shall vest with the client upon full and final payment.
1. The Electronics Engineer team shall provide a minimum of two (2) on-site visits per week during the active development phase in Nepal Kathmandu, with remote support available on all other working days.
1. Any work beyond the scope defined in this Quotation Estimate shall require a written change order signed by both parties before execution.
1. The warranty period of twelve (12) months covers defects in design, workmanship, and components. It does not cover damage caused by misuse, unauthorized modification, or force majeure events.
1. Disputes arising from this Quotation Estimate shall be resolved through amicable negotiation. In the event of failure to resolve, the matter shall be referred to the competent court of law in Kathmandu, Nepal.
1. All work shall be conducted in compliance with the labor laws of Nepal and the occupational health and safety regulations applicable in the Kathmandu Valley region.
1. This Quotation Estimate does not constitute a binding contract until formally accepted in writing by both parties and a separate Service Agreement is executed.
Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Electronics Engineer services in Nepal Kathmandu.
For ElectroTech Solutions Pvt. Ltd.
Name: Ramesh Shrestha
Designation: Senior Electronics Engineer / Project Lead
Signature & Company Seal
For Himalayan Industrial Systems (P) Ltd.
Name: Suresh Adhikari
Designation: Managing Director
Signature & Company Seal
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Thank you for considering our Electronics Engineer services in Nepal Kathmandu. We look forward to a successful collaboration.
