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Client Information
	Field
	Details

	Company Name
	Minera del Pacífico S.A.C.

	Contact Person
	Ing. Carlos Mendoza Ríos

	Address
	Av. Arequipa 2340, Miraflores, Lima, Peru

	RUC
	20456789012

	Project Reference
	Industrial Automation Upgrade – Plant Lima Norte


Scope of Work – Electronics Engineer Services
This Quotation Estimate is issued by Andina Electronics Engineering S.A.C. to provide comprehensive professional services rendered by a certified Electronics Engineer for the industrial automation upgrade project located in the Lima Norte industrial zone, Peru Lima. The scope encompasses the full lifecycle of electronic system design, implementation, testing, and commissioning as detailed below.
The Electronics Engineer assigned to this project holds a professional degree from the Pontificia Universidad Católica del Perú (PUCP), is registered with the Colegio de Ingenieros del Perú (CIP), and possesses over twelve years of experience in industrial electronics, PLC programming, embedded systems, and power electronics within the Peru Lima metropolitan area and surrounding industrial corridors.
Itemized Cost Breakdown
	Item No.
	Description of Service
	Duration / Qty
	Unit Price (S/)
	Subtotal (S/)

	01
	Initial site assessment and diagnostic audit of existing electronic infrastructure at the client's facility in Lima Norte, Peru Lima
	3 days
	1,850.00
	5,550.00

	02
	Design and engineering of the new PLC-based control system, including schematic diagrams, wiring plans, and component specifications prepared by the Electronics Engineer
	15 days
	2,200.00
	33,000.00

	03
	Procurement coordination and technical validation of electronic components (PLC modules, HMI panels, sensors, actuators, power supplies, and communication interfaces)
	10 days
	1,500.00
	15,000.00

	04
	On-site installation, wiring, and physical integration of the electronic control system at the Peru Lima plant facility
	20 days
	2,400.00
	48,000.00

	05
	Programming, configuration, and commissioning of PLC logic, SCADA interface, and industrial communication networks (Modbus, Profinet, Ethernet/IP)
	12 days
	2,600.00
	31,200.00

	06
	System testing, performance validation, and safety compliance verification per Peruvian electrical regulations (NTP 370.032) and IEC 61508 standards
	8 days
	2,100.00
	16,800.00

	07
	Preparation of technical documentation: as-built drawings, operation manuals, maintenance guides, and training materials for client personnel
	5 days
	1,900.00
	9,500.00

	08
	On-site operator and maintenance technician training sessions conducted by the Electronics Engineer at the Peru Lima facility (4 sessions, 4 hours each)
	4 sessions
	1,200.00
	4,800.00

	09
	Post-commissioning technical support and warranty period (90 days of remote and on-site support within Lima, Peru)
	90 days
	1,000.00
	9,000.00

	TOTAL ESTIMATED COST (Before IGV 18%)
	S/ 172,850.00

	IGV (18% – Impuesto General a las Ventas, Peru)
	S/ 31,113.00

	GRAND TOTAL (Including IGV)
	S/ 203,963.00


Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing may be subject to revision due to market fluctuations in electronic component costs within Peru.
· All services will be performed by a qualified Electronics Engineer who is a registered professional with the Colegio de Ingenieros del Perú, ensuring full compliance with Peruvian professional engineering regulations.
· The project will be executed at the client's premises located in the Lima Norte district, Peru Lima, or at such other location within the Lima metropolitan area as mutually agreed upon in writing.
· Payment terms: 30% advance upon contract signing, 40% upon completion of installation and commissioning, and 30% upon final acceptance and delivery of all technical documentation.
· Invoices will be issued in accordance with Peruvian tax regulations (SUNAT) and will include the applicable IGV of 18%.
· The Electronics Engineer shall maintain full professional liability insurance coverage throughout the duration of the project, as required by Peruvian law for engineering services.
· Any changes to the scope of work must be documented through a formal Change Order signed by both parties. The Quotation Estimate does not cover work outside the defined scope without prior written authorization.
· Warranty on workmanship is ninety (90) days from the date of final acceptance. Warranty on electronic components is governed by the respective manufacturer's terms.
· This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties in accordance with Peruvian civil and commercial law.
· All intellectual property related to custom designs, PLC programs, and engineering documentation developed specifically for this project shall transfer to the client upon full payment.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through the courts of Lima, Peru, in accordance with applicable Peruvian legislation.
Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the Electronics Engineer services to be performed in Peru Lima.
For Andina Electronics Engineering S.A.C.
Ing. Ricardo Salazar Vega
Electronics Engineer – CIP Reg. 123456
Date: _______________
For Minera del Pacífico S.A.C. (Client)
Ing. Carlos Mendoza Ríos
Project Manager
Date: _______________
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