Quotation Estimate - Electronics Engineer Services - Switzerland Zurich
QUOTATION ESTIMATE
Professional Electronics Engineer Services
Switzerland Zurich — Canton of Zurich
Quotation Reference No: QE-ZRH-2025-0417
Provider
SwissTech Electronics Engineering GmbH
Bahnhofstrasse 142, 8001 Zurich, Switzerland
VAT No: CHE-123.456.789 IVA
Phone: +41 44 555 0192
Email: quotes@swisstech-electronics.ch
Client
Alpine Precision Manufacturing AG
Industriestrasse 27, 8005 Zurich, Switzerland
Contact: Dr. Markus Keller, Procurement Director
Phone: +41 44 778 3321
Email: m.keller@alpineprecision.ch
Date of Issue: 15 June 2025
Valid Until: 15 July 2025 (30 days)
Project Location: Switzerland Zurich, 8005
Project Duration: 12 weeks (estimated)
1. Scope of Work — Electronics Engineer Services in Switzerland Zurich
This Quotation Estimate is issued by SwissTech Electronics Engineering GmbH to provide comprehensive professional services of a senior Electronics Engineer for the duration of the project. The Electronics Engineer will be deployed on-site at the client's facility in Switzerland Zurich and will be responsible for the design, prototyping, testing, and documentation of embedded electronic systems for the client's next-generation industrial sensor array. All work will be performed in accordance with Swiss Federal regulations, IEC 61508 functional safety standards, and the specific technical requirements outlined in the project brief dated 28 May 2025.
2. Detailed Breakdown of Services and Costs
	No.
	Description of Service
	Duration
	Rate (CHF)
	Subtotal (CHF)
	Notes

	1
	System Architecture Design — The Electronics Engineer will develop the complete hardware architecture for the multi-channel sensor interface board, including schematic design, component selection, and power distribution planning.
	3 weeks
	1,250 / day
	18,750.00
	On-site, Switzerland Zurich

	2
	PCB Layout & Prototyping — Four-layer PCB design using Altium Designer, fabrication of two prototype boards, and assembly of all surface-mount and through-hole components.
	3 weeks
	1,250 / day
	18,750.00
	Includes 2 prototype units

	3
	Firmware Development & Integration — Embedded C/C++ firmware for the ARM Cortex-M7 microcontroller, sensor calibration routines, and communication protocol implementation (SPI, I2C, UART).
	3 weeks
	1,250 / day
	18,750.00
	Source code delivered

	4
	Testing, Validation & EMC Compliance — Full electrical testing, signal integrity analysis, thermal profiling, and pre-compliance EMC testing to ensure the design meets EN 55032 Class B requirements for the Switzerland Zurich industrial zone.
	2 weeks
	1,250 / day
	12,500.00
	Lab access provided by client

	5
	Technical Documentation & Handover — Complete design documentation package including schematics, BOM, test reports, user manual, and maintenance guide in both German and English for the Switzerland Zurich regulatory filing.
	1 week
	1,250 / day
	6,250.00
	5 copies + digital

	6
	Project Management & Weekly Reporting — Coordination with client engineering team, progress reporting, risk assessment, and milestone reviews conducted in Switzerland Zurich.
	12 weeks
	850 / week
	10,200.00
	Includes 12 weekly reports

	7
	Travel & Local Transportation — Daily commuting within the Switzerland Zurich metropolitan area, parking, and public transport (ZVV zone 100).
	12 weeks
	45 / day
	2,700.00
	Flat daily rate

	Subtotal
	87,900.00
	

	VAT (7.7% — Swiss standard rate)
	6,768.30
	Applied per Swiss VAT law

	TOTAL AMOUNT DUE (CHF)
	94,668.30
	


3. Terms and Conditions of This Quotation Estimate
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After the expiry date, all rates and availability of the Electronics Engineer are subject to re-evaluation.
1. All prices are quoted in Swiss Francs (CHF) and are inclusive of the Electronics Engineer's professional expertise, tools, and software licenses. Any additional hardware components or third-party services not listed above will be invoiced separately at cost plus 15%.
1. Payment terms: 30% advance payment upon acceptance of this Quotation Estimate, 40% upon completion of the prototyping phase (Week 6), and 30% upon final delivery and acceptance of all documentation in Switzerland Zurich.
1. Invoices are payable within thirty (30) days of the invoice date. Late payments will incur interest at the rate of 5% per annum in accordance with Swiss Code of Obligations (OR Art. 104).
1. The Electronics Engineer shall comply with all applicable Swiss labor laws, data protection regulations (FADP/revised nFADP), and site safety protocols at the client's premises in Switzerland Zurich.
1. Intellectual property: All designs, schematics, firmware, and documentation created specifically for this project shall become the exclusive property of the client upon full payment. The Electronics Engineer retains the right to reference the project in a general portfolio without disclosing confidential details.
1. Confidentiality: Both parties agree to maintain strict confidentiality regarding all technical data, trade secrets, and business information exchanged during the project, in line with Swiss commercial practice in Switzerland Zurich.
1. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, pandemics, or government-mandated closures affecting the Switzerland Zurich region.
1. Dispute Resolution: Any disputes arising from this Quotation Estimate shall be resolved through mediation in Zurich, Switzerland, and if unresolved, shall be subject to the exclusive jurisdiction of the courts of the Canton of Zurich.
1. This Quotation Estimate does not constitute a binding contract until formally accepted in writing by both parties via signature or electronic acknowledgment.
4. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for the services of the Electronics Engineer as described herein, to be performed in Switzerland Zurich. The provider confirms availability and commitment to deliver the scope of work within the stated timeline and budget.
For SwissTech Electronics Engineering GmbH
Signature & Date
Dr. Elena Brandt, Managing Director
For Alpine Precision Manufacturing AG
Signature & Date
Dr. Markus Keller, Procurement Director
SwissTech Electronics Engineering GmbH — Bahnhofstrasse 142, 8001 Zurich, Switzerland — CHE-123.456.789 IVA
This Quotation Estimate QE-ZRH-2025-0417 is issued for Electronics Engineer services in Switzerland Zurich. Page 1 of 1.
