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QUOTATION ESTIMATE
Professional Electronics Engineer Services — Uzbekistan Tashkent
	Quotation Estimate No.:
	QE-2025-TSK-0472

	Date of Issue:
	14 June 2025

	Valid Until:
	14 July 2025 (30 calendar days)

	Prepared By:
	Central Asia Technical Solutions LLC, 12 Amir Temur Avenue, Tashkent, Uzbekistan

	Prepared For:
	Uzbekistan Tashkent Industrial Development Authority, 45 Navoi Street, Tashkent 100000, Uzbekistan

	Project Reference:
	Smart Manufacturing Facility Upgrade — Phase II, Tashkent Industrial Zone


1. Purpose of This Quotation Estimate
This Quotation Estimate is issued by Central Asia Technical Solutions LLC to formally present the scope, schedule, and financial breakdown for the engagement of a senior Electronics Engineer to support the Smart Manufacturing Facility Upgrade project located in Uzbekistan Tashkent. This document serves as a binding proposal for the client's review and approval. All pricing is quoted in Uzbekistan Som (UZS) unless otherwise stated, and all services will be delivered in accordance with the regulatory standards of the Republic of Uzbekistan and applicable international engineering codes.
2. Scope of Work — Electronics Engineer Services
The Electronics Engineer engaged under this Quotation Estimate shall perform the following duties and deliverables within the Uzbekistan Tashkent project site and associated laboratories:
· Design, simulation, and prototyping of custom printed circuit boards (PCBs) for industrial automation controllers used in the Tashkent manufacturing line.
· Development and integration of embedded firmware for sensor arrays, motor control units, and real-time data acquisition systems.
· Conducting electromagnetic compatibility (EMC) testing and signal integrity analysis in compliance with IEC 61000 and local Uzbekistan Tashkent municipal electrical safety regulations.
· Supervision of the installation and commissioning of programmable logic controllers (PLCs), human-machine interfaces (HMIs), and industrial Ethernet networks across the facility.
· Preparation of comprehensive technical documentation, including schematics, bill of materials (BOM), test reports, and as-built drawings, all to be submitted in both English and Uzbek languages.
· Training of on-site maintenance personnel in Tashkent on the operation, troubleshooting, and preventive maintenance of the electronics subsystems.
· Provision of a 12-month post-commissioning technical support window, including remote diagnostics and up to four on-site visits to the Uzbekistan Tashkent facility.
3. Project Duration and Milestones
The total engagement period for the Electronics Engineer under this Quotation Estimate is estimated at fourteen (14) calendar weeks, commencing upon written acceptance of this document. Key milestones are as follows:
· Weeks 1–3: Requirements gathering, site survey at the Uzbekistan Tashkent facility, and preliminary design review.
· Weeks 4–8: Detailed PCB design, firmware development, and laboratory prototyping.
· Weeks 9–11: On-site installation, integration, and commissioning at the Tashkent project location.
· Weeks 12–13: System testing, EMC verification, and documentation finalization.
· Week 14: Client acceptance, handover, and commencement of the support period.
4. Financial Breakdown
	Item No.
	Description
	Unit
	Quantity
	Unit Price (UZS)
	Amount (UZS)

	01
	Electronics Engineer — Senior (Design & Development)
	Man-week
	8
	12,500,000
	100,000,000

	02
	Electronics Engineer — Installation & Commissioning
	Man-week
	4
	11,000,000
	44,000,000

	03
	EMC Testing & Signal Integrity Analysis
	Lump sum
	1
	18,500,000
	18,500,000

	04
	Technical Documentation (English & Uzbek)
	Lump sum
	1
	7,200,000
	7,200,000

	05
	On-site Training for Maintenance Staff (Tashkent)
	Session (8 hrs)
	3
	4,800,000
	14,400,000

	06
	Post-Commissioning Technical Support (12 months)
	Year
	1
	22,000,000
	22,000,000

	07
	Travel & Accommodation within Uzbekistan Tashkent
	Lump sum
	1
	5,600,000
	5,600,000

	Subtotal
	211,700,000

	VAT (12% — Uzbekistan Tashkent)
	25,404,000

	TOTAL AMOUNT (UZS)
	237,104,000


* All amounts are exclusive of any third-party hardware procurement costs, which will be itemized in a separate schedule upon client request. The total is equivalent to approximately USD 18,900 at the National Bank of Uzbekistan reference rate on the date of this Quotation Estimate.
5. Payment Terms
5.1 — 30% advance payment (UZS 71,131,200) due within ten (10) business days of written acceptance of this Quotation Estimate.
5.2 — 40% progress payment (UZS 94,841,600) due upon completion of the installation and commissioning milestone (Week 11).
5.3 — 30% final payment (UZS 71,131,200) due upon formal client acceptance and handover of all documentation (Week 14).
5.4 — All payments shall be made via bank transfer to the account of Central Asia Technical Solutions LLC, National Bank of Uzbekistan, Tashkent branch. Late payments shall accrue interest at 1.5% per month.
6. Terms and Conditions
6.1 — This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be revised to reflect market conditions in Uzbekistan Tashkent.
6.2 — The Electronics Engineer shall comply with all occupational health and safety regulations applicable in the Republic of Uzbekistan, including those enforced by the Tashkent City Executive Committee.
6.3 — Intellectual property rights for all designs, firmware, and documentation produced under this engagement shall vest in the client upon full payment.
6.4 — Any change in scope beyond the items listed in Section 2 shall be subject to a formal change order and a supplementary Quotation Estimate issued by the contractor.
6.5 — Disputes arising from this Quotation Estimate shall be resolved through arbitration in Tashkent, Uzbekistan, in accordance with the rules of the Tashkent International Arbitration Centre.
6.6 — The contractor reserves the right to substitute the assigned Electronics Engineer with a professional of equivalent or superior qualification, subject to prior written notice to the client.
7. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the scope, pricing, and terms outlined herein for the Electronics Engineer services to be delivered in Uzbekistan Tashkent.
For and on behalf of the Contractor:
Central Asia Technical Solutions LLC
Name / Signature / Date
For and on behalf of the Client:
Uzbekistan Tashkent Industrial Development Authority
Name / Signature / Date
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