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QUOTATION ESTIMATE
Environmental Engineer Professional Services
GreenSolutions Environmental Consulting Co.
No. 42, Vali-e-Asr Street, Jomhouri Square, Tehran, Iran
Tel: +98-21-8876-5432 | Email: info@greensolutions-iran.com
Registration No. 104582 | Environmental Engineering License: IR-ENV-2019-00347
	Quotation Estimate No.
	QE-2025-TEH-01187

	Date of Issue
	14 June 2025 (24 Khordad 1404)

	Valid Until
	14 July 2025 (24 Tir 1404)

	Prepared For
	Tehran Metropolitan Municipality – Department of Urban Planning & Environmental Compliance

	Project Location
	Iran Tehran, District 22, South Tehran Industrial Zone

	Project Title
	Comprehensive Environmental Impact Assessment and Remediation Planning for the South Tehran Industrial Corridor

	Currency
	Iranian Rial (IRR) / USD equivalent


1. Scope of Work – Environmental Engineer Services in Iran Tehran
This Quotation Estimate is issued by GreenSolutions Environmental Consulting Co. to formally propose the engagement of a senior Environmental Engineer and a supporting technical team to deliver a full-spectrum environmental assessment and remediation programme for the South Tehran Industrial Corridor. The Environmental Engineer will be responsible for conducting site-specific environmental audits, air quality monitoring, soil and groundwater contamination profiling, waste management system design, and the preparation of a comprehensive Environmental Impact Assessment (EIA) report in full compliance with the regulations of the Department of Environment of the Islamic Republic of Iran (DOE-IR) and the Tehran Metropolitan Municipality environmental bylaws.
The Environmental Engineer will coordinate with local authorities in Iran Tehran, including the Tehran Air Quality Management Center, the South Tehran Water and Wastewater Company, and the Ministry of Industry, Mine and Trade, to ensure that all findings, recommendations, and remediation strategies align with national and municipal environmental standards. All fieldwork, laboratory sampling, and data analysis will be conducted within the boundaries of Iran Tehran, with particular focus on the industrial estates of Districts 19, 20, and 22.
2. Itemized Cost Breakdown
	Item No.
	Description of Environmental Engineer Service
	Duration / Qty
	Unit Cost (IRR)
	Total (IRR)

	01
	Senior Environmental Engineer – Site Assessment & Desktop Review (including review of existing Iran Tehran environmental permits, historical discharge records, and land-use maps)
	15 working days
	8,500,000
	127,500,000

	02
	Environmental Engineer – Air Quality Monitoring Campaign (PM2.5, PM10, SO₂, NOₓ, CO, O₃ at 12 monitoring stations across Iran Tehran industrial zones)
	30 days
	12,000,000
	360,000,000

	03
	Environmental Engineer – Soil & Groundwater Contamination Profiling (drilling, sampling, and laboratory analysis at 45 borehole locations in South Tehran)
	25 working days
	15,500,000
	387,500,000

	04
	Environmental Engineer – Waste Management & Hazardous Material Audit (inventory of industrial waste streams, compliance check with Iran Tehran municipal waste regulations)
	10 working days
	9,000,000
	90,000,000

	05
	Environmental Engineer – EIA Report Preparation & Submission (full Environmental Impact Assessment document, public consultation coordination, and DOE-IR submission package)
	20 working days
	11,000,000
	220,000,000

	06
	Environmental Engineer – Remediation Strategy Design & Cost Modelling (tailored to Iran Tehran soil types, climate, and regulatory framework)
	15 working days
	10,500,000
	157,500,000

	07
	Environmental Engineer – Stakeholder Meetings & Public Consultation Facilitation (minimum 3 sessions with local communities, industry operators, and Iran Tehran municipal officials)
	3 sessions
	4,500,000
	13,500,000

	08
	Environmental Engineer – Final Report, Executive Summary & 12-Month Post-Implementation Monitoring Plan
	10 working days
	7,500,000
	75,000,000

	Subtotal (Professional Services)
	1,431,000,000

	Laboratory Analysis & Field Equipment (third-party, Iran Tehran accredited labs)
	215,000,000

	Travel, Permits & Miscellaneous (within Iran Tehran metropolitan area)
	48,000,000

	GRAND TOTAL (Quotation Estimate)
	1,694,000,000 IRR


* USD equivalent at the time of this Quotation Estimate: approximately USD 41,850 (rate: 40,478 IRR/USD, Central Bank of Iran, June 2025). Final settlement in IRR.
3. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, the Environmental Engineer rates and project costs may be revised to reflect changes in the Iranian Rial exchange rate, inflation, or regulatory updates in Iran Tehran.
1. Payment shall be made in three (3) milestones: 30% upon contract signing, 40% upon completion of fieldwork and laboratory analysis, and 30% upon delivery and acceptance of the final EIA report and remediation plan.
1. The Environmental Engineer and the supporting team shall comply with all applicable laws of the Islamic Republic of Iran, including the Environmental Protection Act (1376), the Tehran Metropolitan Municipality Environmental Regulations, and the DOE-IR technical guidelines for industrial impact assessments.
1. All data collected during the engagement in Iran Tehran shall remain the property of the client. The Environmental Engineer shall not disclose site-specific findings to any third party without written consent.
1. The Environmental Engineer shall provide weekly progress reports and a final comprehensive report in both Persian (Farsi) and English to facilitate submission to Iran Tehran municipal authorities and, if required, international review bodies.
1. Any scope changes, additional monitoring stations, or extended remediation modelling beyond the parameters outlined in this Quotation Estimate shall be subject to a supplementary amendment and additional cost assessment.
1. Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or public health emergencies affecting Iran Tehran, shall suspend the project timeline without penalty to either party.
1. Disputes arising from this Quotation Estimate or the subsequent contract shall be resolved through arbitration in Tehran, Iran, in accordance with the rules of the Tehran Regional Arbitration Center (TRAC).
4. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes GreenSolutions Environmental Consulting Co. to proceed with the engagement of the Environmental Engineer and the delivery of the services described herein for the project located in Iran Tehran.
For GreenSolutions Environmental Consulting Co.

______________________________
Dr. Amir Hosseini, P.E.
Lead Environmental Engineer
Date: _______________
For Tehran Metropolitan Municipality

______________________________
Authorized Representative
Department of Urban Planning & Environmental Compliance
Date: _______________
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