Quotation Estimate - Environmental Engineer Services - Qatar Doha
Quotation Estimate
Professional Environmental Engineering Services
Al Khaleej Environmental Consultancy LLC
Office 412, Business Bay Tower, Street 35, Doha, State of Qatar
Tel: +974-4455-6677 | Email: estimates@alkhaleej-env.qa
Qatar Doha – Licensed Environmental Consultant
Quotation No.: QE-2025-0847
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Project Location: Qatar Doha
1. Client Information
	Client Name:
	Qatar Development & Infrastructure Authority (QDIA)

	Project Address:
	Industrial Area, Doha, State of Qatar

	Point of Contact:
	Eng. Khalid Al-Mansoori – Project Director

	Reference No.:
	QDIA/ENV/2025/0312


2. Scope of Work – Environmental Engineer Services
This Quotation Estimate is issued by Al Khaleej Environmental Consultancy LLC to provide comprehensive Environmental Engineer services for the proposed mixed-use development project located in the Industrial Area of Qatar Doha. The scope encompasses all phases of environmental assessment, regulatory compliance, and sustainability planning in accordance with the Qatar Environment and Energy Agency (QEEA) regulations and the National Vision 2030 environmental directives.
The designated Environmental Engineer, holding a Master's degree in Environmental Engineering from a recognized international university and possessing over twelve (12) years of professional experience in the Gulf region, will lead all technical deliverables. The Environmental Engineer will ensure full compliance with Qatar Doha municipal bylaws, Qatari environmental standards, and international best practices for sustainable development.
3. Itemized Cost Breakdown
	Item No.
	Description of Service
	Duration
	Unit Cost (QAR)
	Amount (QAR)

	01
	Initial Environmental Impact Assessment (EIA) – Site survey, baseline data collection, and stakeholder consultation in Qatar Doha
	6 weeks
	—
	185,000

	02
	Air Quality Impact Modelling and Dispersion Study conducted by the lead Environmental Engineer
	4 weeks
	—
	92,500

	03
	Water Resources and Wastewater Management Plan for the Qatar Doha project site
	5 weeks
	—
	78,000

	04
	Soil and Groundwater Contamination Assessment with laboratory analysis
	3 weeks
	—
	54,000

	05
	Noise and Vibration Impact Assessment per Qatari Environmental Standards
	3 weeks
	—
	42,000

	06
	Environmental Management Plan (EMP) and Monitoring Protocol preparation
	4 weeks
	—
	67,500

	07
	Regulatory Submissions and Liaison with QEEA and Qatar Doha Municipal authorities
	Ongoing
	—
	38,000

	08
	Sustainability and Green Building Certification Support (Qatar Green Building Council)
	4 weeks
	—
	55,000

	09
	Post-Construction Environmental Monitoring (12-month period) supervised by the Environmental Engineer
	12 months
	—
	120,000

	10
	Final Environmental Compliance Report and Project Closure Documentation
	2 weeks
	—
	30,000

	Subtotal
	762,000

	VAT (5%)
	38,100

	TOTAL AMOUNT (QAR)
	800,100


4. Payment Schedule
This Quotation Estimate stipulates the following payment milestones, payable within fourteen (14) calendar days of invoice issuance:
	Milestone
	Percentage
	Amount (QAR)

	Upon contract signing and mobilization of the Environmental Engineer team
	20%
	160,020

	Submission of EIA report and baseline studies
	25%
	200,025

	Completion of all impact assessments and EMP
	25%
	200,025

	Regulatory approval obtained from QEEA, Qatar Doha
	15%
	120,015

	Completion of 12-month monitoring and final compliance report
	15%
	120,015


5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) days from the date of issue. Any acceptance beyond this period requires written reconfirmation of pricing.
· All Environmental Engineer services shall be performed in strict compliance with Qatari law, Qatar Doha municipal regulations, and QEEA environmental standards.
· The Environmental Engineer and all supporting technical staff shall hold valid Qatari professional licenses and insurance coverage as mandated by the Ministry of Labour.
· Any scope changes or additional services beyond the items listed in this Quotation Estimate shall be subject to a separate written amendment and additional cost approval.
· Confidentiality: All data, reports, and findings generated during the engagement in Qatar Doha shall remain the exclusive property of the client. The Environmental Engineer shall not disclose project details to third parties without written consent.
· Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to extreme weather conditions common to the Qatar Doha climate, government directives, or pandemics.
· Disputes arising from this Quotation Estimate shall be resolved through arbitration in Doha, Qatar, in accordance with the Qatar Arbitration Law.
· The total project duration, including the 12-month monitoring phase, is estimated at approximately fourteen (14) months from the date of contract execution.
6. Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms, scope, and pricing outlined in this Quotation Estimate for Environmental Engineer services in Qatar Doha.
For: Al Khaleej Environmental Consultancy LLC
Name: Eng. Sarah Al-Thani
Title: Lead Environmental Engineer / Managing Director
Date: _______________
For: Qatar Development & Infrastructure Authority
Name: Eng. Khalid Al-Mansoori
Title: Project Director
Date: _______________
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