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QUOTATION ESTIMATE
Professional Environmental Engineering Services — United States Chicago
Quotation No.: QE-CHI-2025-0487
Date of Issue: June 12, 2025
Valid Until: July 12, 2025 (30 days)
Currency: United States Dollar (USD)
Prepared By: Meridian Environmental Consulting Group, LLC
Address: 233 S Wacker Drive, Suite 4200, Chicago, IL 60606, United States
Contact: (312) 555-0198 | quotes@meridianenv.com
IL License No.: 051-004872
Prepared For: Lakefront Development Partners, Inc.
Client Address: 140 N LaSalle Street, Chicago, IL 60602, United States
Project Site: 847 W Fulton Market, Chicago, IL 60607
Project Title: Industrial Site Remediation & Environmental Compliance Assessment
Reference No.: LDP-2025-ENV-003
Point of Contact: Mr. David Hartman, VP of Operations
1. Purpose of This Quotation Estimate
This Quotation Estimate is issued by Meridian Environmental Consulting Group, LLC (hereinafter referred to as "the Consultant") to Lakefront Development Partners, Inc. (hereinafter referred to as "the Client") in connection with the provision of comprehensive Environmental Engineer services for the above-referenced industrial site located in United States Chicago. This document outlines the scope of work, professional fees, project timeline, and all applicable terms governing the engagement. The Quotation Estimate is prepared in accordance with the standards of the American Society of Civil Engineers (ASCE) and complies with all applicable regulations set forth by the Illinois Environmental Protection Agency (IEPA) and the United States Environmental Protection Agency (EPA).
2. Scope of Work
The Environmental Engineer services proposed under this Quotation Estimate encompass the following deliverables and professional activities:
2.1 Phase I & Phase II Environmental Site Assessment
A thorough Phase I Environmental Site Assessment (ESA) in compliance with ASTM E1527-21 standards, followed by a Phase II ESA including soil and groundwater sampling at a minimum of twelve (12) monitoring locations across the 4.2-acre site in United States Chicago. All sampling will be conducted in accordance with IEPA and EPA protocols.
2.2 Remediation Design & Engineering
Development of a comprehensive remediation engineering plan, including but not limited to: soil excavation and off-site disposal specifications, in-situ chemical oxidation (ISCO) design, groundwater pump-and-treat system engineering, and vapor mitigation system design. The Environmental Engineer will prepare all construction drawings, specifications, and technical reports required for IEPA permit submission.
2.3 Regulatory Compliance & Permitting
Preparation and submission of all necessary permits to the Illinois EPA, the United States EPA Region 5 office, and the City of Chicago Department of Buildings. This includes the preparation of a Remedial Action Plan (RAP) and coordination with the Illinois State Pollutant Discharge Elimination System (IL-SPDES) program.
2.4 Construction Phase Environmental Oversight
On-site Environmental Engineer supervision during the active remediation phase, including weekly progress reports, quality assurance/quality control (QA/QC) sampling, and monthly compliance reporting to regulatory authorities.
2.5 Post-Remediation Verification & Closure
Conduct of post-remediation verification sampling, preparation of the final Remediation Completion Report, and coordination with IEPA for formal site closure and issuance of a No Further Action (NFA) letter.
3. Fee Schedule & Cost Breakdown
	No.
	Description of Environmental Engineer Services
	Duration
	Rate (USD)
	Total (USD)

	1
	Phase I & Phase II Environmental Site Assessment (including laboratory analysis of 48 soil and 24 groundwater samples)
	8 weeks
	$18,500
	$18,500.00

	2
	Remediation Engineering Design, Construction Drawings & Technical Reports
	12 weeks
	$42,000
	$42,000.00

	3
	Regulatory Permitting, RAP Preparation & Agency Coordination (IEPA, EPA Region 5, City of Chicago)
	10 weeks
	$24,750
	$24,750.00

	4
	Construction Phase Environmental Oversight & QA/QC (estimated 16 weeks of on-site supervision)
	16 weeks
	$3,200/week
	$51,200.00

	5
	Post-Remediation Verification Sampling & Site Closure Documentation
	6 weeks
	$16,800
	$16,800.00

	6
	Contingency & Unforeseen Site Conditions (10% of subtotal)
	—
	—
	$15,325.00

	TOTAL ESTIMATED PROFESSIONAL FEES
	$169,575.00


Note: The above Quotation Estimate does not include third-party laboratory analysis costs, off-site disposal fees, or construction costs, which will be billed directly to the Client at actual cost. All fees are exclusive of applicable Illinois state and federal taxes. Travel expenses within the City of Chicago and Cook County are included; travel beyond a 50-mile radius of downtown Chicago will be billed at $0.85 per mile plus lodging at actual cost.
4. Project Timeline
The total estimated project duration from mobilization to site closure is approximately 52 weeks (13 months), subject to regulatory review timelines and weather conditions typical of the United States Chicago climate. A detailed Gantt chart will be provided upon execution of the contract.
5. Payment Terms
Payment shall be made in accordance with the following schedule: 20% upon contract execution, 25% upon completion of Phase II ESA, 25% upon approval of the Remediation Design, 15% upon completion of construction oversight, and 15% upon issuance of the NFA letter. Invoices are due within thirty (30) days of receipt. Late payments shall accrue interest at 1.5% per month.
6. Terms & Conditions
This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Acceptance of this Quotation Estimate constitutes a binding agreement between the parties. The Environmental Engineer services shall be performed in a professional and workmanlike manner consistent with the standards of practice in the State of Illinois. The Consultant shall maintain professional liability insurance of no less than $2,000,000 per occurrence. This agreement is governed by the laws of the State of Illinois, and any disputes shall be resolved through binding arbitration in Chicago, Illinois, in accordance with the rules of the American Arbitration Association.
7. Acceptance & Authorization
By signing below, the Client acknowledges receipt of this Quotation Estimate and authorizes Meridian Environmental Consulting Group, LLC to proceed with the Environmental Engineer services as described herein for the project site located in United States Chicago.
For the Consultant:
Meridian Environmental Consulting Group, LLC
Signature: ___________________________
Name: Dr. Sarah K. Mitchell, P.E., P.G.
Title: Principal Environmental Engineer
Date: ___________________________
For the Client:
Lakefront Development Partners, Inc.
Signature: ___________________________
Name: ___________________________
Title: ___________________________
Date: ___________________________
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