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1. Purpose of This Quotation Estimate
This Quotation Estimate is issued by Pacific Coast Environmental Consulting, LLC to Meridian Development Group, Inc. in connection with the provision of comprehensive Environmental Engineer services for the proposed mixed-use development project located in the downtown corridor of United States Los Angeles. This document outlines the scope of professional services, associated costs, project timeline, and contractual terms governing the engagement. All pricing presented herein reflects current market rates for licensed Environmental Engineer professionals operating within the jurisdiction of Los Angeles County, California, and complies with all applicable federal, state, and municipal regulatory frameworks.
2. Scope of Environmental Engineer Services
The Environmental Engineer team assigned to this project will deliver the following professional services in accordance with the California Environmental Quality Act (CEQA), the National Environmental Policy Act (NEPA), and all Los Angeles Department of Building and Safety (LADBS) environmental compliance requirements:
	#
	Service Description
	Duration
	Professional
	Estimated Cost (USD)

	1
	Phase I Environmental Site Assessment (ESA) including historical records review, site reconnaissance, and regulatory database search for the 12-acre parcel in downtown Los Angeles.
	4 weeks
	Senior Environmental Engineer
	$18,500.00

	2
	Phase II Environmental Site Assessment including soil and groundwater sampling, laboratory analysis, and contaminant characterization per EPA and California DTSC protocols.
	6 weeks
	Environmental Engineer Team (3)
	$42,750.00

	3
	Stormwater Management and Water Quality Control Plan design in compliance with the Los Angeles Regional Stormwater Quality Management Plan and NPDES General Permit.
	8 weeks
	Lead Environmental Engineer
	$31,200.00

	4
	Air Quality Impact Assessment and Construction Emissions Analysis per South Coast Air Quality Management District (SCAQMD) Rule 403 and Rule 483 requirements.
	5 weeks
	Environmental Engineer / Air Quality Specialist
	$24,800.00

	5
	CEQA Initial Study / Negative Declaration preparation, public review coordination, and response to comments from the City of Los Angeles Planning Department.
	10 weeks
	Environmental Engineer / CEQA Analyst
	$38,600.00

	6
	Construction Environmental Monitoring Plan (CEMP) development, including noise, dust, vibration, and traffic management protocols for the Los Angeles construction site.
	4 weeks
	Environmental Engineer
	$15,900.00

	7
	Wetland delineation, biological resource survey coordination, and habitat conservation compliance for the Los Angeles River adjacent parcel boundary.
	6 weeks
	Environmental Engineer / Biologist
	$22,400.00

	8
	Final environmental compliance reporting, permit submittal support, and 12-month post-construction monitoring oversight.
	12 months
	Environmental Engineer (Oversight)
	$28,350.00


3. Cost Summary
	Subtotal — Professional Environmental Engineer Services
	$222,500.00

	Laboratory Analysis and Third-Party Testing Fees
	$14,200.00

	Permit Filing Fees (City of Los Angeles, SCAQMD, RWQCB)
	$6,850.00

	Travel, Fieldwork, and Mobilization (Los Angeles Metro Area)
	$3,400.00

	Applicable California State Sales Tax (7.25%)
	$18,270.63

	TOTAL ESTIMATED COST
	$265,220.63


4. Terms and Conditions of This Quotation Estimate
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issuance. After the expiration date, all rates and availability of the Environmental Engineer team are subject to re-evaluation.
1. All services shall be performed by a licensed Professional Engineer (PE) holding a valid California license in the discipline of Environmental Engineering, as required by the California Board for Professional Engineers, Land Surveyors, and Geologists.
1. Payment terms: 30% upon execution of the contract, 40% upon completion of Phase I and Phase II assessments, and 30% upon final delivery of all compliance documentation and permit approvals.
1. Any change in scope, additional regulatory requirements imposed by the City of Los Angeles or state agencies, or unforeseen site conditions discovered during fieldwork in United States Los Angeles shall be documented via a formal Change Order and priced separately.
1. The Environmental Engineer of record assumes professional liability for the accuracy of all technical analyses, reports, and design documents delivered under this engagement, consistent with the standard of care expected of a reasonably competent environmental engineer practicing in the State of California.
1. All work products, including but not limited to environmental reports, maps, data sets, and permit applications, shall become the property of the client upon full payment. The consulting firm retains the right to reference the project in professional portfolios with client written consent.
1. This engagement is governed by the laws of the State of California. Any disputes arising from this Quotation Estimate or the resulting contract shall be resolved through binding arbitration in Los Angeles County, United States, in accordance with the rules of the American Arbitration Association.
1. The client acknowledges that the Environmental Engineer services described herein are advisory and technical in nature and do not constitute a guarantee of permit approval by any governmental agency in Los Angeles or the State of California.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes Pacific Coast Environmental Consulting, LLC to proceed with the engagement of the Environmental Engineer team for the project located in United States Los Angeles under the terms and conditions stated herein.
For: Pacific Coast Environmental Consulting, LLC
Name: Dr. Maria Santos, P.E.
Title: Principal Environmental Engineer
Date: ______________________
For: Meridian Development Group, Inc.
Name: ______________________
Title: ______________________
Date: ______________________
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