Quotation Estimate - Film Director Services - Argentina Córdoba
QUOTATION ESTIMATE
Professional Film Director Services — Argentina Córdoba
Service Provider
Andes Vision Productions S.R.L.
Av. Vélez Sarsfield 1247, Piso 4
Córdoba, Córdoba, Argentina
CUIT: 30-71234567-8
Phone: +54 351 422-8890
Email: produccion@andesvision.com.ar
Client Information
Client Name: [To be completed]
Company: [To be completed]
Address: [To be completed]
City: Córdoba, Argentina
Contact: [To be completed]
Email: [To be completed]
Quotation Estimate No.: QTE-AC-2025-0487
Date of Issue: 15 June 2025
Valid Until: 15 July 2025 (30 calendar days)
Project Location: Córdoba, Argentina (principal filming locations within the province of Córdoba)
Currency: Argentine Pesos (ARS) / US Dollars (USD) — dual pricing provided
1. Scope of Services — Film Director Engagement
This Quotation Estimate is issued by Andes Vision Productions S.R.L. to formally propose the professional services of a Film Director for the production of a feature-length narrative film (approximately 90 minutes of screen time) to be shot primarily in and around the city of Argentina Córdoba and its surrounding regions, including the Sierras Chicas, the historic center of Córdoba, and selected rural locations in the province. The Film Director engagement encompasses all creative and operational leadership responsibilities from pre-production through final delivery, as detailed in the itemized breakdown below.
2. Itemized Cost Breakdown
	#
	Service / Deliverable
	Duration / Qty
	Unit Price (ARS)
	Subtotal (ARS)

	1
	Pre-Production — Script Development & Storyboarding
Collaboration with the screenwriting team, visual concept development, shot-by-shot storyboard creation, and location scouting across Córdoba, Argentina.
	4 weeks
	ARS 1,850,000 / week
	ARS 7,400,000

	2
	Pre-Production — Casting & Rehearsals
Direction of casting sessions in Córdoba, Argentina; coordination with local casting agencies; table reads and on-set rehearsal blocks with principal cast.
	3 weeks
	ARS 1,600,000 / week
	ARS 4,800,000

	3
	Principal Photography — On-Set Direction
Full creative and operational direction during the shooting schedule. Includes daily call sheet oversight, actor direction, camera movement coordination, and real-time creative decision-making at all filming locations in Argentina Córdoba.
	28 shooting days
	ARS 2,200,000 / day
	ARS 61,600,000

	4
	Second Unit & Pick-Up Shots Direction
Supervision and direction of second-unit sequences, insert shots, and any post-production pick-up photography required to complete the visual narrative.
	5 days
	ARS 1,900,000 / day
	ARS 9,500,000

	5
	Post-Production — Editorial Direction
Active participation in the editing process, review of rough cuts, fine cuts, and final picture lock. Direction of color grading sessions and final visual polish. Conducted at the editing facility in Córdoba, Argentina.
	6 weeks
	ARS 1,400,000 / week
	ARS 8,400,000

	6
	Post-Production — Sound & Score Supervision
Direction of sound design sessions, foley recording, and orchestral score recording. Coordination with the composer and sound team to ensure the Film Director's creative vision is fully realized in the final mix.
	3 weeks
	ARS 1,200,000 / week
	ARS 3,600,000

	7
	Marketing & Festival Circuit Support
Attendance at press events, film festivals (including the Festival Internacional de Cine de Mar del Plata and local Córdoba screenings), and promotional interviews. The Film Director will represent the project in all public-facing activities.
	2 months
	ARS 950,000 / month
	ARS 1,900,000

	8
	Travel & Accommodation Allowance
Coverage of the Film Director's travel, lodging, and per diem for all location shoots across the province of Córdoba, Argentina, including remote Sierras Chicas sites.
	45 days
	ARS 380,000 / day
	ARS 17,100,000

	9
	Contingency & Overtime Provision
Reserved budget for schedule overruns, weather-related delays (common in Córdoba's variable climate), and additional creative sessions beyond the base scope.
	10% of subtotal
	—
	ARS 11,430,000

	TOTAL ESTIMATED COST (before IVA 21%)
	ARS 125,730,000

	IVA (21% — Argentine Value Added Tax)
	ARS 26,403,300

	GRAND TOTAL (ARS)
	ARS 152,133,300

	GRAND TOTAL (USD equivalent at ARS 1,050/USD)
	USD 144,889


3. Payment Schedule
This Quotation Estimate proposes the following payment milestones, all payable to Andes Vision Productions S.R.L. via bank transfer to the account registered in Córdoba, Argentina:
	Milestone
	Percentage
	Amount (ARS)
	Trigger

	Contract Signing
	20%
	ARS 30,426,660
	Upon mutual execution of the service agreement

	Pre-Production Completion
	15%
	ARS 22,819,995
	Delivery of final storyboard and locked shooting schedule

	Principal Photography (50%)
	25%
	ARS 38,033,325
	Completion of 14 of 28 shooting days

	Principal Photography (100%)
	15%
	ARS 22,819,995
	Final shooting day wrap

	Post-Production & Delivery
	20%
	ARS 30,426,660
	Delivery of final DCP and digital master

	Marketing & Festival Wrap
	5%
	ARS 7,606,665
	Completion of all promotional obligations


4. Terms and Conditions
4.1 Validity. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, all pricing is subject to revision due to currency fluctuation, availability of the Film Director, and changes in local production costs within Argentina Córdoba.
4.2 Scope Changes. Any modification to the creative scope, shooting schedule, or location requirements beyond those specified in this document will be addressed through a formal Change Order, signed by both parties. The Film Director reserves the right to adjust the timeline and associated costs accordingly.
4.3 Location Permits. The client is responsible for securing all municipal, provincial, and national filming permits required by the city of Córdoba, the province of Córdoba, and any federal agencies in Argentina. The Film Director will provide technical input for permit applications but does not bear the cost of permit fees.
4.4 Intellectual Property. Upon full payment, all creative direction materials, storyboards, shot lists, and editorial decisions made by the Film Director become the property of the client. The Film Director retains the right to display the completed work in personal portfolios, festival submissions, and industry showcases.
4.5 Force Majeure. Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to severe weather events in Córdoba, Argentina, government-mandated shutdowns, or natural disasters affecting the province.
4.6 Governing Law. This agreement and this Quotation Estimate shall be governed by the civil and commercial laws of the Province of Córdoba, Argentina, and the national laws of the Argentine Republic. Any disputes shall be resolved through arbitration in Córdoba, Argentina.
4.7 Confidentiality. Both parties agree to maintain strict confidentiality regarding the creative content, financial terms, and production details of this project. This obligation survives the termination of the engagement for a period of three (3) years.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes Andes Vision Productions S.R.L. to proceed with the engagement of the Film Director for the production described herein, to be executed in Argentina Córdoba under the terms and conditions stated above.
For Andes Vision Productions S.R.L.
Name: ___________________________
Title: Managing Director
Date: ___________________________
For the Client
Name: ___________________________
Title: ___________________________
Date: ___________________________
Quotation Estimate No. QTE-AC-2025-0487 — Issued by Andes Vision Productions S.R.L., Córdoba, Argentina.
This document is a formal Quotation Estimate for Film Director services and does not constitute a binding contract until countersigned by both parties.
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