# Quotation Estimate - Film Director Services | India Mumbai

# QUOTATION ESTIMATE

## Film Director Services & Creative Direction

Professional Cinematic Direction | India Mumbai

Quotation No.: QTE-MUM-2025-0472
Date of Issue: 15 June 2025
Valid Until: 15 July 2025

Prepared By: CineCraft Productions Pvt. Ltd.
Location: Andheri West, Mumbai, Maharashtra, India
Contact: +91-22-4567-8900 | info@cinecraftmumbai.in

1. Client / Project Details

| Field | Details |
| --- | --- |
| Client Name | Stellar Media House Pvt. Ltd., Nariman Point, Mumbai, India |
| Project Title | "Monsoon Echoes" – Feature Film (90 min runtime) |
| Project Type | Feature-length narrative film with commercial promotional segments |
| Shooting Location | Mumbai, India (Andheri, Juhu, Bandra, and suburban locations) |
| Estimated Shoot Duration | 22 working days (including 3 buffer days) |
| Post-Production Window | 45 calendar days from last day of principal photography |

2. Scope of Work – Film Director Services

This Quotation Estimate outlines the comprehensive services to be rendered by our senior Film Director and associated creative team for the production of "Monsoon Echoes." The engagement is specifically tailored to the cinematic landscape of India Mumbai, leveraging the city's diverse locations, skilled crew base, and world-class post-production infrastructure. The Film Director shall be responsible for the following:

- Creative Vision & Pre-Production: Development of the director's treatment, shot-by-shot storyboard, location scouting across Mumbai's iconic and hidden locales, casting direction, and rehearsal scheduling. The Film Director will conduct a minimum of four full-table reads with the principal cast in Mumbai.

- Principal Photography Direction: On-set direction of all actors, camera operators, and department heads across 22 shooting days. The Film Director will manage the daily shooting schedule, ensure continuity, and maintain the artistic integrity of the project throughout the production phase in India Mumbai.

- Post-Production Supervision: The Film Director will oversee the editing process, select and direct the final cut, supervise the color grading, sound design, and music scoring sessions. All post-production work will be coordinated through studios located in Mumbai, India.

- Marketing & Festival Support: The Film Director will participate in up to three promotional interviews, one press conference in Mumbai, and provide creative input for the film's trailer and marketing materials.

3. Financial Breakdown – Quotation Estimate

| # | Service / Item | Duration / Qty | Rate (INR) | Amount (INR) |
| --- | --- | --- | --- | --- |
| 1 | Film Director – Pre-Production (Treatment, Storyboard, Casting, Rehearsals) | 30 days | ₹85,000/day | ₹25,50,000 |
| 2 | Film Director – Principal Photography (On-Set Direction) | 22 days | ₹1,20,000/day | ₹26,40,000 |
| 3 | Film Director – Post-Production Supervision (Editing, Color, Sound, Score) | 45 days | ₹60,000/day | ₹27,00,000 |
| 4 | Assistant Director (AD) – Full Production Cycle | 97 days | ₹35,000/day | ₹33,95,000 |
| 5 | Director's Second Unit (B-Roll & Insert Shots, Mumbai Locations) | 5 days | ₹55,000/day | ₹2,75,000 |
| 6 | Location Scouting & Permits (Mumbai Municipal & State Permits) | Lump Sum | — | ₹4,50,000 |
| 7 | Marketing & Festival Appearances (3 interviews + 1 press event) | Lump Sum | — | ₹1,80,000 |
| 8 | Travel, Accommodation & Per Diem (Film Director & AD, within Mumbai) | 97 days | ₹8,000/day | ₹7,76,000 |
| 9 | Contingency & Buffer (10% of subtotal) | — | — | ₹12,96,100 |
| GRAND TOTAL (Inclusive of all charges) |  |  |  | ₹1,42,62,100 |
| Applicable GST (18% on service charges) |  |  |  | ₹25,67,178 |
| TOTAL PAYABLE (INR) |  |  |  | ₹1,68,29,278 |

Amount in words: One Crore Sixty-Eight Lakh Twenty-Nine Thousand Two Hundred and Seventy-Eight Indian Rupees Only.

4. Payment Schedule

| Milestone | Percentage | Amount (INR) | Due Date |
| --- | --- | --- | --- |
| Advance (upon signing of this Quotation Estimate) | 30% | ₹50,48,783 | Within 7 days of acceptance |
| Pre-Production Completion | 20% | ₹33,65,856 | Upon delivery of final storyboard & cast confirmation |
| Principal Photography Completion | 30% | ₹50,48,783 | Within 10 days of wrap day |
| Final Delivery (Post-Production Complete) | 20% | ₹33,65,856 | Upon delivery of final DCP & digital masters |

5. Terms & Conditions

- This Quotation Estimate is valid for 30 calendar days from the date of issue. Beyond this period, rates may be revised based on market conditions in the India Mumbai film industry.

- All payments shall be made via bank transfer to CineCraft Productions Pvt. Ltd., HDFC Bank, Andheri West Branch, Mumbai, India. Cheques payable to "CineCraft Productions Pvt. Ltd."

- The Film Director retains full creative authority over artistic decisions during production. However, the Client retains final approval rights over the completed film as per the separate Production Agreement.

- Any change in shooting schedule exceeding 5 additional days in Mumbai, India, or relocation of principal photography to another city in India, shall be subject to a revised Quotation Estimate and mutual written consent.

- The Film Director and all crew members shall comply with all applicable laws of India, including the Cinematographers Act, 1927, and local municipal regulations of Mumbai.

- Intellectual property of the final film shall vest with the Client upon full and final payment. The Film Director retains the right to display the work in personal portfolios and festival submissions.

- Force Majeure: Neither party shall be liable for delays caused by monsoon flooding, government-imposed lockdowns, or other events beyond reasonable control, which are common considerations for film production in India Mumbai.

- Disputes arising from this Quotation Estimate shall be resolved through arbitration in Mumbai, Maharashtra, India, in accordance with the Arbitration and Conciliation Act, 1996.

- This document constitutes a Quotation Estimate only and does not form a binding contract until both parties execute the definitive Production Agreement.

6. Acceptance & Authorization

By signing below, the Client acknowledges receipt of this Quotation Estimate for Film Director services in India Mumbai and agrees to the terms, conditions, and financial breakdown outlined herein. This acceptance does not constitute a final contract but serves as a binding expression of intent to proceed to the definitive Production Agreement within 14 days.

For CineCraft Productions Pvt. Ltd.
(Film Director & Production House)
Mumbai, India

Name: _________________________
Designation: _________________________
Date: _________________________

For Stellar Media House Pvt. Ltd.
(Client / Producer)
Mumbai, India

Name: _________________________
Designation: _________________________
Date: _________________________

CineCraft Productions Pvt. Ltd. | CIN: U92100MH2018PTC312456 | GSTIN: 27AABCC1234F1Z5

Plot 42, Film City Complex, Andheri West, Mumbai – 400053, Maharashtra, India

This Quotation Estimate is generated electronically and is valid without a physical stamp. For queries, contact: estimates@cinecraftmumbai.in