# Quotation Estimate - Film Director Services - Indonesia Jakarta

# PT Sinema Nusantara Kreatif

Jl. Sudirman Kav. 45, Menteng

Jakarta Pusat 10310, Indonesia

Tel: +62-21-5555-0198 | Email: quotation@sinemanusantara.co.id

NPWP: 01.234.567.8-051.000

Quotation No: QTE-JKT-2025-0847

Date: 15 June 2025

Valid Until: 15 July 2025

## QUOTATION ESTIMATE

Film Director Services — Indonesia Jakarta

| Prepared For: | PT Global Media Vision Indonesia Jl. Gatot Subroto No. 88, Kuningan, Jakarta Selatan 12950 |
| --- | --- |
| Project Title: | "Nusantara Heritage" — 90-Minute Documentary Feature Film |
| Location of Work: | Indonesia Jakarta (Primary) and surrounding provinces |
| Estimated Duration: | 12 weeks (Pre-production through Post-production) |
| Currency: | Indonesian Rupiah (IDR) |

### 1. Scope of Services — Film Director Engagement

This Quotation Estimate is issued by PT Sinema Nusantara Kreatif to formally outline the professional fees, deliverables, and associated costs for the engagement of a senior Film Director for the production of a 90-minute documentary feature film. The primary production base will be located in Indonesia Jakarta, with supplementary location shoots in Yogyakarta, Bali, and East Kalimantan. The Film Director will be responsible for the complete creative vision, on-set direction, actor and subject performance guidance, storyboard development, and final editorial oversight of the project. All services described in this Quotation Estimate are tailored specifically to the production standards, regulatory environment, and cultural context of Indonesia Jakarta and the broader Indonesian film industry.

### 2. Itemized Cost Breakdown

| No. | Description of Service | Duration / Qty | Unit Rate (IDR) | Subtotal (IDR) |
| --- | --- | --- | --- | --- |
| 1 | Film Director — Pre-production consultation, script development, and creative concept design in Indonesia Jakarta | 3 weeks | 45,000,000 | 135,000,000 |
| 2 | Film Director — On-set direction and performance coaching (primary shoot in Indonesia Jakarta) | 4 weeks | 55,000,000 | 220,000,000 |
| 3 | Film Director — Location shoot supervision in Yogyakarta, Bali, and East Kalimantan | 3 weeks | 60,000,000 | 180,000,000 |
| 4 | Film Director — Post-production editorial direction, color grading oversight, and final cut approval in Indonesia Jakarta | 2 weeks | 50,000,000 | 100,000,000 |
| 5 | Assistant Film Director (2 persons) — Full production support across all phases in Indonesia Jakarta | 12 weeks | 12,000,000 | 288,000,000 |
| 6 | Production coordinator and local logistics team based in Indonesia Jakarta | 12 weeks | 8,500,000 | 102,000,000 |
| 7 | Travel, accommodation, and per diem for Film Director and crew (Jakarta to regional locations) | 3 weeks | 18,000,000 | 54,000,000 |
| 8 | Permits, licensing, and regulatory compliance for film production in Indonesia Jakarta (Kominfo, local government) | 1 lot | 25,000,000 | 25,000,000 |
| 9 | Screening and client review sessions (3 sessions) at a private cinema in Indonesia Jakarta | 3 sessions | 7,500,000 | 22,500,000 |
| 10 | Final deliverables: 4K master file, DCP, and promotional trailer (directed by Film Director) | 1 lot | 35,000,000 | 35,000,000 |
| SUBTOTAL (IDR) |  |  |  | 1,161,500,000 |
| VAT 11% (Indonesia) |  |  |  | 127,765,000 |
| TOTAL AMOUNT DUE (IDR) |  |  |  | 1,289,265,000 |

### 3. Payment Terms

Payment for this Quotation Estimate shall be made in three installments: 40% upon contract signing, 35% upon completion of principal photography in Indonesia Jakarta and regional locations, and 25% upon final delivery of all master files. All payments shall be transferred via bank transfer to the account of PT Sinema Nusantara Kreatif, Bank Mandiri, Jakarta.

### 4. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, all rates and availability of the Film Director are subject to revision.

- The Film Director retains full creative authority over the final cut of the film, subject to one (1) round of client-approved revisions as outlined in the production agreement.

- All production activities in Indonesia Jakarta and other Indonesian locations shall comply with the regulations set forth by the Ministry of Communication and Information Technology (Kominfo) and applicable local government ordinances.

- Any change in scope, additional shooting days, or extended post-production work beyond the 12-week timeline will be subject to a supplementary Quotation Estimate issued separately.

- The Film Director and all crew members shall be provided with comprehensive production insurance covering the duration of the engagement in Indonesia Jakarta and all regional shoot locations.

- Intellectual property rights to the final film shall transfer to the client upon full payment. The Film Director retains the right to display the work in professional portfolios and industry festivals.

- This Quotation Estimate does not constitute a binding contract until both parties have executed the formal Production Services Agreement.

- All costs are quoted in Indonesian Rupiah (IDR). No foreign currency conversion is applicable as all services are rendered within Indonesia Jakarta and its surrounding regions.

### 5. Acceptance and Authorization

By signing below, both parties acknowledge and accept the terms, conditions, and financial obligations outlined in this Quotation Estimate for the Film Director engagement in Indonesia Jakarta. This document serves as the formal basis for the subsequent Production Services Agreement.

For PT Sinema Nusantara Kreatif
Name: _________________________
Title: Head of Production
Date: _________________________

For PT Global Media Vision Indonesia
Name: _________________________
Title: _________________________
Date: _________________________

PT Sinema Nusantara Kreatif — Quotation Estimate QTE-JKT-2025-0847 — Film Director Services — Indonesia Jakarta

This document is generated electronically and is valid without a physical stamp. For inquiries, contact quotation@sinemanusantara.co.id.