# Quotation Estimate - Film Director Services - Iraq Baghdad

# QUOTATION ESTIMATE

Professional Film Director Services — Iraq Baghdad

Ref: QTE-IRB-2025-0417 | Issued by: Cinematic Vision Productions Ltd.

| Quotation Estimate No. | QTE-IRB-2025-0417 | Date of Issue | 14 June 2025 |
| --- | --- | --- | --- |
| Valid Until | 14 July 2025 (30 days) | Currency | US Dollars (USD) |
| Client Name | Al-Rafidain Media Group | Client Address | Al-Mansour District, Baghdad, Iraq |
| Project Location | Baghdad, Iraq — Primary filming at Tigris Riverfront, Al-Mutanabbi Street, and selected studio facilities in Baghdad |  |  |
| Project Title | "Echoes of the Tigris" — Feature Documentary (90 minutes) |  |  |

## 1. Scope of Services — Film Director Engagement in Iraq Baghdad

This Quotation Estimate is prepared specifically for the engagement of a senior Film Director to oversee the complete production of a 90-minute feature documentary titled "Echoes of the Tigris." All services described herein will be delivered on location in Iraq Baghdad, encompassing pre-production planning, principal photography, and post-production supervision. The Film Director will be responsible for the creative vision, on-set management, and final artistic delivery of the project, working in close coordination with the client's production team based in Baghdad.

The Film Director will conduct a minimum of three (3) on-site location scouting visits in Iraq Baghdad prior to the start of principal photography. These visits will cover the Tigris Riverfront, historical sites in the Old City of Baghdad, and the client's designated studio in Al-Mansour District. The director will also coordinate with local Iraqi authorities, security personnel, and municipal offices to obtain all necessary filming permits specific to the Iraq Baghdad jurisdiction.

## 2. Itemized Cost Breakdown

| Item No. | Description of Service | Duration / Qty | Unit Rate (USD) | Amount (USD) |
| --- | --- | --- | --- | --- |
| 01 | Pre-production consultation & creative development (script review, storyboard approval, shot-list design) — conducted in Baghdad, Iraq | 10 days | $1,200 | $12,000 |
| 02 | Location scouting & permit coordination in Iraq Baghdad (Tigris Riverfront, Old City, Al-Mutanabbi Street, studio) | 3 visits | $850 | $2,550 |
| 03 | Principal photography — on-set direction, actor/subject coaching, camera direction, lighting supervision | 25 shooting days | $1,500 | $37,500 |
| 04 | Post-production supervision — editing direction, color grading approval, sound design oversight, final cut review | 20 days | $1,100 | $22,000 |
| 05 | Travel, accommodation & local transport within Iraq Baghdad (hotel, airport transfers, city transport) | 60 days | $180 | $10,800 |
| 06 | Security detail coordination & local fixer services specific to Iraq Baghdad filming operations | 60 days | $95 | $5,700 |
| 07 | Contingency & schedule buffer (up to 5 additional days of director availability in Baghdad) | 5 days | $1,500 | $7,500 |
| SUBTOTAL |  |  |  | $98,050 |
| Applicable Taxes & Local Levies (Iraq Baghdad municipal fees, 5%) |  |  |  | $4,902.50 |
| TOTAL QUOTATION ESTIMATE AMOUNT |  |  |  | $102,952.50 |

## 3. Payment Schedule

The total amount stated in this Quotation Estimate shall be paid according to the following milestone schedule, all transactions denominated in US Dollars and processed via international wire transfer to the account of Cinematic Vision Productions Ltd.:

| Milestone | Trigger Event | Percentage | Amount (USD) |
| --- | --- | --- | --- |
| Advance Payment | Upon signed acceptance of this Quotation Estimate | 30% | $30,885.75 |
| Pre-Production Complete | Delivery of approved storyboard and shot-list | 20% | $20,590.50 |
| Principal Photography Complete | Final day of shooting in Iraq Baghdad confirmed | 30% | $30,885.75 |
| Final Delivery | Delivery of final cut and all master files | 20% | $20,590.50 |

## 4. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, all rates and availability of the Film Director are subject to reconfirmation.

- The Film Director shall be available for a minimum of sixty (60) working days in Iraq Baghdad as outlined in the scope of services. Any extension beyond this period will be billed at the daily rate specified in Item 03.

- All filming activities in Iraq Baghdad are subject to obtaining the requisite permits from the Iraqi Ministry of Culture, the Baghdad Municipal Council, and any relevant security clearances. Delays caused by governmental or security-related factors in Iraq Baghdad shall not be considered a breach of schedule by either party.

- The client shall provide a safe working environment in Iraq Baghdad, including but not limited to adequate security arrangements, medical support, and compliance with all Iraqi labor and safety regulations applicable to foreign production crews.

- Intellectual property rights in the final documentary shall vest in the client upon full payment. The Film Director retains the right to display the work in professional portfolios and festival submissions, subject to the client's prior written approval.

- Force majeure events, including but not limited to civil unrest, natural disasters, or government-imposed restrictions in Iraq Baghdad, shall suspend obligations under this agreement for the duration of the event, with a maximum suspension period of thirty (30) days before either party may terminate without penalty.

- Disputes arising from this Quotation Estimate or the resulting engagement shall be resolved through arbitration in accordance with the rules of the International Chamber of Commerce, with the seat of arbitration in Baghdad, Iraq.

- This Quotation Estimate does not constitute a binding contract until countersigned by both parties. Upon signature, it shall form the basis of the definitive Production Services Agreement.

## 5. Acceptance and Authorization

By signing below, both parties acknowledge that they have read, understood, and agree to the terms set forth in this Quotation Estimate for the engagement of a Film Director for production activities in Iraq Baghdad.

For Cinematic Vision Productions Ltd.

Name: _________________________

Title: Head of Production

Signature & Date

For Al-Rafidain Media Group (Client)

Name: _________________________

Title: _________________________

Signature & Date

This Quotation Estimate (Ref: QTE-IRB-2025-0417) was prepared for Film Director services to be executed in Iraq Baghdad. All figures are in US Dollars. This document is confidential and intended solely for the named client. © 2025 Cinematic Vision Productions Ltd. All rights reserved.