Quotation Estimate - Geologist Services - China Shanghai
QUOTATION ESTIMATE
GeoShanghai Professional Services Co., Ltd.
1288 Nanjing East Road, Huangpu District, China Shanghai, 200001
Tel: +86-21-5588-6600 | Email: estimates@geoshanghai.cn
Unified Social Credit Code: 91310101MA1FL8XK2P
	Quotation Estimate No.:
	QEST-2025-SH-0472

	Date of Issue:
	14 June 2025

	Valid Until:
	14 September 2025 (90 calendar days)

	Prepared For:
	Shanghai Municipal Urban Planning & Land Resources Bureau

	Project Reference:
	Geological Survey – Pudong New Area Expansion Zone, China Shanghai

	Prepared By:
	Dr. Wei Zhang, Senior Geologist & Lead Consultant

	Currency:
	Chinese Yuan (CNY / RMB)


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by GeoShanghai Professional Services Co., Ltd. in response to the formal request for geological consulting services in the Pudong New Area Expansion Zone of China Shanghai. The purpose of this document is to provide a comprehensive, itemized cost breakdown for the engagement of a qualified Geologist and supporting geological team to conduct subsurface investigation, geological mapping, and environmental geotechnical assessment for the proposed urban development corridor spanning approximately 42 square kilometres.
The Quotation Estimate covers all professional fees, fieldwork expenses, laboratory analysis, reporting, and project management costs associated with the services of the designated Geologist and the supporting technical staff. All pricing is quoted in Chinese Yuan (CNY) and is inclusive of applicable Value Added Tax (VAT) at the current rate of 6% for professional services as mandated by the State Taxation Administration of the People's Republic of China.
2. Scope of Geological Services
The Geologist engaged under this Quotation Estimate shall perform the following duties within the China Shanghai project area:
· Conduct a detailed geological reconnaissance survey covering the entire 42 km² expansion zone, including identification of bedrock formations, alluvial deposits, and potential fault structures.
· Design and supervise a borehole drilling programme comprising no fewer than 120 boreholes at depths ranging from 15 metres to 80 metres below ground level.
· Perform in-situ geotechnical testing, including Standard Penetration Tests (SPT), Cone Penetration Tests (CPT), and vane shear tests at designated intervals.
· Collect, log, and submit core samples and disturbed soil samples to an accredited laboratory in China Shanghai for petrographic, geochemical, and geotechnical analysis.
· Assess the geological and geohydrological risk profile of the site, with particular attention to the Yangtze River alluvial plain characteristics prevalent in the China Shanghai region.
· Prepare a comprehensive Geological Investigation Report in both English and Mandarin Chinese, compliant with the GB/T 50021-2016 national standard for engineering geological investigation.
· Provide two on-site technical review meetings with the client's engineering team during the fieldwork phase.
3. Itemized Cost Breakdown
	Item No.
	Description of Service / Cost Element
	Unit
	Quantity
	Unit Price (CNY)
	Amount (CNY)

	3.1
	Senior Geologist – Professional Consultancy Fee (project duration: 14 months)
	Month
	14
	48,000
	672,000

	3.2
	Assistant Geologist & Field Team (4 personnel) – Professional Fees
	Month
	14
	18,500
	518,000

	3.3
	Borehole Drilling Programme (120 holes, avg. depth 45 m)
	Hole
	120
	12,800
	1,536,000

	3.4
	In-Situ Geotechnical Testing (SPT, CPT, Vane Shear)
	Test
	480
	1,250
	600,000

	3.5
	Laboratory Analysis – Petrographic, Geochemical & Geotechnical (China Shanghai accredited lab)
	Sample
	600
	850
	510,000

	3.6
	Geological Mapping & GIS Data Compilation (42 km²)
	km²
	42
	3,200
	134,400

	3.7
	Geohydrological Assessment & Groundwater Monitoring (6-month period)
	Lot
	1
	285,000
	285,000

	3.8
	Final Geological Investigation Report (Bilingual: EN/Chinese, 4 copies + digital)
	Lot
	1
	96,000
	96,000

	3.9
	Project Management, Coordination & Client Review Meetings
	Lot
	1
	120,000
	120,000

	3.10
	Field Equipment, Vehicle Hire & Site Logistics (China Shanghai operations)
	Lot
	1
	175,000
	175,000

	3.11
	Insurance, Permits & Regulatory Compliance (China Shanghai municipal authorities)
	Lot
	1
	68,000
	68,000

	Subtotal (Excluding VAT)
	4,780,400

	VAT @ 6%
	286,824

	TOTAL QUOTATION ESTIMATE AMOUNT (Incl. VAT)
	5,067,224


4. Payment Terms
Payment against this Quotation Estimate shall be made in the following instalments, all denominated in CNY and payable via bank transfer to the account of GeoShanghai Professional Services Co., Ltd. at Bank of China, China Shanghai Branch:
1. 30% Advance Payment (CNY 1,520,167.20): Due within 15 business days of mutual execution of the service contract and acceptance of this Quotation Estimate.
1. 40% Progress Payment (CNY 2,026,889.60): Due upon completion of 70% of the borehole drilling programme and submission of the interim fieldwork report.
1. 25% Final Payment (CNY 1,266,806.00): Due within 20 business days of delivery and formal acceptance of the final bilingual Geological Investigation Report.
1. 5% Retention (CNY 253,361.20): Released 12 months after final report acceptance, subject to no outstanding quality claims.
5. Terms and Conditions
1. This Quotation Estimate is valid for a period of 90 calendar days from the date of issue. Beyond this period, all prices are subject to revision based on prevailing market rates in China Shanghai.
1. The Geologist and all supporting personnel shall hold valid professional qualifications recognised by the China Geological Society and the Ministry of Natural Resources of the People's Republic of China.
1. All fieldwork in the China Shanghai project area shall comply with local municipal regulations, environmental protection statutes, and the Shanghai Municipal Geological Survey Management Ordinance.
1. The client shall provide safe access to the site, necessary municipal permits, and coordination with adjacent property owners prior to the commencement of drilling operations.
1. Any variation in scope exceeding 10% of the original work programme shall be subject to a supplementary Quotation Estimate issued by the Geologist and approved in writing by the client before additional work commences.
1. Intellectual property rights in all reports, data sets, and geological models produced under this engagement shall vest in the client upon full and final payment.
1. Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration under the Shanghai International Arbitration Centre (SHIAC) in accordance with its rules of procedure.
1. This Quotation Estimate does not constitute a binding contract until both parties have executed the formal Service Agreement incorporating these terms.
6. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate for Geologist services in China Shanghai and agrees to the terms, conditions, and pricing set forth herein. This acceptance shall serve as the basis for the preparation of the definitive Service Agreement.
For and on behalf of GeoShanghai Professional Services Co., Ltd.
Dr. Wei Zhang – Senior Geologist & Lead Consultant
Signature: ___________________________
Date: ___________________________
Company Seal:
For and on behalf of the Client
Shanghai Municipal Urban Planning & Land Resources Bureau
Signature: ___________________________
Name & Title: ___________________________
Date: ___________________________
Official Seal:
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