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Quotation Estimate
Quotation Details
Quotation No.: QE-2025-MDE-0347
Date Issued: June 12, 2025
Valid Until: July 12, 2025 (30 days)
Project Location: Colombia Medellín, Antioquia Department
Client Information
Company: Constructora Valle del Aburrá S.A.S.
Contact: Ing. María Fernanda Restrepo
Address: Av. La Playa # 45-20, Medellín, Colombia
NIT: 830.456.789-1
1. Scope of Services – Geologist Consultation in Colombia Medellín
This Quotation Estimate is issued by GeoAndes Professional Services S.A.S. to provide comprehensive geological consulting services delivered by a licensed Geologist for the proposed mixed-use development project located in the Aburrá Valley region of Colombia Medellín. The Geologist assigned to this engagement, Dr. Alejandro Cárdena (MSc. in Engineering Geology, Universidad de Antioquia), holds over fifteen years of field experience conducting geological assessments across the Andean geological formations characteristic of the Colombia Medellín metropolitan area and its surrounding municipalities.
The services outlined in this Quotation Estimate encompass a full-cycle geological investigation, including but not limited to: site reconnaissance, subsurface characterization, geotechnical mapping, seismic hazard assessment, groundwater evaluation, and the preparation of a comprehensive geological report compliant with the Colombian National Construction Code (Código de Construcción Sismo Resistente, NSR-10) and the regulations established by the Servicio Geológico Colombiano for the Colombia Medellín jurisdiction.
2. Itemized Cost Breakdown
	No.
	Description of Service
	Quantity
	Unit (COP)
	Total (COP)
	Duration

	01
	Initial site reconnaissance and geological mapping by the Geologist at the project site in Colombia Medellín (El Poblado sector)
	1
	4,500,000
	4,500,000
	3 days

	02
	Subsurface investigation: 4 boreholes (depth 25 m each) with standard penetration tests (SPT) and soil sampling
	4
	8,200,000
	32,800,000
	10 days

	03
	Geotechnical laboratory analysis of soil and rock samples (Atterberg limits, triaxial compression, uniaxial compressive strength, XRD mineralogy)
	1
	12,600,000
	12,600,000
	15 days

	04
	Seismic microzonation and liquefaction potential assessment per NSR-10 for the Colombia Medellín zone
	1
	7,800,000
	7,800,000
	7 days

	05
	Groundwater hydrogeological study: piezometer installation (2 units), water quality analysis, and flow direction mapping
	1
	6,400,000
	6,400,000
	8 days

	06
	Preparation of the final Geological and Geotechnical Report by the Geologist, including recommendations for foundation design, slope stability, and dewatering systems
	1
	9,500,000
	9,500,000
	12 days

	07
	Regulatory submission support: filing the geological report with the Secretaría de Planeación de Medellín and the Servicio Geológico Colombiano
	1
	2,200,000
	2,200,000
	5 days

	08
	On-site supervision during excavation phase (presence of the Geologist for 10 working days)
	10
	480,000
	4,800,000
	10 days

	SUBTOTAL
	80,600,000
	

	VAT (IVA) 19%
	15,314,000
	

	TOTAL (COP)
	95,914,000
	

	TOTAL (USD – approx. at 3,950 COP/USD)
	$24,282.03
	


3. Terms and Conditions of This Quotation Estimate
3.1 Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, prices may be adjusted to reflect changes in material costs, fuel surcharges, or regulatory fee modifications applicable in Colombia Medellín.
3.2 Payment Schedule: 40% upon contract signing, 35% upon completion of fieldwork (boreholes and sampling), and 25% upon delivery and acceptance of the final geological report. All payments shall be made in Colombian Pesos (COP) via bank transfer to the account of GeoAndes Professional Services S.A.S.
3.3 Professional Liability: The Geologist and GeoAndes Professional Services S.A.S. maintain professional liability insurance (póliza de responsabilidad civil profesional) with a coverage of COP 500,000,000, as required by the Colombian Chamber of Geologists (Colegio Colombiano de Geólogos).
3.4 Intellectual Property: All data, maps, borehole logs, and reports generated under this Quotation Estimate shall remain the exclusive property of the client upon full payment. The Geologist retains the right to reference the project in academic publications with prior written consent.
3.5 Force Majeure: Delays caused by seismic events, volcanic activity (including but not limited to the Nevado del Ruiz), heavy rainfall typical of the Colombia Medellín climate, or government-mandated work stoppages shall extend the project timeline without penalty to either party.
3.6 Governing Law: This Quotation Estimate and any resulting contract shall be governed by the civil and commercial laws of the Republic of Colombia. Disputes shall be resolved by the competent courts of Colombia Medellín, Antioquia.
3.7 Confidentiality: Both parties agree to maintain strict confidentiality regarding all geological data, site conditions, and commercial terms disclosed during the execution of this engagement in Colombia Medellín.
4. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes GeoAndes Professional Services S.A.S. to proceed with the geological services described herein, to be performed by the designated Geologist at the project site in Colombia Medellín.
GeoAndes Professional Services S.A.S.
Dr. Alejandro Cárdena – Lead Geologist
NIT: 901.234.567-8
Date: _______________
Constructora Valle del Aburrá S.A.S.
Ing. María Fernanda Restrepo – Project Director
NIT: 830.456.789-1
Date: _______________
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