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QUOTATION ESTIMATE
Professional Geological Services — Geologist Consultation & Site Assessment
Prepared for: Japan Osaka Region
Quotation No.: QE-OSK-2025-0417
Date Issued: 15 June 2025
Valid Until: 15 September 2025
Prepared By: K. Tanaka, P.Geo (Principal Geologist)
Company: Kansai GeoConsulting Co., Ltd.
Address: 3-12-8 Umeda, Kita-ku, Osaka 530-0001, Japan
1. Client Information
	Field
	Details

	Client Name
	Osaka Metropolitan Development Authority

	Project Location
	Chuo-ku, Osaka, Japan (Nishinomiya Basin Corridor)

	Project Reference
	OMDA-2025-Geological Survey Phase II

	Contact Person
	Mr. Hiroshi Yamamoto, Senior Planning Director


2. Scope of Work — Geologist Services in Japan Osaka
This Quotation Estimate outlines the comprehensive professional services to be rendered by a licensed Geologist and supporting geological team for the above-referenced project situated in the Japan Osaka metropolitan area. The scope encompasses the following deliverables:
· Geological Site Investigation: A thorough subsurface geological survey covering a 12-hectare parcel in the Nishinomiya Basin, including borehole drilling (minimum 6 boreholes to a depth of 40 metres), standard penetration tests (SPT), and in-situ shear wave velocity measurements to characterize the alluvial and bedrock strata typical of the Osaka sedimentary basin.
· Seismic Hazard Assessment: Evaluation of liquefaction potential, seismic amplification factors, and fault proximity analysis in accordance with the Japan Building Standards Act (Act No. 202 of 1950) and the Osaka Prefecture Seismic Hazard Mitigation Guidelines. The Geologist will prepare a detailed seismic microzonation map for the Japan Osaka site.
· Groundwater and Hydrogeological Study: Identification of aquifer layers, groundwater flow direction, and contamination risk assessment relevant to the Japan Osaka urban development context, including compliance with the Water Environment Conservation Act.
· Geotechnical Design Parameters: Provision of engineering geological parameters (cohesion, friction angle, compressibility, bearing capacity) for foundation design, retaining structures, and underground excavation planning.
· Regulatory Compliance Reporting: Preparation of all mandatory geological reports required by the Osaka City Planning Bureau and the Ministry of Land, Infrastructure, Transport and Tourism (MLIT) for construction permits in Japan Osaka.
· On-Site Geologist Supervision: Minimum 15 working days of on-site supervision by the Principal Geologist during the active investigation phase, including daily progress logging and real-time quality assurance of sampling procedures.
3. Itemized Cost Breakdown
	Item No.
	Description of Geologist Service
	Unit
	Qty
	Unit Price (JPY)
	Amount (JPY)

	01
	Principal Geologist Professional Fee (design, oversight, and final report authorisation)
	Lot
	1
	1,850,000
	1,850,000

	02
	Borehole Drilling & SPT Testing (6 boreholes × 40 m)
	Borehole
	6
	420,000
	2,520,000

	03
	Seismic Microzonation & Liquefaction Analysis (Japan Osaka site-specific)
	Lot
	1
	980,000
	980,000

	04
	Hydrogeological Investigation & Groundwater Monitoring Setup
	Lot
	1
	640,000
	640,000

	05
	Geotechnical Laboratory Testing (soil mechanics, rock core analysis)
	Lot
	1
	720,000
	720,000

	06
	On-Site Geologist Supervision (15 working days, Japan Osaka)
	Day
	15
	58,000
	870,000

	07
	Regulatory Report Preparation & Submission (Osaka City, MLIT)
	Lot
	1
	450,000
	450,000

	08
	Travel, Accommodation & Local Logistics (Japan Osaka area)
	Lot
	1
	210,000
	210,000

	Subtotal
	8,240,000

	Consumption Tax (10%)
	824,000

	TOTAL (JPY)
	9,064,000


4. Project Timeline
	Phase
	Activity
	Duration
	Target Completion

	Phase 1
	Desk study, site reconnaissance, and mobilisation in Japan Osaka
	2 weeks
	July 2025

	Phase 2
	Field investigation, borehole drilling, and in-situ testing
	4 weeks
	August 2025

	Phase 3
	Laboratory analysis, seismic modelling, and data interpretation
	3 weeks
	September 2025

	Phase 4
	Final Geologist report, regulatory submission, and client presentation
	2 weeks
	October 2025


5. Terms and Conditions
1. This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, all pricing is subject to revision based on prevailing market rates in Japan Osaka.
1. Payment terms: 30% advance payment upon contract execution, 40% upon completion of Phase 2 fieldwork, and 30% upon delivery and acceptance of the final Geologist report.
1. All geological data, reports, and intellectual property generated under this engagement shall become the sole property of the Client upon full payment.
1. The Principal Geologist and all supporting personnel shall hold valid qualifications recognised by the Japan Association of Engineering Geologists (JAEG) and comply with all applicable Japanese professional standards.
1. Any change in scope, additional boreholes, or extended site conditions in the Japan Osaka area shall be subject to a supplementary Quotation Estimate issued prior to commencement of the additional work.
1. Force majeure events, including but not limited to typhoons, earthquakes, or government-mandated work stoppages in Osaka, shall extend the project timeline proportionally without penalty to either party.
1. Disputes arising from this Quotation Estimate shall be resolved through arbitration under the rules of the Japan Commercial Arbitration Association (JCAA), with the seat of arbitration in Osaka, Japan.
1. This document constitutes a formal Quotation Estimate and does not represent a binding contract until countersigned by both parties and executed as a formal service agreement.
6. Acceptance and Authorisation
By signing below, both parties acknowledge and accept the terms, scope, and pricing outlined in this Quotation Estimate for Geologist services to be performed in Japan Osaka.
For: Kansai GeoConsulting Co., Ltd.
Name: K. Tanaka, P.Geo
Title: Principal Geologist / Director
Signature: ___________________________
Date: ___________________________
For: Osaka Metropolitan Development Authority
Name: H. Yamamoto
Title: Senior Planning Director
Signature: ___________________________
Date: ___________________________
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