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1. INTRODUCTION AND SCOPE OF SERVICES
This Quotation Estimate is issued by TerraScope Geological Consultancy Ltd. in response to the request for professional geological assessment services in the Nigeria Lagos metropolitan area. Our firm, with over fifteen years of experience in Nigerian geological surveying and environmental consulting, is pleased to present this detailed Quotation Estimate for the engagement of a senior Geologist and supporting technical team to carry out comprehensive subsurface investigation, soil classification, and geological hazard mapping for the proposed Lagos Coastal Infrastructure Corridor Project.
The scope of work outlined in this Quotation Estimate encompasses all geological fieldwork, laboratory analysis, and reporting activities required to deliver a complete geological feasibility assessment. The Geologist assigned to this project will hold a minimum of ten (10) years of post-qualification experience in Nigerian sedimentary geology, with specific expertise in the coastal and deltaic formations characteristic of the Nigeria Lagos region.
2. ITEMIZED COST BREAKDOWN
	S/N
	Description of Service
	Duration
	Unit Rate (NGN)
	Total Amount (NGN)

	1
	Engagement of Lead Geologist (M.Sc. Geology, MNIS) for site reconnaissance, borehole supervision, and geological interpretation across the Nigeria Lagos project corridor (approx. 42 km)
	21 working days
	₦450,000 / day
	₦9,450,000

	2
	Deployment of two (2) junior geological assistants and one (1) field technician for core logging, sample collection, and in-situ testing at 28 designated borehole locations
	21 working days
	₦180,000 / day (combined)
	₦3,780,000

	3
	Geophysical survey (Electrical Resistivity Tomography and Seismic Refraction) at 14 critical nodes along the Nigeria Lagos coastal stretch
	10 working days
	₦1,200,000 / day
	₦12,000,000

	4
	Laboratory geotechnical and petrographic analysis of 168 soil and rock samples (Atterberg limits, grain size distribution, XRD, thin-section microscopy)
	14 working days
	₦85,000 / sample
	₦14,280,000

	5
	Preparation of the Final Geological Report, including geological cross-sections, lithological columnar logs, foundation recommendations, and a geological hazard risk matrix for the Nigeria Lagos area
	15 working days
	Flat fee
	₦6,500,000

	6
	Mobile laboratory and field equipment mobilization/demobilization (drilling rig, ERT array, seismic geophones, GPS units) within Lagos State
	3 working days
	Flat fee
	₦2,800,000

	7
	Project management, client liaison, regulatory compliance (NESREA, LUSDA permits), and quality assurance/quality control oversight
	Entire project
	Flat fee
	₦3,200,000

	SUBTOTAL
	₦51,010,000

	VAT (7.5%)
	₦3,825,750

	GRAND TOTAL (NGN)
	₦54,835,750


3. TERMS AND CONDITIONS
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any acceptance beyond this period will require a revised Quotation Estimate reflecting current market rates for geological services in Nigeria Lagos.
1. Payment terms: 40% advance mobilization payment upon execution of the contract; 35% upon completion of all fieldwork and borehole drilling; 25% upon delivery and acceptance of the Final Geological Report.
1. All payments shall be made in Nigerian Naira (NGN) via bank transfer to the account details provided in the accompanying invoice. Late payments shall attract a penalty of 1.5% per month on the outstanding balance.
1. The Geologist and technical team shall comply with all applicable Nigerian regulations, including the Nigerian Geological Survey Act, NESREA environmental guidelines, and Lagos State building and infrastructure codes.
1. Any change in scope, additional borehole locations, or extended geophysical survey beyond the parameters stated in this Quotation Estimate shall be subject to a supplemental quotation and written approval from the client prior to execution.
1. TerraScope Geological Consultancy Ltd. shall maintain professional indemnity insurance of not less than ₦500,000,000 for the duration of the project. A certificate of insurance shall be provided upon request.
1. All data, reports, and deliverables produced under this engagement shall become the exclusive property of the client upon full payment. The Geologist and team shall sign a non-disclosure agreement prior to commencing fieldwork in the Nigeria Lagos project area.
1. Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in Lagos, Nigeria, in accordance with the Arbitration and Conciliation Act (Cap A18, LFN 2004).
4. PROJECT TIMELINE
	Phase
	Activity
	Estimated Duration

	Phase 1
	Site reconnaissance, permit acquisition, and mobilization in Nigeria Lagos
	Week 1

	Phase 2
	Borehole drilling, core logging, and geophysical survey by the Geologist team
	Weeks 2–4

	Phase 3
	Laboratory analysis and data interpretation
	Weeks 5–6

	Phase 4
	Report compilation, review, and final submission
	Weeks 7–8


5. ACCEPTANCE AND AUTHORIZATION
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Geologist and associated geological services in Nigeria Lagos.
For and on behalf of TerraScope Geological Consultancy Ltd.

______________________________
Name: Dr. Adewale O. Okonkwo
Title: Lead Geologist / Managing Director
Date: _______________
For and on behalf of the Client (LUSUDA)

______________________________
Name: _________________________
Title: _________________________
Date: _______________
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