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1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Andes Geological Consulting S.A.C. to Minera del Pacífico S.A.C. for the provision of comprehensive geological services to be executed in the metropolitan area of Peru Lima and its surrounding districts. The scope encompasses site characterization, geological mapping, hydrogeological assessment, and environmental geotechnical evaluation for the proposed industrial infrastructure development project located in the Callao district, Peru Lima. This document serves as a formal Quotation Estimate outlining all deliverables, timelines, and associated costs for the client's review and approval.
2. Professional Qualifications of the Geologist
The lead Geologist assigned to this project, Ing. Carlos Mendoza R., holds a Master of Science in Economic Geology from the Pontificia Universidad Católica del Perú (PUCP) and is a registered professional with the Colegio de Ingenieros del Perú (CIP), Registration No. 184523. With over fifteen years of field experience in Peru Lima and the broader Lima region, the Geologist has conducted more than 120 site investigations, geological surveys, and environmental assessments. The supporting team includes two junior geologists, one geotechnical engineer, and a hydrogeology specialist, all of whom are licensed professionals registered with the relevant Peruvian regulatory authorities.
3. Itemized Services and Pricing
	Item
	Description of Service
	Duration
	Unit
	Cost (USD)

	01
	Desktop geological review and compilation of existing data for the Peru Lima project site, including review of IGEPN and SENACE records
	5 working days
	Lump Sum
	$4,800.00

	02
	Field geological mapping and lithological description at the Peru Lima project site (area: 12 hectares), conducted by the lead Geologist and support team
	10 working days
	Lump Sum
	$12,500.00

	03
	Drilling and geotechnical sampling: 8 boreholes to a maximum depth of 30 meters each, including core logging and sample preparation
	15 working days
	8 Boreholes
	$28,400.00

	04
	Hydrogeological assessment: installation of 3 monitoring piezometers, water quality sampling, and groundwater flow analysis for the Peru Lima area
	12 working days
	Lump Sum
	$9,750.00

	05
	Geophysical survey: electrical resistivity tomography (ERT) and seismic refraction across 6 lines (200 m each) to identify subsurface geological structures
	8 working days
	Lump Sum
	$11,200.00

	06
	Seismic hazard and liquefaction potential assessment specific to the Peru Lima coastal plain, including review of historical seismicity data
	7 working days
	Lump Sum
	$7,600.00

	07
	Preparation of the final comprehensive geological report, including maps, cross-sections, data tables, and recommendations for foundation design
	10 working days
	Lump Sum
	$8,900.00

	08
	Regulatory compliance: submission of geological study to the Ministry of Energy and Mines (MINEM) and coordination with local Peru Lima municipal authorities
	5 working days
	Lump Sum
	$3,250.00

	09
	On-site supervision and client presentation of findings by the lead Geologist in Peru Lima (2 sessions)
	2 days
	2 Sessions
	$2,400.00

	SUBTOTAL
	$88,800.00

	IGV (18%)
	$15,984.00

	TOTAL ESTIMATED COST
	$104,784.00


4. Project Timeline
The total estimated duration for the completion of all geological services in Peru Lima is approximately 72 working days (approximately 14 calendar weeks) from the date of contract execution. The schedule will be coordinated with the client's project management team and will account for seasonal weather conditions typical of the Peru Lima coastal region, particularly the influence of the El Niño phenomenon on fieldwork accessibility.
5. Terms and Conditions
· Payment Terms: 30% advance upon contract signing, 40% upon completion of fieldwork, and 30% upon delivery and acceptance of the final geological report.
· Validity: This Quotation Estimate is valid for 30 calendar days from the date of issue. Prices are subject to revision after the expiration date.
· Scope Changes: Any modifications to the scope of geological services in Peru Lima must be agreed upon in writing by both parties. Additional work will be billed at the rates specified in this Quotation Estimate.
· Access and Permits: The client shall provide full access to the project site in Peru Lima and obtain all necessary municipal and environmental permits prior to the commencement of fieldwork.
· Insurance: The Geologist and all field personnel shall be covered under professional liability insurance and workers' compensation as required by Peruvian labor law.
· Confidentiality: All geological data, reports, and findings generated under this Quotation Estimate shall remain the exclusive property of the client and shall not be disclosed to third parties without written consent.
· Dispute Resolution: Any disputes arising from this Quotation Estimate shall be resolved through arbitration in Lima, Peru, in accordance with the rules of the Centro de Arbitraje y Conciliación de la Cámara de Comercio de Lima.
· Force Majeure: Neither party shall be liable for delays caused by natural disasters, government actions, or other events beyond reasonable control, including but not limited to seismic events common to the Peru Lima region.
Note: This Quotation Estimate assumes standard operating conditions in Peru Lima. If the Geologist encounters unexpected subsurface conditions (e.g., high groundwater pressure, unstable soil layers, or contaminated materials) during fieldwork, additional costs may be incurred and will be communicated to the client within 48 hours of discovery.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the geological services to be performed in Peru Lima. This signature constitutes a binding agreement for the services described.
For Andes Geological Consulting S.A.C.
Ing. Carlos Mendoza R., M.Sc.
Lead Geologist & Project Director
CIP Reg. No. 184523
Date: _______________
For Minera del Pacífico S.A.C.
Authorized Representative
Name: _______________
Position: _______________
Date: _______________
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