# Quotation Estimate - Geologist Services - Sudan Khartoum

# Quotation Estimate

Nile Basin Geological & Environmental Consultants

Office No. 42, Al-Muruj Business District, Sudan Khartoum

Tel: +249-183-555-0192 | Email: info@nilebasingeology.sd

Registration No: SD-GEOL-2019-0047 | VAT: 104-228-771

Quotation Estimate No: QTE-2025-KRT-0347

Date of Issue: 14 June 2025

Valid Until: 14 July 2025

Project Location: Sudan Khartoum

## 1. Client Information

| Client Name: | Ministry of Irrigation and Water Resources, Republic of Sudan |
| --- | --- |
| Project Reference: | MWRI-2025-Hydro-Geological Survey – Khartoum North Basin |
| Point of Contact: | Eng. Ahmed El-Tahir, Director of Hydrological Studies |
| Address: | Ministry Complex, Al-Muruj, Sudan Khartoum |

## 2. Scope of Work – Geologist Services in Sudan Khartoum

This Quotation Estimate is prepared by Nile Basin Geological & Environmental Consultants to provide comprehensive professional services rendered by a licensed Geologist for the hydro-geological survey and environmental assessment of the Khartoum North Basin. All fieldwork, laboratory analysis, and reporting will be conducted within the administrative boundaries of Sudan Khartoum, in full compliance with the Sudanese Geological Survey Act (2012) and the Ministry of Environment and Forestry regulations.

The appointed Geologist holds a Master of Science in Applied Geology from the University of Khartoum and possesses over twelve (12) years of field experience in sedimentary basin mapping, groundwater resource assessment, and geological hazard evaluation across the Nile Corridor. The Geologist is registered with the Sudanese Council of Professional Engineers and Geologists (SCPEG) under License No. SCPEG-2013-0891.

## 3. Itemized Cost Breakdown

| No. | Description of Service | Duration | Unit | Amount (Sudanese Pounds – SDG) |
| --- | --- | --- | --- | --- |
| 1 | Professional fee – Senior Geologist (field supervision, site inspection, and geological mapping of the Khartoum North Basin) | 30 days | Per day | 45,000 × 30 = 1,350,000 |
| 2 | Geological field survey and borehole logging (minimum 12 boreholes across Sudan Khartoum district) | 15 days | Per borehole | 85,000 × 12 = 1,020,000 |
| 3 | Rock core sampling and laboratory petrographic analysis (conducted at University of Khartoum Geology Lab) | 10 days | Per sample set | 32,000 × 12 = 384,000 |
| 4 | Groundwater hydro-geological assessment and aquifer characterization report | 20 days | Lump sum | 750,000 |
| 5 | Geological hazard and landslide risk mapping for the Omdurman escarpment area, Sudan Khartoum | 12 days | Lump sum | 520,000 |
| 6 | GIS-based geological database creation and digital map production (scale 1:25,000) | 10 days | Lump sum | 380,000 |
| 7 | Final technical report, executive summary, and two (2) hard-bound copies for the Ministry | 7 days | Lump sum | 120,000 |
| 8 | Travel, local transport, and field logistics within Sudan Khartoum (4×4 vehicle, fuel, and accommodation for the Geologist team) | 45 days | Per day | 18,000 × 45 = 810,000 |
| 9 | Permits, regulatory filings, and Sudanese Geological Survey coordination fees | — | Lump sum | 95,000 |
| Subtotal |  |  |  | 5,429,000 SDG |
| VAT (10%) |  |  |  | 542,900 SDG |
| TOTAL AMOUNT DUE |  |  |  | 5,971,900 SDG |

Note: This Quotation Estimate is denominated in Sudanese Pounds (SDG). In the event of significant currency fluctuation exceeding 15% between the date of issue and the date of payment, the parties agree to renegotiate the total amount in good faith. All rates are inclusive of the Geologist's professional liability insurance as mandated by SCPEG for operations within Sudan Khartoum.

## 4. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all rates and availability of the Geologist are subject to reconfirmation in writing.

- Payment terms: 30% advance payment upon acceptance of this Quotation Estimate; 40% upon completion of all fieldwork in Sudan Khartoum; and 30% upon delivery and acceptance of the final geological report.

- The Geologist shall submit a weekly progress report to the client's designated point of contact every Friday, detailing field activities, borehole status, and any geological anomalies observed in the Sudan Khartoum study area.

- All geological data, core samples, and digital maps produced under this engagement shall become the property of the client upon full payment. The Geologist retains the right to publish anonymized findings in peer-reviewed journals with prior written consent from the Ministry.

- Force majeure: Delays caused by seasonal flooding of the Nile in Sudan Khartoum, civil unrest, or government-imposed restrictions shall extend the project timeline proportionally without penalty to either party.

- Disputes arising from this Quotation Estimate shall be resolved through amicable negotiation, failing which they shall be referred to the Sudanese Arbitration Centre in Khartoum in accordance with the Sudanese Arbitration Act (2005).

- The Geologist and all supporting field personnel shall comply with all environmental, health, and safety regulations applicable to geological fieldwork in Sudan Khartoum, including proper disposal of drilling fluids and core waste.

## 5. Acceptance and Authorization

By signing below, the client acknowledges and accepts this Quotation Estimate for the geological services described herein, to be performed by the designated Geologist and team within the Sudan Khartoum project area.

For Nile Basin Geological & Environmental Consultants
Dr. Fatima El-Siddig, Lead Geologist
SCPEG License No. SCPEG-2013-0891
Signature & Date: _________________________

For the Client (Ministry of Irrigation & Water Resources)
Eng. Ahmed El-Tahir, Director
Sudan Khartoum
Signature & Date: _________________________

This Quotation Estimate (Ref: QTE-2025-KRT-0347) is issued by Nile Basin Geological & Environmental Consultants for geological services in Sudan Khartoum. This document is confidential and intended solely for the named client. Unauthorized reproduction or distribution is prohibited under Sudanese commercial law.

Page 1 of 1 | Generated: 14 June 2025