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1. Purpose of This Quotation Estimate
This Quotation Estimate has been prepared specifically to outline the professional services, deliverables, and associated costs for a dedicated Graphic Designer engagement within the city of Argentina Córdoba. The purpose of this document is to provide the client with a transparent, itemized breakdown of all fees, timelines, and terms governing the design project. All pricing in this Quotation Estimate reflects current market rates applicable to the Graphic Designer profession in the Argentina Córdoba metropolitan area and surrounding provinces.
2. Scope of Work — Graphic Designer Services
The Graphic Designer engaged under this Quotation Estimate will deliver a comprehensive suite of visual communication services tailored to the client's brand identity and marketing objectives. The scope includes, but is not limited to, the following deliverables:
· Brand Identity Development: Creation of a complete logo suite, color palette, typography system, and brand guidelines document. The Graphic Designer will conduct initial research on the competitive landscape in Argentina Córdoba to ensure the visual identity is distinctive and locally resonant.
· Print Collateral Design: Design of business cards, letterheads, brochures, flyers, and posters optimized for local print vendors operating in the Argentina Córdoba region.
· Digital & Social Media Assets: Design of social media templates, email marketing headers, website banners, and digital advertisements. The Graphic Designer will ensure all digital assets are responsive and platform-optimized.
· Packaging & Label Design: If applicable, the Graphic Designer will develop packaging concepts and label artwork compliant with Argentine regulatory standards for product labeling.
· Revisions & Iterations: Three (3) rounds of revisions are included per deliverable. Additional revision cycles will be billed at the hourly rate specified in Section 4 of this Quotation Estimate.
3. Project Timeline
The Graphic Designer will adhere to the following schedule, commencing upon receipt of the signed Quotation Estimate and the initial 40% advance payment:
	Phase
	Description
	Duration
	Estimated Completion

	Phase 1
	Discovery, mood boards, and initial concepts
	10 business days
	July 5, 2025

	Phase 2
	Refinement, client feedback, and final design
	15 business days
	July 25, 2025

	Phase 3
	Production files, brand guidelines, and handoff
	7 business days
	August 8, 2025


4. Itemized Cost Breakdown
The following table constitutes the financial core of this Quotation Estimate. All amounts are expressed in Argentine Pesos (ARS) and reflect the prevailing rates for a senior Graphic Designer operating in Argentina Córdoba as of the date of issuance.
	Item
	Description
	Qty
	Unit Price (ARS)
	Subtotal (ARS)

	1
	Brand Identity Package (logo, palette, typography, guidelines)
	1
	185,000
	185,000

	2
	Print Collateral Design (business cards, letterhead, brochure, 2 flyers, 1 poster)
	1
	95,000
	95,000

	3
	Digital & Social Media Asset Pack (12 templates, 4 email headers, 3 web banners)
	1
	120,000
	120,000

	4
	Packaging / Label Design (up to 3 SKUs)
	1
	140,000
	140,000

	5
	Additional Revision Hour (beyond included 3 rounds)
	5
	8,500
	42,500

	6
	Project Management & Coordination (local, Córdoba-based)
	1
	35,000
	35,000

	Subtotal
	617,500

	IVA (21% — Argentine Value Added Tax)
	129,675

	TOTAL ESTIMATED COST
	747,175


* All prices are in Argentine Pesos (ARS). The Quotation Estimate is subject to adjustment if the Argentine peso experiences a devaluation exceeding 15% between the date of issuance and the date of final invoice. The Graphic Designer reserves the right to re-quote under such circumstances.
5. Payment Terms
· Advance Payment: 40% of the total amount (ARS 298,870) due upon signing this Quotation Estimate and before the Graphic Designer commences Phase 1 work.
· Progress Payment: 35% of the total amount (ARS 261,511) due upon client approval of final design concepts at the end of Phase 2.
· Final Payment: 25% of the total amount (ARS 186,794) due upon delivery of all production files and the brand guidelines document at the conclusion of Phase 3.
· Payment may be made via bank transfer (CBU/CVU) to the account of Studio Visión Gráfica, or by certified cheque payable in Argentina Córdoba. Late payments will incur a monthly interest rate equivalent to the BCRA (Banco Central de la República Argentina) reference rate.
6. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issuance. After this period, the Graphic Designer reserves the right to revise pricing due to market fluctuations in Argentina Córdoba.
· All intellectual property rights to the final approved designs transfer to the client upon full and final payment. The Graphic Designer retains the right to display completed work in their professional portfolio.
· The Graphic Designer is an independent contractor and not an employee of the client. This engagement is governed by the Civil and Commercial Code of the Argentine Nation and applicable provincial regulations of the Province of Córdoba.
· Any changes to the scope of work beyond what is described in this Quotation Estimate will require a written change order signed by both parties. The Graphic Designer will provide a supplemental cost estimate within five (5) business days of the change request.
· Confidentiality: The Graphic Designer agrees to treat all client information, trade secrets, and unreleased materials as strictly confidential throughout the engagement and for a period of two (2) years thereafter.
· Disputes arising from this Quotation Estimate shall be resolved through mediation in the city of Argentina Córdoba before submission to the competent commercial courts of Córdoba.
7. Acceptance and Authorization
By signing below, both parties acknowledge that they have read, understood, and agree to all terms set forth in this Quotation Estimate for Graphic Designer services in Argentina Córdoba. This document constitutes a binding agreement upon execution by both parties.
Studio Visión Gráfica (Graphic Designer)
Name: _________________________
DNI: _________________________
Date: _________________________
Client Representative
Name: _________________________
DNI / CUIT: _________________________
Date: _________________________
This Quotation Estimate (Ref. QE-CD-2025-0472) was prepared by Studio Visión Gráfica, a registered Graphic Designer studio based in Argentina Córdoba. For inquiries or amendments, please contact us at contacto@visiongrafica.com.ar or visit our office at Av. Vélez Sarsfield 1245, Piso 3, Córdoba, Argentina. This document is generated electronically and does not require a physical stamp to be valid under Argentine law.
