# Quotation Estimate - Graphic Designer - Germany Berlin

# KreativStudio Berlin GmbH

Mitte, Friedrichstraße 128

10117 Berlin, Germany

Tel: +49 30 5556 7890

Email: estimates@kreativstudio-berlin.de

USt-IdNr.: DE 312 456 789

## QUOTATION ESTIMATE

Ref: QTE-2025-BER-0472

Date: 14 June 2025

Valid until: 14 July 2025

### Client Information

#### Prepared For

Client Name: TechVision Solutions GmbH

Address: Prenzlauer Allee 45, 10405 Berlin, Germany

Contact: Dr. Anna Müller, Managing Director

Email: a.mueller@techvision-solutions.de

#### Project Reference

Project: Corporate Brand Identity & Digital Design Package

Location: Germany Berlin – Kreuzberg Studio

Service Category: Graphic Designer Services

Estimated Duration: 12 weeks

### Scope of Work – Graphic Designer Services

This Quotation Estimate is issued by KreativStudio Berlin GmbH to provide a comprehensive and transparent cost breakdown for the engagement of a senior Graphic Designer based in Germany Berlin. The following services have been scoped in accordance with the client's requirements for a full corporate rebranding and digital asset production programme. All work will be executed by a dedicated Graphic Designer operating from our studio in the Kreuzberg district of Berlin, ensuring local market awareness and cultural alignment with the Berlin creative scene.

The Graphic Designer will be responsible for developing a cohesive visual identity system, producing print-ready and digital-ready assets, and delivering all final files in industry-standard formats. The engagement reflects current market rates for freelance and agency-based Graphic Designer professionals in Germany Berlin, factoring in the cost of living, studio overheads, and the high demand for creative talent in the capital city.

### Itemised Cost Breakdown

| # | Description of Service | Quantity | Unit Rate (EUR) | Subtotal (EUR) | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Brand Identity Development – Logo design, colour palette, typography system, and brand guidelines document (delivered by senior Graphic Designer) | 1 package | 4,800.00 | 4,800.00 | Weeks 1–3 |
| 2 | Corporate Stationery Design – Business cards, letterheads, envelopes, and presentation folders (print-ready files, CMYK, 300 DPI) | 1 package | 1,650.00 | 1,650.00 | Weeks 3–5 |
| 3 | Digital Asset Production – Website hero banners, social media templates (LinkedIn, Instagram, X), email newsletter headers, and digital ad creatives | 24 assets | 185.00 | 4,440.00 | Weeks 5–8 |
| 4 | Marketing Collateral – Brochure (12-page A4), product one-pagers, and event banners for trade shows in Berlin and Munich | 1 package | 3,200.00 | 3,200.00 | Weeks 8–10 |
| 5 | Revisions and Iteration – Up to three (3) full revision rounds per deliverable, managed by the assigned Graphic Designer | 3 rounds | 450.00 | 1,350.00 | Ongoing |
| 6 | Final File Delivery and Handover – Source files (AI, PSD, INDD), PDF proofs, and a structured brand asset library organised for the client's CMS | 1 package | 750.00 | 750.00 | Week 12 |
| 7 | On-site Consultation in Berlin – Two (2) half-day meetings at the client's office in Prenzlauer Berg for creative direction alignment | 2 sessions | 380.00 | 760.00 | Weeks 2 & 7 |
| Subtotal (excl. VAT) |  |  |  | 16,950.00 |  |
| VAT (MwSt.) 19% – Germany Berlin |  |  |  | 3,220.50 |  |
| TOTAL AMOUNT DUE (incl. VAT) |  |  |  | 20,170.50 |  |

All prices are quoted in Euro (EUR). VAT of 19% (Mehrwertsteuer) is applied in accordance with German tax regulations applicable to services rendered in Berlin, Germany. This Quotation Estimate is valid for 30 calendar days from the date of issue.

### Terms and Conditions

- Validity: This Quotation Estimate remains valid for thirty (30) days from the date of issue. After this period, rates may be adjusted to reflect current market conditions for Graphic Designer services in Germany Berlin.

- Payment Terms: 40% deposit upon acceptance of this Quotation Estimate, 30% upon completion of the brand identity deliverables (Week 3), and the remaining 30% upon final file handover (Week 12). Payment is due within fourteen (14) days of invoice date via bank transfer (SEPA) to the account of KreativStudio Berlin GmbH, IBAN: DE89 3704 0044 0532 0130 00, BIC: COBADEFFXXX.

- Intellectual Property: Upon full and final payment, all rights to the final approved designs transfer to the client. The Graphic Designer retains the right to display completed work in their professional portfolio and case studies, subject to the client's written consent for confidential projects.

- Revisions: The quoted price includes three (3) revision rounds per deliverable. Additional revision cycles beyond the included rounds will be billed at a rate of EUR 95.00 per hour, consistent with standard Graphic Designer freelance rates in Berlin.

- Third-Party Costs: Costs for stock photography, premium font licences, or specialised print production services are not included in this Quotation Estimate and will be invoiced at cost with a 10% handling surcharge.

- Force Majeure: Neither party shall be liable for delays caused by circumstances beyond reasonable control, including but not limited to natural disasters, government-mandated closures, or significant disruptions to the Berlin metropolitan area.

- Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the Federal Republic of Germany. Any disputes shall be subject to the exclusive jurisdiction of the competent courts in Berlin, Germany.

- Confidentiality: The Graphic Designer and KreativStudio Berlin GmbH agree to maintain strict confidentiality regarding all client materials, trade secrets, and project details shared during the engagement in Germany Berlin.

### Acceptance and Authorisation

By signing below, the client acknowledges and accepts this Quotation Estimate for Graphic Designer services to be performed in Germany Berlin. This signature constitutes a binding agreement to the scope, pricing, and terms outlined in this document.

For KreativStudio Berlin GmbH

Name: Jonas Weber, Creative Director

Date: ____________________

For TechVision Solutions GmbH

Name: Dr. Anna Müller, Managing Director

Date: ____________________

KreativStudio Berlin GmbH · Friedrichstraße 128, 10117 Berlin, Germany · HRB 123456 B, Amtsgericht Charlottenburg

This Quotation Estimate was prepared exclusively for the named client and may not be reproduced or distributed without prior written consent.

Document Ref: QTE-2025-BER-0472 · Page 1 of 1