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QUOTATION ESTIMATE
Professional Industrial Engineer Services — Israel Tel Aviv
Ref: QTE-2025-TLV-0472
	Date of Issue:
	June 12, 2025
	Valid Until:
	July 12, 2025

	Prepared By:
	Merav Cohen, P.E. — Lead Industrial Engineer
	Client:
	Tel Aviv Manufacturing & Logistics Group Ltd.

	Client Address:
	45 HaYarkon Street, Tel Aviv-Yafo, Israel 6777501
	Contact:
	Mr. David Levi — Operations Director

	Project Location:
	Industrial Zone B, Tel Aviv, Israel
	Currency:
	Israeli New Shekel (ILS / NIS)


Scope of Work — Industrial Engineer Engagement in Israel Tel Aviv
This Quotation Estimate is issued by Merav Cohen, a certified Industrial Engineer registered with the Israeli Engineers Association, to provide comprehensive process optimization, production line redesign, and operational efficiency consulting services to the client's manufacturing and distribution facilities located in Israel Tel Aviv. The scope encompasses on-site assessments, data-driven workflow analysis, ergonomic evaluations, and the development of actionable improvement roadmaps tailored to the specific operational environment of the Tel Aviv industrial corridor.
As an Industrial Engineer operating within the Israel Tel Aviv market, the undersigned brings specialized expertise in lean manufacturing, supply chain integration, quality control systems, and human-factors engineering. All recommendations and deliverables contained within this Quotation Estimate are designed to comply with Israeli labor regulations, the Standards of Israel (SII) industrial codes, and the operational standards expected by the Tel Aviv municipal industrial authority.
Itemized Services & Pricing
	#
	Service Description
	Duration
	Rate (ILS)
	Subtotal (ILS)
	Notes

	1
	Initial site assessment and process mapping of the Tel Aviv production floor, including value-stream mapping and bottleneck identification
	3 days
	4,500
	13,500
	On-site, Israel Tel Aviv

	2
	Industrial Engineer-led time-and-motion study of assembly lines; development of standard work procedures and cycle-time benchmarks
	5 days
	4,800
	24,000
	Includes statistical analysis

	3
	Ergonomic risk assessment and workstation redesign proposal in compliance with Israeli occupational health and safety regulations
	4 days
	4,200
	16,800
	Per SII 5300 standard

	4
	Supply chain and inventory optimization modeling for the Tel Aviv distribution hub; warehouse layout redesign
	6 days
	5,000
	30,000
	Simulation-based analysis

	5
	Quality control system implementation plan; Six Sigma / Lean integration roadmap for the Israel Tel Aviv facility
	5 days
	5,200
	26,000
	Includes training materials

	6
	Staff training workshops (2 sessions) on lean principles, 5S methodology, and continuous improvement culture
	2 days
	6,000
	12,000
	Up to 30 participants

	7
	Final comprehensive report, implementation timeline, and 30-day post-deployment follow-up consultation
	3 days
	4,000
	12,000
	Delivered in Hebrew & English


	Subtotal
	134,300 ILS

	VAT (18% — Israel)
	24,174 ILS

	Travel & Local Transportation (Tel Aviv Metro Area)
	3,500 ILS

	Grand Total
	161,974 ILS


Terms & Conditions
Quotation Estimate Terms — Industrial Engineer Services, Israel Tel Aviv
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing for the Industrial Engineer services may be subject to revision based on market conditions in Israel Tel Aviv.
1. Payment terms: 40% advance payment upon acceptance of this Quotation Estimate; 40% upon completion of on-site fieldwork in Tel Aviv; 20% upon delivery of the final report and completion of the follow-up consultation period.
1. All work performed by the Industrial Engineer shall be conducted in accordance with the Israeli Labor Law, the Occupational Safety and Health Law, and applicable Tel Aviv municipal permits for industrial consulting activities.
1. The client agrees to provide the Industrial Engineer with full access to all relevant production data, floor plans, and operational records at the Israel Tel Aviv facility during the engagement period.
1. Intellectual property: All process maps, optimization models, and reports generated by the Industrial Engineer under this Quotation Estimate shall become the property of the client upon full payment.
1. Force majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to national security alerts, public health emergencies, or government-mandated closures affecting operations in Israel Tel Aviv.
1. Disputes arising from this Quotation Estimate shall be resolved under the jurisdiction of the Tel Aviv District Court, Israel, in accordance with Israeli civil law.
1. This Quotation Estimate does not constitute a binding contract until formally accepted in writing by both parties. The Industrial Engineer reserves the right to decline the engagement if site conditions in Tel Aviv present safety hazards not disclosed by the client.
Prepared & Issued By:
Merav Cohen, P.E.
Industrial Engineer
Israeli Engineers Association Reg. No. 48291
Signature & Date
Accepted By (Client):
David Levi
Operations Director
Tel Aviv Manufacturing & Logistics Group Ltd.
Signature & Date
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