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	Client Name
	Beijing Urban Development Authority

	Client Address
	12 Hepingli Street, Xicheng District, China Beijing

	Project Location
	Yongdingmen Cultural Heritage Restoration Zone, China Beijing

	Prepared By
	Wang Jianguo, Senior Mason & Project Estimator


1. Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Beijing Precision Mason & Construction Co., Ltd. to provide a comprehensive and itemized cost breakdown for all masonry works required at the Yongdingmen Cultural Heritage Restoration Zone in China Beijing. The scope of work encompasses traditional brick masonry, stone carving, mortar preparation, and structural reinforcement in accordance with the historical preservation standards mandated by the Beijing Municipal Cultural Relics Protection Bureau. This Quotation Estimate reflects current market pricing for all materials, labor, and equipment as of the date of issue and is subject to the terms and conditions outlined herein.
2. Scope of Mason Work
The Mason team assigned to this project will execute the following tasks at the designated site in China Beijing:
· Restoration and repointing of approximately 2,400 square meters of traditional grey brick masonry walls using locally sourced Huangshan grey bricks and lime-based mortar to match the original Ming Dynasty construction methodology.
· Carving and installation of 180 decorative stone lintels and sills from Hebei Province granite, including precise fitting, chiseling, and surface finishing by master Mason artisans.
· Construction of 35 new foundation piers using reinforced concrete and traditional rammed-earth techniques, each measuring 1.2m x 1.2m x 2.8m in depth.
· Application of traditional white lime plaster to 1,800 square meters of interior wall surfaces, including three coats of finish and decorative border patterns.
· Repair and reconstruction of 12 arched gateway openings using hand-cut voussoir bricks, requiring specialized Mason expertise in curved masonry geometry.
· Installation of drainage channels and weep holes throughout the perimeter wall to prevent water infiltration, in compliance with China Beijing municipal building codes.
3. Itemized Cost Breakdown
	Item No.
	Description
	Unit
	Quantity
	Unit Price (CNY)
	Total (CNY)

	01
	Traditional grey brick masonry repointing (lime mortar)
	m²
	2,400
	185.00
	444,000.00

	02
	Decorative granite stone lintels and sills (carved & installed)
	pcs
	180
	3,200.00
	576,000.00

	03
	Foundation piers (reinforced concrete + rammed earth)
	pcs
	35
	12,500.00
	437,500.00

	04
	White lime plaster, three-coat finish with decorative borders
	m²
	1,800
	95.00
	171,000.00

	05
	Arched gateway reconstruction (hand-cut voussoir masonry)
	pcs
	12
	48,000.00
	576,000.00

	06
	Drainage channels and weep hole installation
	m
	420
	210.00
	88,200.00

	07
	Master Mason artisan labor premium (heritage certification)
	man-days
	1,200
	650.00
	780,000.00

	08
	Material transport within China Beijing municipal area
	lot
	1
	45,000.00
	45,000.00

	09
	Scaffolding, formwork, and temporary works
	lot
	1
	128,000.00
	128,000.00

	10
	Quality inspection, heritage compliance testing, and documentation
	lot
	1
	65,000.00
	65,000.00

	SUBTOTAL
	3,319,700.00

	VAT (9% - Construction Services, China Beijing)
	298,773.00

	GRAND TOTAL (CNY)
	3,618,473.00


4. Project Timeline and Milestones
The total estimated duration for completion of all Mason works is 14 calendar weeks from the date of contract execution. The project will be executed in four phases: Phase 1 (Weeks 1–3) covers site preparation, material procurement, and foundation pier construction; Phase 2 (Weeks 4–8) addresses primary wall masonry and arched gateway reconstruction; Phase 3 (Weeks 9–12) involves stone carving installation and plastering; and Phase 4 (Weeks 13–14) is dedicated to drainage systems, final finishing, and heritage compliance inspection. All milestones are subject to weather conditions in China Beijing, particularly the summer monsoon season, which may necessitate schedule adjustments.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all pricing is subject to revision based on prevailing material and labor costs in the China Beijing construction market.
· Payment terms: 30% advance payment upon contract signing; 40% upon completion of Phase 2; 25% upon completion of Phase 3; 5% upon final acceptance and issuance of the heritage compliance certificate.
· All Mason work shall be performed in strict accordance with the GB/T 50203-2011 Code for Acceptance of Masonry Structure Engineering Quality and the Beijing Municipal Cultural Relics Protection Regulations.
· The Mason contractor shall provide a twelve-month defect liability period commencing from the date of final acceptance, during which all workmanship defects shall be rectified at no additional cost.
· Any variation in scope exceeding 10% of the total Quotation Estimate value shall require a written amendment signed by both parties prior to execution of additional work.
· All materials used in this project shall be sourced from approved suppliers registered with the China Beijing Construction Materials Quality Supervision Bureau.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration at the Beijing Arbitration Commission in accordance with its rules of procedure.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and confirms that the scope, pricing, and terms described herein are acceptable for the Mason works to be carried out at the specified location in China Beijing. This document does not constitute a binding contract until a formal construction contract is executed by both parties.
For and on behalf of Beijing Precision Mason & Construction Co., Ltd.

Name: Wang Jianguo
Title: Senior Mason & Project Director
Date: ______________________
Signature: ______________________
Company Seal:
For and on behalf of Beijing Urban Development Authority

Name: ______________________
Title: ______________________
Date: ______________________
Signature: ______________________
Official Seal:
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