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1. Introduction and Scope of Work
This Quotation Estimate is issued by Alexandria Mason & Construction Co., a licensed and registered masonry firm operating within the governorate of Egypt Alexandria. We are pleased to present this detailed estimate for the comprehensive masonry works required at the client's residential property located in the Smouha District. Our team of experienced Mason professionals has conducted a thorough site assessment and prepared this document to ensure full transparency regarding all costs, materials, labor, and timelines associated with the project.
The scope of work encompasses the construction of a two-storey masonry extension, including foundation reinforcement, load-bearing wall construction, interior partition walls, exterior plastering, and decorative stone finishing on the ground-floor facade. All masonry work will be executed in strict accordance with Egyptian Building Code standards and the municipal regulations governing construction activities in Egypt Alexandria.
2. Itemized Cost Breakdown
	Item No.
	Description of Mason Work
	Unit
	Quantity
	Unit Price (EGP)
	Total (EGP)

	01
	Foundation masonry reinforcement using C25 concrete and reinforced steel mesh (Mason-supervised)
	m³
	18.5
	4,200
	77,700

	02
	Load-bearing wall construction – solid clay bricks, 20 cm thickness, with cement mortar (1:5 ratio)
	m²
	142
	680
	96,560

	03
	Interior partition walls – hollow concrete blocks, 10 cm thickness
	m²
	96
	420
	40,320

	04
	Exterior plastering – two-coat cement render with waterproofing additive
	m²
	210
	350
	73,500

	05
	Decorative natural stone cladding – ground-floor facade (local Alexandria limestone)
	m²
	64
	1,850
	118,400

	06
	Lintels, sills, and structural masonry elements (precast concrete)
	pcs
	22
	1,200
	26,400

	07
	Skilled Mason labor, site supervision, and project management (full duration)
	lump sum
	1
	85,000
	85,000

	08
	Scaffolding, formwork, and temporary masonry support structures
	lump sum
	1
	22,000
	22,000

	09
	Waste removal, site cleanup, and compliance with Egypt Alexandria municipal regulations
	lump sum
	1
	12,500
	12,500

	SUBTOTAL
	552,380

	VAT (14% – Egyptian Tax Authority)
	77,333

	GRAND TOTAL (EGP)
	629,713


3. Project Timeline
The estimated duration for completion of all masonry works outlined in this Quotation Estimate is eleven (11) working weeks, commencing from the date of contract signing and receipt of the initial payment. The timeline has been calibrated to account for seasonal weather conditions typical of Egypt Alexandria, including the higher humidity levels during the summer months, which may affect mortar curing times. Our lead Mason and site engineer will provide weekly progress reports to the client throughout the project duration.
4. Payment Schedule
Payment shall be structured as follows: 30% advance payment upon contract execution; 40% upon completion of structural masonry (walls and foundation); 20% upon completion of plastering and stone cladding; and the remaining 10% upon final inspection, sign-off, and handover of the completed works. All payments are to be made in Egyptian Pounds (EGP) via bank transfer to the account designated in the contract annex.
5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Prices are subject to revision upon expiry due to potential fluctuations in material costs within the Egypt Alexandria market.
1. All masonry work is guaranteed for a period of twenty-four (24) months from the date of final acceptance, covering structural integrity, mortar adhesion, and plastering defects.
1. The client is responsible for obtaining all necessary building permits and approvals from the Alexandria Governorate Municipal Authority prior to the commencement of works.
1. Any additional or variation works beyond the scope defined in this estimate shall be subject to a separate written amendment and additional Quotation Estimate approved by both parties.
1. Our Mason team shall comply with all occupational health and safety regulations as mandated by the Egyptian Ministry of Manpower and Social Solidarity.
1. Disputes arising from this agreement shall be resolved through amicable negotiation, failing which they shall be referred to the competent courts in Egypt Alexandria.
1. Force majeure events, including but not limited to extreme weather, government-mandated shutdowns, or supply chain disruptions, shall extend the project timeline proportionally without penalty to either party.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the masonry services to be performed in Egypt Alexandria. This document, once countersigned, constitutes a binding preliminary agreement pending the execution of the full construction contract.
For Alexandria Mason & Construction Co.
Authorized Representative
Name: Eng. Khaled Mansour
Date: _______________
Client Acknowledgment
Name: Mr. Ahmed El-Sayed Hassan
Signature: _______________
Date: _______________
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