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Quotation Estimate
	Quotation No.:
	QTE-2025-ALM-0047
	Date Issued:
	15 June 2025

	Valid Until:
	15 July 2025
	Currency:
	Kazakhstani Tenge (KZT)

	Client Name:
	Tengri Residential Development Group
	Client Address:
	88 Dostyk Avenue, Almaty, Kazakhstan

	Project Location:
	Makhtaarata District, Almaty, Kazakhstan
	Project Type:
	Residential Masonry Construction


1. Introduction and Scope of Work
This Quotation Estimate is prepared by Almaty Masonry & Construction Services LLP in response to the formal request submitted by Tengri Residential Development Group for comprehensive masonry works at their residential development site in the Makhtaarata District of Kazakhstan Almaty. This document outlines the full scope of Mason services, material costs, labor charges, and associated project terms that will govern the execution of the masonry construction phase.
The Mason works encompassed in this Quotation Estimate include the laying of load-bearing and non-load-bearing brick walls, construction of concrete block partitions, installation of lintels and ring beams, application of mortar joints in accordance with Kazakhstani building codes (SNiP standards applicable in Kazakhstan Almaty), and the preparation of masonry surfaces for subsequent plastering and finishing. All Mason work will be performed by certified masonry professionals who are fully familiar with the seismic construction requirements mandated for the Almaty region, given its classification as a high-seismicity zone.
2. Itemized Cost Breakdown
	Item No.
	Description of Mason Work
	Quantity
	Unit
	Unit Rate (KZT)
	Total (KZT)

	1
	Laying of solid clay brick walls (load-bearing), 380mm thickness, including mortar preparation and joint finishing
	1,250
	m³
	185,000
	231,250,000

	2
	Construction of aerated concrete block partitions (200mm), including leveling and mortar application
	860
	m³
	128,000
	110,080,000

	3
	Installation of precast concrete lintels and ring beams (seismic reinforcement per Almaty code)
	340
	linear m
	42,500
	14,450,000

	4
	Construction of foundation walls using heavy-duty concrete blocks (400mm), including waterproofing mortar layer
	420
	m³
	210,000
	88,200,000

	5
	Application of cement-sand mortar for surface preparation (two coats, 15mm each) on all masonry surfaces
	5,600
	m²
	8,500
	47,600,000

	6
	Supply and installation of masonry reinforcement mesh (seismic zone requirement, Almaty)
	3,200
	m²
	6,200
	19,840,000

	7
	Site supervision by senior Mason engineer and daily quality inspection reporting
	90
	days
	185,000
	16,650,000

	8
	Waste removal, site cleanup, and material handling within the Almaty project boundary
	1
	lump sum
	4,500,000
	4,500,000

	Subtotal
	522,570,000

	VAT (12% per Kazakhstan tax code)
	62,708,400

	TOTAL ESTIMATED COST
	585,278,400 KZT


3. Project Timeline
The Mason works described in this Quotation Estimate are scheduled to commence on 1 August 2025 and are projected for completion by 30 October 2025, subject to weather conditions typical of Kazakhstan Almaty during the late summer and early autumn period. The total duration of the masonry phase is estimated at 90 working days. Any delays caused by extreme weather events, including early frost or heavy precipitation common in the Almaty region, will be documented and communicated to the client within 24 hours.
4. Terms and Conditions
· This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After the expiry date, all pricing and material costs are subject to revision based on current market conditions in Kazakhstan Almaty.
· Payment shall be made in tranches: 30% upon contract signing, 40% upon completion of 60% of the Mason works, and 30% upon final acceptance and sign-off by the client's site engineer.
· All masonry work will comply with the Kazakhstani State Construction Standards (SNiP) and the specific seismic design requirements applicable to Almaty (seismic intensity zone 9).
· The Mason team will consist of a minimum of twelve (12) skilled masons, two (2) foremen, and one (1) senior structural engineer for supervision. All personnel will hold valid work permits for employment in Kazakhstan.
· Materials including bricks, concrete blocks, mortar, and reinforcement will be sourced from approved suppliers within the Almaty metropolitan area to minimize logistics costs and ensure timely delivery to the project site.
· A warranty period of twenty-four (24) months shall apply to all Mason works from the date of final acceptance. This warranty covers structural integrity, joint quality, and compliance with the specifications outlined in this Quotation Estimate.
· Any changes to the scope of work must be agreed upon in writing via a formal variation order. The Quotation Estimate prices shall not be adjusted for variations unless explicitly stated in the variation document.
· Disputes arising from this agreement shall be resolved through arbitration in Almaty, Kazakhstan, in accordance with the rules of the Almaty International Arbitration Centre.
5. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate represents a fair and accurate assessment of the Mason services to be rendered at the specified project location in Kazakhstan Almaty. This document, once countersigned, shall serve as the basis for the formal construction contract to be executed within fourteen (14) days of acceptance.
For Almaty Masonry & Construction Services LLP:
Name: Dauren Bekzhanov
Title: Chief Mason Engineer / Director
Signature: _________________________
Date: _________________________
For Tengri Residential Development Group:
Name: _________________________
Title: Project Director
Signature: _________________________
Date: _________________________
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