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QUOTATION ESTIMATE
Professional Mechanical Engineer Services — Belgium Brussels
	Quotation Estimate No.
	QTE-2025-BRX-0487

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Prepared For
	Client Name / Company Name, Address, Brussels, Belgium

	Project Reference
	ME-BRX-2025-Industrial Retrofit Programme

	Prepared By
	Senior Mechanical Engineer, Brussels Mechanical Engineering Solutions BV


1. Scope of Work & Description of Services
This Quotation Estimate is issued by Brussels Mechanical Engineering Solutions BV to provide a comprehensive and transparent cost breakdown for the engagement of a qualified Mechanical Engineer to deliver design, analysis, and consultancy services within the Belgium Brussels metropolitan area. The Mechanical Engineer assigned to this project holds a recognised engineering degree, is registered with the Belgian Engineering Council (Bureau du Conseil des Ingénieurs), and possesses a minimum of twelve years of professional experience in industrial mechanical systems, HVAC infrastructure, and process equipment design.
· Site Assessment & Feasibility Study: The Mechanical Engineer shall conduct a full on-site inspection of the client's industrial premises located in Belgium Brussels, evaluating existing mechanical installations, structural constraints, and regulatory compliance under Belgian and EU directives.
· Conceptual & Detailed Design: Production of complete mechanical design packages including P&ID drawings, 3D CAD models (SolidWorks / AutoCAD Mechanical), material specifications, and load calculations in accordance with Eurocode standards applicable in Belgium.
· Thermal & Structural Analysis: Finite Element Analysis (FEA) and Computational Fluid Dynamics (CFD) simulations to validate design integrity for pressure vessels, piping networks, and heat exchangers operating within the Belgium Brussels facility.
· Regulatory Compliance & Permitting: Preparation and submission of all necessary technical documentation to the Brussels-Capital Region (Région de Bruxelles-Capitale) authorities, including conformity assessments under the Belgian Code of Economic Law and relevant ATEX directives.
· Procurement Support & Vendor Coordination: The Mechanical Engineer will assist in the preparation of technical specifications for tendering, review of vendor submittals, and coordination with local Belgium Brussels subcontractors and suppliers.
· Commissioning & Handover: On-site supervision of mechanical installation, performance testing, and final commissioning. Delivery of as-built documentation, operation and maintenance manuals, and a formal handover report to the client.
2. Itemised Cost Breakdown
	Ref
	Description of Service
	Duration
	Rate (EUR)
	Amount (EUR)

	01
	Site assessment, feasibility study, and initial report (Mechanical Engineer on-site, Belgium Brussels)
	3 days
	€ 950 / day
	€ 2,850.00

	02
	Conceptual design, 3D modelling, and P&ID development
	15 days
	€ 875 / day
	€ 13,125.00

	03
	Detailed engineering, FEA/CFD analysis, and design validation
	20 days
	€ 875 / day
	€ 17,500.00

	04
	Regulatory compliance documentation and Brussels-Capital Region permit submission
	5 days
	€ 900 / day
	€ 4,500.00

	05
	Procurement support, vendor coordination, and technical tender review
	8 days
	€ 825 / day
	€ 6,600.00

	06
	Commissioning supervision, performance testing, and handover documentation
	10 days
	€ 950 / day
	€ 9,500.00

	07
	Travel, accommodation, and local transport within Belgium Brussels (estimated)
	—
	Flat fee
	€ 1,200.00

	08
	Software licences, simulation hours, and third-party testing fees
	—
	Flat fee
	€ 3,400.00

	Subtotal (excl. VAT)
	€ 58,675.00

	VAT @ 21% (Belgian standard rate)
	€ 12,321.75

	TOTAL AMOUNT DUE (incl. VAT)
	€ 70,996.75


All rates are quoted in Euros (EUR). VAT is applied at the Belgian standard rate of 21%. If the client is a VAT-registered entity within the European Union, the reverse-charge mechanism may apply, in which case no Belgian VAT will be charged on this Quotation Estimate.
3. Payment Terms
3.1 A mobilisation payment of 25% of the total Quotation Estimate value (€ 17,749.19 incl. VAT) is due within 10 business days of the client's written acceptance of this document.
3.2 Progress payments of 25% shall be invoiced at the completion of the Detailed Engineering phase (Item 03) and again at the completion of Commissioning (Item 06).
3.3 The final balance of 25% is due within 15 business days of the formal handover and acceptance of all deliverables by the client.
3.4 All invoices are payable by bank transfer to the IBAN specified in the header. Late payments shall attract interest at the rate prescribed by the Belgian Law of 2 August 2002 on late payment in commercial transactions.
4. Terms & Conditions
4.1 This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, rates and availability of the Mechanical Engineer are subject to reconfirmation.
4.2 The scope of work described herein is based on the information available at the time of this Quotation Estimate. Any significant change in scope, site conditions, or regulatory requirements in Belgium Brussels may result in a revised estimate, to be agreed in writing by both parties.
4.3 The Mechanical Engineer shall comply with all applicable Belgian labour laws, health and safety regulations, and professional codes of conduct. Professional indemnity insurance of a minimum € 2,000,000 per claim is maintained throughout the engagement.
4.4 All intellectual property rights in design documents, CAD files, and reports produced under this Quotation Estimate shall transfer to the client upon full and final payment.
4.5 Disputes arising from this Quotation Estimate shall be governed by the laws of Belgium and shall be subject to the exclusive jurisdiction of the courts of Brussels.
4.6 This Quotation Estimate does not constitute a binding contract until a formal Service Agreement is executed by both parties.
5. Acceptance & Signatures
By signing below, the client acknowledges receipt of this Quotation Estimate for Mechanical Engineer services in Belgium Brussels and agrees to the terms, conditions, and pricing set out above. This signature constitutes a request to proceed and does not, in itself, form a binding contract until the formal Service Agreement is countersigned.
For and on behalf of the Client:
Name: ______________________________
Title: ______________________________
Date: ______________________________
Signature: ______________________________
For and on behalf of Brussels Mechanical Engineering Solutions BV:
Name: ______________________________
Title: Lead Mechanical Engineer
Date: ______________________________
Signature: ______________________________
Important Notice: This Quotation Estimate has been prepared specifically for the client named above and for the project referenced herein. It may not be reproduced, distributed, or relied upon by any third party without the prior written consent of Brussels Mechanical Engineering Solutions BV. All engineering services described are to be performed in accordance with the professional standards of the Belgian Engineering Council and applicable EU directives. For queries regarding this Quotation Estimate, please contact our Brussels office at +32 2 555 0142 or quotes@bmengineers.be.
