Quotation Estimate - Mechanical Engineer Services - Egypt Cairo
Quotation Estimate
Nile Delta Mechanical Engineering Consultants
127 Tahrir Square, Downtown District, Egypt Cairo
Tel: +20 2 2574 8890 | Email: info@niledelta-mec.com
Commercial Registration No. 458210 | Tax ID: 522-884-103
	Quotation Estimate No.
	QTE-2025-CAIRO-0472
	Date of Issue
	14 June 2025

	Validity Period
	30 Calendar Days from Date of Issue
	Currency
	Egyptian Pound (EGP)

	Prepared For
	Al-Nile Industrial Development Co., Ltd. – 45 El-Mokattam Road, Egypt Cairo
	Project Reference
	PRJ-ND-2025-118

	Prepared By
	Eng. Mahmoud El-Sayed, Senior Mechanical Engineer
	Department
	Mechanical Engineering & Plant Design


1. Subject and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Nile Delta Mechanical Engineering Consultants to Al-Nile Industrial Development Co., Ltd. for the provision of comprehensive Mechanical Engineer services related to the design, review, and commissioning of a new HVAC and process piping system for the client's manufacturing facility located in the 10th of Ramadan Industrial Zone, Egypt Cairo. This document serves as a binding financial and technical proposal and shall remain valid for the period stated above unless otherwise extended in writing by both parties.
2. Scope of Mechanical Engineer Services
The Mechanical Engineer team assigned to this project in Egypt Cairo shall deliver the following services in full compliance with Egyptian Building Code (EBC 301), ASME standards, and local municipal regulations applicable to Egypt Cairo:
· Site Survey and Assessment: A dedicated Mechanical Engineer shall conduct a full on-site survey of the existing plant infrastructure in Egypt Cairo, documenting current piping layouts, equipment conditions, load calculations, and utility connections. This phase includes thermal imaging and airflow mapping across all production floors.
· Conceptual and Detailed Design: The lead
· Mechanical Engineer shall produce complete AutoCAD and Revit MEP drawings for the new HVAC system, including ductwork sizing, chiller selection, pump specifications, and process piping isometrics. All designs shall be tailored to the climatic conditions of Egypt Cairo, accounting for peak summer temperatures exceeding 42°C.
· Equipment Procurement Support: The Mechanical Engineer shall prepare detailed technical data sheets, issue Requests for Quotation (RFQs) to approved vendors, and evaluate supplier proposals to ensure cost-effective procurement of chillers, air handling units, centrifugal pumps, and associated instrumentation.
· Construction Supervision and QA/QC: A resident Mechanical Engineer shall be stationed at the Egypt Cairo project site throughout the installation phase to supervise contractor work, verify weld quality, perform pressure testing of piping circuits, and ensure adherence to the approved design documents.
· Commissioning and Handover: The Mechanical Engineer shall oversee the start-up sequence, perform performance testing against design parameters, prepare as-built documentation, and deliver a comprehensive operations and maintenance manual to the client's facility management team in Egypt Cairo.
· Regulatory Compliance and Permitting: The Mechanical Engineer shall coordinate with the Cairo Governorate Engineering Department and the Egyptian Environmental Affairs Agency to secure all necessary permits, environmental impact assessments, and final occupancy approvals specific to Egypt Cairo jurisdictions.
3. Itemized Cost Breakdown
	No.
	Description of Service
	Duration
	Unit Rate (EGP)
	Total Amount (EGP)

	1
	Site survey, assessment, and thermal/airflow mapping by Mechanical Engineer team
	10 working days
	45,000 / day
	450,000

	2
	Conceptual and detailed mechanical design (HVAC + process piping) – Revit & AutoCAD deliverables
	45 working days
	38,000 / day
	1,710,000

	3
	Equipment procurement support, vendor evaluation, and technical bid analysis
	20 working days
	32,000 / day
	640,000

	4
	Resident Mechanical Engineer construction supervision and QA/QC at Egypt Cairo site
	90 working days
	52,000 / day
	4,680,000

	5
	Commissioning, performance testing, and handover documentation
	15 working days
	48,000 / day
	720,000

	6
	Regulatory compliance, permit coordination with Cairo Governorate, and environmental clearance
	25 working days
	28,000 / day
	700,000

	7
	Travel, accommodation, and local transportation within Egypt Cairo for the Mechanical Engineer team
	205 working days
	3,500 / day
	717,500

	8
	Software licensing, printing, and reproduction of engineering drawings and reports
	Lump Sum
	—
	185,000

	Subtotal (EGP)
	10,802,500

	VAT 14% (Egyptian Tax Authority)
	1,512,350

	GRAND TOTAL (EGP)
	12,314,850


4. Payment Terms and Schedule
4.1 – A mobilization advance of 20% of the total Quotation Estimate value shall be payable within 10 business days of contract signature and issuance of a valid bank guarantee from a licensed Egyptian bank.
4.2 – Monthly progress payments of up to 70% of the value of work certified by the client's project manager shall be invoiced at the end of each calendar month. Invoices must reference this Quotation Estimate number (QTE-2025-CAIRO-0472).
4.3 – The remaining 10% shall be released upon successful commissioning, final acceptance by the client, and delivery of all as-built documentation and the O&M manual at the Egypt Cairo facility.
4.4 – All payments shall be made in Egyptian Pounds (EGP) via bank transfer to the account of Nile Delta Mechanical Engineering Consultants, National Bank of Egypt, Cairo Main Branch, IBAN: EG38000200015678901234567890.
5. Terms and Conditions
5.1 – This Quotation Estimate is valid for 30 calendar days from the date of issue. Any request for extension beyond this period must be submitted in writing and is subject to re-evaluation of material and labor costs in Egypt Cairo.
5.2 – The Mechanical Engineer services described herein are exclusive to the scope outlined in Section 2. Any additional or revised scope shall be subject to a supplementary Quotation Estimate and a formal change order signed by both parties.
5.3 – The client shall provide safe access to the Egypt Cairo project site, all existing as-built drawings, utility connection data, and any third-party approvals required before the Mechanical Engineer team commences work.
5.4 – All intellectual property, design documents, and engineering calculations produced under this engagement shall become the property of the client upon full payment. The Mechanical Engineer firm retains the right to reference the project in its portfolio with prior written consent.
5.5 – Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in accordance with the rules of the Egyptian Arbitration Center, with the seat of arbitration in Egypt Cairo.
5.6 – This Quotation Estimate does not constitute a contract until a formal Service Agreement is executed by authorized representatives of both parties.
6. Acceptance and Authorization
For and on behalf of
Nile Delta Mechanical Engineering Consultants
Eng. Mahmoud El-Sayed
Senior Mechanical Engineer / Project Director
Signature & Company Stamp
Accepted and Approved by
Al-Nile Industrial Development Co., Ltd.
Authorized Signatory
Name: _________________________
Title: _________________________
Signature & Company Stamp
Important Note: This Quotation Estimate has been prepared specifically for the project located in Egypt Cairo and reflects current market rates for Mechanical Engineer professional services as of June 2025. Rates are subject to adjustment in the event of significant changes in the Egyptian Pound exchange rate, government tax policy, or material cost indices. Please direct all inquiries regarding this Quotation Estimate to Eng. Mahmoud El-Sayed at +20 2 2574 8890 or info@niledelta-mec.com.
