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Quotation Reference
Ref: QTE-2025-ME-0487
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Valid Until: 14 September 2025
Currency: EUR (€)
Client Information
Company: Société Industrielle du Grand Paris SAS
Address: 45 Rue de la Convention, 75015 Paris, France
Contact: M. Laurent Dubois, Director of Operations
Email: l.dubois@societe-industrielle-gp.fr
Dear Mr. Dubois,
Thank you for your request dated 2 June 2025 regarding the provision of specialised mechanical engineering services for your new manufacturing facility located in the 15th arrondissement of France Paris. Following our initial site assessment and technical consultation, we are pleased to present this formal Quotation Estimate outlining the full scope of work, associated costs, and delivery timelines for the engagement of our senior Mechanical Engineer team. This document constitutes a binding commercial proposal valid for the period stated above and is prepared in accordance with French commercial law (Code de commerce, Articles L441-1 et seq.).
1. Scope of Work – Mechanical Engineer Services in France Paris
This Quotation Estimate covers the comprehensive provision of a dedicated Mechanical Engineer and supporting technical staff to deliver the following services at your premises in France Paris:
· Complete mechanical design and CAD modelling (SolidWorks / CATIA V6) of three (3) automated assembly lines, including kinematic analysis, tolerance stack-up studies, and finite element analysis (FEA) for structural integrity verification.
· Thermal and fluid-dynamic simulation of the central cooling and lubrication systems, ensuring compliance with French industrial safety regulations (Code du travail, Livre IV) and applicable EU directives (2006/42/EC – Machinery Directive).
· Selection, specification, and procurement oversight of all mechanical components, actuators, bearings, and transmission systems, with sourcing prioritised from certified suppliers operating within France Paris and the Île-de-France region.
· On-site installation supervision, commissioning, and performance validation of all mechanical subsystems, including vibration analysis, alignment checks, and load testing under operational conditions.
· Preparation of full technical documentation packages: as-built drawings, maintenance manuals, spare parts lists, and operator training materials in both French and English.
· Post-commissioning support: a twelve (12) month warranty period covering defect rectification, with a dedicated Mechanical Engineer on call for critical interventions within 24 hours at any location within France Paris.
2. Detailed Cost Breakdown
	Ref
	Description of Service
	Duration
	Rate (€/hr)
	Hours
	Amount (€)

	01
	Mechanical Engineer – Senior (Design & FEA)
	12 weeks
	95.00
	480
	45,600.00

	02
	Mechanical Engineer – Mid-level (Thermal/Fluid Simulation)
	8 weeks
	72.00
	320
	23,040.00

	03
	CAD Technician (Drawing & Documentation)
	10 weeks
	55.00
	400
	22,000.00

	04
	On-site Installation Supervision & Commissioning
	6 weeks
	85.00
	240
	20,400.00

	05
	Procurement Management & Supplier Coordination (France Paris region)
	8 weeks
	65.00
	160
	10,400.00

	06
	Technical Documentation & Training Materials (FR/EN)
	4 weeks
	60.00
	120
	7,200.00

	07
	Post-Commissioning Warranty Support (12 months, on-call)
	12 months
	—
	—
	12,000.00

	08
	Software Licences (SolidWorks, ANSYS, CATIA – project duration)
	26 weeks
	—
	—
	8,500.00

	09
	Travel, Accommodation & Subsistence (within France Paris metro area)
	26 weeks
	—
	—
	4,800.00


Subtotal: € 153,940.00
TVA (20% – French Value Added Tax): € 30,788.00
Total Amount Due: € 184,728.00
3. Payment Schedule
This Quotation Estimate is structured with the following milestone-based payment schedule, all amounts inclusive of applicable French VAT (TVA) at the standard rate of 20%:
· Milestone 1 – 30% upon contract signature: € 55,418.40 (due within 15 business days of acceptance)
· Milestone 2 – 25% upon completion of design & simulation phase: € 46,182.00
· Milestone 3 – 25% upon completion of installation & commissioning: € 46,182.00
· Milestone 4 – 20% upon final acceptance & handover of documentation: € 36,945.60
4. Terms & Conditions
4.1 Validity: This Quotation Estimate shall remain valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, all rates and availability commitments are subject to reconfirmation in writing.
4.2 Intellectual Property: All designs, models, simulations, and documentation produced under this engagement shall become the exclusive property of Société Industrielle du Grand Paris SAS upon full payment. Atelier Mécanique Précision SARL retains the right to reference the project in its portfolio with prior written consent.
4.3 Confidentiality: Both parties agree to maintain strict confidentiality regarding all technical data, commercial terms, and proprietary information exchanged in connection with this Quotation Estimate, in accordance with French data protection law (Loi Informatique et Libertés) and the EU General Data Protection Regulation (GDPR).
4.4 Liability & Insurance: Our Mechanical Engineer team operates under a professional liability insurance policy (RC Professionnelle) with a coverage limit of € 5,000,000 per claim, held with AXA France. A certificate of insurance shall be provided upon request.
4.5 Force Majeure: Neither party shall be liable for delays or failures in performance resulting from events beyond reasonable control, including but not limited to natural disasters, industrial strikes, or government-mandated closures affecting operations in France Paris.
4.6 Dispute Resolution: Any dispute arising from this Quotation Estimate or the resulting contract shall be submitted to the competent commercial court of Paris (Tribunal de Commerce de Paris) in accordance with French procedural law.
4.7 Governing Law: This Quotation Estimate and any resulting agreement shall be governed by and construed in accordance with the laws of the French Republic.
5. Acceptance
To accept this Quotation Estimate, please sign and return a copy of this document within the validity period stated above, or issue a formal purchase order referencing Quotation No. QTE-2025-ME-0487. Upon receipt of your signed acceptance, we will issue a formal service contract (Contrat de Prestation de Services) within five (5) business days.
For and on behalf of
ATELIER MÉCANIQUE PRÉCISION SARL
Signature & Company Seal
M. Philippe Moreau, Gérant
Date: ____________________
Accepted by
SOCIÉTÉ INDUSTRIELLE DU GRAND PARIS SAS
Signature & Company Seal
M. Laurent Dubois, Directeur des Opérations
Date: ____________________
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