Quotation Estimate - Mechanical Engineer Services - Mexico Mexico City
QUOTATION ESTIMATE
Professional Mechanical Engineer Services — Mexico, Mexico City
Quotation No.: QTE-MX-2025-04782
Date Issued: June 12, 2025
Valid Until: July 12, 2025
Prepared By: Ing. Ricardo A. Salazar, P.E.
Firm: Salazar & Asociados Ingeniería Mecnica, S.A. de C.V.
Location: Av. P. de los Insurgentes Sur 1502, Col. Insurgentes Mixcoac, C.P. 03920, Mexico City, Mexico
1. Client Information
	Field
	Details

	Client Name
	Grupo Industrial del Valle, S.A. de C.V.

	Project Address
	Blvd. Manuel Avila Camacho 500, Col. Lomas Altas, C.P. 11950, Mexico City, Mexico

	Point of Contact
	Lic. Mariana Torres, Director of Operations

	RFI Reference
	RFI-GIV-2025-031 (Received May 28, 2025)


2. Scope of Work — Mechanical Engineer Services
This Quotation Estimate is issued by Salazar & Asociados Ingeniería Mecnica, S.A. de C.V., a licensed Mechanical Engineer consultancy operating in Mexico, Mexico City, in direct response to the client's Request for Information. The scope of work encompasses the full spectrum of Mechanical Engineer professional services required for the design, analysis, and commissioning of the industrial HVAC and process piping systems at the client's manufacturing facility located in the Lomas Altas district of Mexico City, Mexico.
The Mechanical Engineer team assigned to this project will deliver the following deliverables in strict compliance with the Mexican Official Standards (NOM-001-SEDE, NOM-020-ENER, and applicable CFE regulations) as well as ASME, ASHRAE, and ISO 9001:2015 quality management requirements. All engineering calculations, system designs, and technical documentation produced under this Quotation Estimate will be executed by a registered Mechanical Engineer holding a valid license issued by the Colegio de Ingenieros Mecnicos de Mxico, A.C., and will be stamped and signed in accordance with Mexican federal and local (CDMX) regulatory requirements.
3. Itemized Cost Breakdown
	Item No.
	Description of Mechanical Engineer Service
	Unit
	Qty
	Unit Price (MXN)
	Subtotal (MXN)

	01
	Site survey and as-built documentation review at Mexico City facility (Mechanical Engineer on-site assessment, 3 days)
	Day
	3
	12,500.00
	37,500.00

	02
	Thermal load calculation and HVAC system design (Mechanical Engineer engineering analysis, CFD modeling, and equipment sizing)
	Lot
	1
	185,000.00
	185,000.00

	03
	Process piping isometric drawings and P&ID development (Mechanical Engineer drafting, 450+ sheets)
	Lot
	1
	220,000.00
	220,000.00

	04
	Structural support design for mechanical equipment and piping racks (Mechanical Engineer structural analysis per ASME B31.3 and NOM-008-SCFI)
	Lot
	1
	145,000.00
	145,000.00

	05
	Commissioning, start-up supervision, and performance testing (Mechanical Engineer on-site supervision, 10 days)
	Day
	10
	14,000.00
	140,000.00

	06
	Regulatory permitting support before CDMX authorities and CFE coordination (Mechanical Engineer liaison services)
	Lot
	1
	65,000.00
	65,000.00

	07
	Operation & Maintenance manual preparation and operator training (Mechanical Engineer technical documentation, 2 sessions)
	Lot
	1
	48,000.00
	48,000.00

	SUBTOTAL (MXN)
	840,500.00

	IVA (16% — Mexican Value Added Tax)
	134,480.00

	TOTAL AMOUNT (MXN, IVA included)
	974,980.00


4. Payment Terms
Payment for the services outlined in this Quotation Estimate shall be made in three (3) installments: 40% upon contract execution and commencement of the Mechanical Engineer design phase; 40% upon delivery and client approval of all engineering drawings and calculations; and 20% upon successful completion of commissioning and handover in Mexico City. All payments shall be made in Mexican Pesos (MXN) via bank transfer to the account designated by Salazar & Asociados Ingeniería Mecnica, S.A. de C.V. A 1.5% monthly interest rate will apply to any overdue balance.
5. Project Timeline
The Mechanical Engineer team estimates a total project duration of fourteen (14) calendar weeks from the date of contract signing. The site survey and as-built review will be completed within the first two weeks. Detailed design and engineering calculations will span weeks three through nine. Drafting, regulatory submissions, and permitting will occupy weeks ten through twelve. Commissioning, start-up, and final documentation will be completed in weeks thirteen and fourteen. All milestones are subject to timely client feedback and availability of the Mexico City facility for on-site work.
6. Terms, Conditions & Validity
Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing may be adjusted to reflect changes in material costs, labor rates, or applicable tax regulations in Mexico.
Exclusions: This estimate does not include the procurement of mechanical equipment, third-party testing by accredited laboratories, or any civil/structural work beyond the mechanical support scope. Travel and lodging for the Mechanical Engineer team beyond the standard Mexico City metropolitan area will be billed at cost with a 10% administrative surcharge.
Intellectual Property: All engineering drawings, calculations, and technical reports produced under this Quotation Estimate shall become the exclusive property of the client upon full payment. The Mechanical Engineer firm retains the right to reference the project in its portfolio with prior written consent.
Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the United Mexican States, with jurisdiction vested in the courts of Mexico City, Mexico. Disputes shall first be subject to mediation before the Cámara de Comercio de la Ciudad de México.
Insurance: The Mechanical Engineer firm maintains professional liability insurance (Seguro de Responsabilidad Profesional) with a coverage limit of MXN 10,000,000, valid throughout the project duration in Mexico City.
7. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate for Mechanical Engineer services in Mexico, Mexico City, and agrees to the terms, conditions, pricing, and scope of work described herein. This signature constitutes a binding acceptance and authorizes Salazar & Asociados Ingeniería Mecnica, S.A. de C.V. to commence the Mechanical Engineer engagement as outlined.
For: Salazar & Asociados Ingeniería Mecnica, S.A. de C.V.
Ing. Ricardo A. Salazar, P.E.
Lead Mechanical Engineer
R.M. No. 4521-8834
For: Grupo Industrial del Valle, S.A. de C.V.
Lic. Mariana Torres
Director of Operations
Authorized Signatory
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