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QUOTATION ESTIMATE
Professional Mechanical Engineer Services
Prepared for Clients in New Zealand Auckland
Quotation Reference: QE-ME-AKL-2025-0472
Date of Issue: 14 June 2025  |  Valid Until: 14 July 2025
Service Provider
Apex Mechanical Engineering Ltd
42 Federal Street, Ponsonby
Auckland 1011, New Zealand
Phone: +64 9 374 8821
Email: enquiries@apexme.co.nz
BNZ: 942-604-118
Client Details
Harbourview Industrial Group Ltd
18 Wharf Road, Wynyard Quarter
Auckland 1010, New Zealand
Attention: Mr. David Chen, Operations Director
Phone: +64 9 301 5567
Email: d.chen@harbourview.co.nz
1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate has been prepared by Apex Mechanical Engineering Ltd to provide Harbourview Industrial Group Ltd with a comprehensive and transparent cost breakdown for the engagement of a qualified Mechanical Engineer to deliver design, analysis, and commissioning services for the new automated packaging line at the client's Wynyard Quarter facility in New Zealand Auckland. This document outlines the full scope of professional services, associated costs, project timelines, and the terms and conditions governing the engagement. All pricing is quoted in New Zealand Dollars (NZD) inclusive of GST at the current rate of 15%.
2. Scope of Mechanical Engineer Services
The Mechanical Engineer assigned to this project, Mr. Jonathan Tui (MEng, NZIE, 12 years' experience), will deliver the following services across the project lifecycle in New Zealand Auckland:
· Conceptual Design & Feasibility: Development of preliminary mechanical layouts, equipment selection, and process flow diagrams for the automated packaging line, ensuring compliance with AS/NZS 1670 and relevant New Zealand building and safety regulations.
· Detailed Engineering Design: Production of full 3D CAD models, 2D fabrication drawings, piping and instrumentation diagrams (P&IDs), and structural support calculations for all mechanical components.
· Thermal & Fluid Systems Analysis: Computational fluid dynamics (CFD) modelling and thermal analysis of the conveyor heating zones and compressed air distribution network.
· Procurement Support: Preparation of technical specifications, vendor evaluation, and material take-off schedules for all mechanical equipment and components.
· Site Supervision & Commissioning: On-site oversight of mechanical installation at the Wynyard Quarter premises, including pressure testing, alignment verification, and performance acceptance testing.
· Documentation & Handover: Compilation of as-built drawings, operation and maintenance manuals, and statutory compliance certificates required by the Auckland Council.
3. Cost Breakdown – Quotation Estimate Line Items
	Ref
	Description of Service
	Rate (NZD)
	Quantity
	Duration
	Amount (NZD)

	01
	Conceptual design, feasibility study & process layout for automated packaging line
	$185.00/hr
	48 hrs
	Weeks 1–3
	$8,880.00

	02
	Detailed mechanical engineering design (3D CAD, 2D drawings, P&IDs, structural calcs)
	$185.00/hr
	120 hrs
	Weeks 4–9
	$22,200.00

	03
	CFD modelling & thermal/fluid systems analysis (conveyor heating zones, compressed air)
	$210.00/hr
	40 hrs
	Weeks 7–9
	$8,400.00

	04
	Procurement support: technical specs, vendor evaluation, material take-off
	$165.00/hr
	32 hrs
	Weeks 10–12
	$5,280.00

	05
	On-site installation supervision, pressure testing & commissioning at Wynyard Quarter, Auckland
	$195.00/hr
	60 hrs
	Weeks 13–16
	$11,700.00

	06
	As-built documentation, O&M manuals & Auckland Council compliance certificates
	$155.00/hr
	24 hrs
	Weeks 16–17
	$3,720.00

	07
	Travel & local transport within Auckland metropolitan area (per diem)
	$95.00/day
	18 days
	Project duration
	$1,710.00

	08
	Software licences (SolidWorks, ANSYS, AutoCAD) – project allocation
	Flat fee
	1
	Project duration
	$2,400.00

	Subtotal (excl. GST)
	$64,290.00

	GST @ 15%
	$9,643.50

	TOTAL QUOTATION ESTIMATE (incl. GST)
	$73,933.50


4. Project Timeline
The total estimated project duration is 17 weeks from the date of contract execution. The Mechanical Engineer will provide weekly progress reports and bi-weekly client review meetings. All site-based activities in New Zealand Auckland will be coordinated with the client's site manager to minimise disruption to ongoing operations at the Wynyard Quarter facility.
5. Terms and Conditions
1. This Quotation Estimate is valid for 30 calendar days from the date of issue. Should the client wish to proceed after the expiry date, a revised quotation will be required to reflect any changes in material or labour costs.
1. Payment terms: 30% deposit upon contract signing, 40% upon completion of detailed design (end of Week 9), and 30% upon final commissioning and handover. All invoices are payable within 14 days of issue.
1. The Mechanical Engineer shall maintain professional indemnity insurance of no less than NZD $10,000,000 and public liability insurance of no less than NZD $20,000,000 throughout the project duration.
1. All work shall comply with the New Zealand Building Code, AS/NZS standards, and any applicable Auckland Council bylaws. The client is responsible for obtaining all necessary resource consents and building permits.
1. Any variation to the scope of work must be agreed in writing by both parties prior to commencement. Variations exceeding 10% of the total Quotation Estimate value will require a formal change order and may affect the project timeline.
1. Intellectual property: All design documents, CAD files, and engineering calculations produced under this engagement shall become the property of the client upon full payment. Apex Mechanical Engineering Ltd retains the right to use anonymised project data for internal training and portfolio purposes.
1. Dispute resolution: Any disputes arising from this engagement shall be resolved through mediation in New Zealand Auckland in accordance with the Disputes Standards Act 2017 before either party may initiate legal proceedings in the District Court of Auckland.
1. This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties.
6. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the scope, pricing, and terms outlined herein for the engagement of the Mechanical Engineer for the automated packaging line project in New Zealand Auckland.
For and on behalf of Apex Mechanical Engineering Ltd
Name: Jonathan Tui, MEng, NZIE
Title: Principal Mechanical Engineer
Signature: ___________________________
Date: ___________________________
For and on behalf of Harbourview Industrial Group Ltd
Name: David Chen
Title: Operations Director
Signature: ___________________________
Date: ___________________________
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