Quotation Estimate - Mechanical Engineer Services - Nigeria Lagos
Apex Mechanical Engineering Solutions Ltd.
14B Admiralty Way, Lekki Phase 1, Lagos, Nigeria
Tel: +234 803 555 0192 | Email: quotes@apexmechanical.ng
RC: 1847293 | TIN: 10458293-0001
Quotation Estimate
Quotation Details
Quotation No.: AMES/QE/2025/0047
Date Issued: 14 June 2025
Valid Until: 14 July 2025
Project Location: Victoria Island, Nigeria Lagos
Client Information
Client Name: Lagos Industrial Development Corp.
Attention: Mr. Tunde Adebayo, Project Director
Address: 22 Adeola Odeku Street, Victoria Island, Nigeria Lagos
Contact: +234 805 771 3344
Dear Mr. Adebayo,
Thank you for your request for a Quotation Estimate for mechanical engineering consultancy and project execution services. Apex Mechanical Engineering Solutions Ltd. is pleased to submit this detailed Quotation Estimate for the design, installation, and commissioning of industrial HVAC and process piping systems at your facility in Nigeria Lagos. As a licensed Mechanical Engineer firm registered with the Council for the Regulation of Engineering in Nigeria (COREN), we bring over fifteen years of specialized experience delivering critical mechanical infrastructure projects across the Lagos metropolitan area and the broader Nigerian industrial corridor.
This Quotation Estimate has been prepared in full compliance with Nigerian Building and Road Works Corporation (NABRDC) standards, the Nigerian Code of Practice for Mechanical Services (COP 2018), and all applicable regulations enforced by the Lagos State Building Control Agency (LASBCA). Our team of certified Mechanical Engineer professionals will oversee every phase of the project from initial site survey through to final handover and warranty support.
Scope of Work and Itemized Costs
	S/N
	Description of Service
	Unit
	Qty
	Unit Cost (NGN)
	Total (NGN)

	1
	Site survey, load calculation, and preliminary design by a senior Mechanical Engineer in Nigeria Lagos
	Lump Sum
	1
	1,850,000
	1,850,000

	2
	Detailed engineering drawings, 3D modelling, and system specifications (HVAC, process piping, and ventilation)
	Lump Sum
	1
	3,200,000
	3,200,000

	3
	Supply and installation of 4 x 15-ton RTU (Rooftop Unit) HVAC systems including ductwork
	Set
	4
	4,750,000
	19,000,000

	4
	Supply and installation of 200 linear metres of insulated process piping (SS316L, 4-inch diameter)
	LM
	200
	85,000
	17,000,000

	5
	Installation of 2 x 50,000-litre industrial water storage tanks with pump sets and control panels
	Set
	2
	6,300,000
	12,600,000

	6
	Commissioning, pressure testing, balancing, and performance verification by the Mechanical Engineer team
	Lump Sum
	1
	2,400,000
	2,400,000

	7
	Regulatory approvals, LASBCA submission, and COREN certification documentation for Nigeria Lagos
	Lump Sum
	1
	950,000
	950,000

	8
	Operator training (2 days) and provision of as-built documentation and maintenance manuals
	Lump Sum
	1
	750,000
	750,000

	SUBTOTAL
	57,750,000

	VAT (7.5% as applicable in Nigeria Lagos)
	4,331,250

	GRAND TOTAL (NGN)
	62,081,250


Amount in words: Sixty-Two Million, Eighty-One Thousand, Two Hundred and Fifty Naira Only.
Payment Terms
1. 30% Advance Payment (NGN 18,624,375) upon acceptance of this Quotation Estimate and execution of the service agreement.
1. 40% Progress Payment (NGN 24,832,500) upon completion of all supply and installation works, subject to inspection by the client's representative.
1. 25% Completion Payment (NGN 15,520,313) upon successful commissioning, pressure testing, and handover of all as-built documentation.
1. 5% Retention (NGN 3,104,063) released after a 90-day defect liability period with no outstanding mechanical issues.
Project Timeline
1. Site survey and design phase: Weeks 1–3
1. Procurement and material delivery: Weeks 4–7
1. Installation and fabrication: Weeks 8–14
1. Commissioning and testing: Weeks 15–16
1. Regulatory sign-off and handover: Week 17
Total estimated project duration: 17 weeks from the date of advance payment receipt.
Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Prices are subject to revision upon expiry due to fluctuations in material costs in the Nigeria Lagos market.
1. All work shall be performed by qualified and COREN-registered Mechanical Engineer professionals under the direct supervision of our Lead Mechanical Engineer, Engr. Chukwuma Okafor (COREN Reg. No. 45218).
1. The client shall provide safe access to the project site in Nigeria Lagos, including necessary permits for heavy equipment movement on Lagos State roads.
1. Any variation in scope beyond 10% of the original Quotation Estimate value shall be subject to a revised quotation and written approval by both parties.
1. Apex Mechanical Engineering Solutions Ltd. warrants all installed mechanical equipment for a period of twenty-four (24) months from the date of commissioning, subject to normal operating conditions.
1. All disputes arising from this engagement shall be resolved through arbitration in accordance with the Arbitration and Conciliation Act (Cap A18, LFN 2004), with the seat of arbitration in Nigeria Lagos.
1. This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties.
Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the mechanical engineering services to be delivered in Nigeria Lagos.
For: Apex Mechanical Engineering Solutions Ltd.
Name: Engr. Chukwuma Okafor
Title: Lead Mechanical Engineer / Managing Director
Date: _______________
For: Lagos Industrial Development Corp.
Name: Mr. Tunde Adebayo
Title: Project Director
Date: _______________
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