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1. Scope of Work – Mechanical Engineer Services in Russia Moscow
This Quotation Estimate is issued by Engineering Solutions Moscow LLC in response to the formal request for professional Mechanical Engineer consulting and design services to be delivered at the client's industrial facility located in the industrial district of Russia Moscow, specifically within the Moscow Industrial Park No. 7, Krasnogorsk Administrative Okrug. The scope encompasses the full lifecycle of mechanical engineering support, including preliminary design, detailed engineering, equipment selection, installation supervision, and commissioning oversight for the client's new manufacturing line expansion project.
The Mechanical Engineer team assigned to this project will operate in full compliance with all applicable Russian Federation regulations, including GOST standards, SNiP building codes, and the requirements of Rostekhnadzor (Federal Service for Environmental, Technological and Nuclear Supervision). All deliverables will be prepared in accordance with the technical specifications outlined in the client's Request for Proposal dated 28 May 2025.
2. Itemized Cost Breakdown
	No.
	Description of Mechanical Engineer Service
	Unit
	Quantity
	Unit Rate (RUB)
	Total (RUB)

	1
	Preliminary mechanical design and feasibility study for the new production line in Moscow, Russia. Includes process flow diagrams, equipment layout, and utility requirements assessment.
	Lot
	1
	485,000
	485,000

	2
	Detailed mechanical engineering design package: P&ID drawings, isometric piping drawings, equipment data sheets, and structural support calculations. Prepared by a licensed Mechanical Engineer per Rostekhnadzor requirements.
	Lot
	1
	1,250,000
	1,250,000

	3
	Equipment selection, vendor coordination, and technical specification preparation for rotating machinery, heat exchangers, pumps, and conveyors to be installed at the Moscow facility.
	Lot
	1
	620,000
	620,000

	4
	On-site installation supervision and quality assurance by a senior Mechanical Engineer. Includes weekly progress reports, non-conformance tracking, and punch-list management. Duration: 12 weeks at the Krasnogorsk site, Russia Moscow.
	Week
	12
	95,000
	1,140,000

	5
	Commissioning support, performance testing, and final handover documentation. Includes preparation of as-built drawings, operation and maintenance manuals, and Rostekhnadzor compliance certification package.
	Lot
	1
	380,000
	380,000

	6
	Travel, accommodation, and per diem for the Mechanical Engineer team (2 engineers, 1 technician) stationed in Russia Moscow for the duration of the project. Compliant with Moscow City corporate travel policy.
	Month
	4
	185,000
	740,000

	7
	Software licensing and CAD/BIM modeling tools (AutoCAD Mechanical, SolidWorks, Revit MEP) for the project duration, including local Russian-language interface configuration.
	Lot
	1
	125,000
	125,000

	Subtotal (RUB):
	4,740,000

	VAT (20% per Russian Tax Code):
	948,000

	Grand Total (RUB):
	5,688,000


Note: All prices in this Quotation Estimate are quoted in Russian Rubles (RUB) and are inclusive of all applicable local taxes in Russia Moscow. The exchange rate reference for international clients is provided upon request. Prices are valid for 30 calendar days from the date of issue.
3. Project Timeline and Milestones
	Milestone
	Deliverable
	Target Date

	Milestone 1
	Submission of preliminary design report and feasibility study
	15 July 2025

	Milestone 2
	Delivery of complete detailed mechanical engineering design package
	15 September 2025

	Milestone 3
	Completion of equipment procurement support and vendor finalization
	15 October 2025

	Milestone 4
	End of on-site installation supervision (12 weeks)
	15 January 2026

	Milestone 5
	Commissioning complete, final documentation and Rostekhnadzor certification submitted
	15 February 2026


4. Terms and Conditions
· This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on market conditions in Russia Moscow.
· Payment terms: 30% advance payment upon contract signing, 40% upon delivery of the detailed design package, 20% upon completion of installation supervision, and 10% upon final commissioning and handover. All payments shall be made in Russian Rubles via bank transfer to the account of Engineering Solutions Moscow LLC, Sberbank, Moscow Branch.
· The Mechanical Engineer team shall maintain full professional liability insurance coverage in accordance with Russian Federation law for the entire duration of the engagement.
· All intellectual property rights in the design documents, calculations, and engineering deliverables produced under this contract shall vest in the client upon full payment. The Mechanical Engineer team retains the right to reference the project in professional portfolios with prior written consent.
· Any changes to the scope of work must be documented through a formal Change Order signed by both parties. Additional costs arising from scope changes will be quoted separately and are not included in this Quotation Estimate.
· Force majeure events, including but not limited to natural disasters, government sanctions, or regulatory changes affecting operations in Russia Moscow, shall be governed by Article 416 of the Civil Code of the Russian Federation.
· Disputes arising from this agreement shall be resolved through arbitration at the Arbitration Court of the City of Moscow, in accordance with the procedural rules of that court.
· The Mechanical Engineer services described herein are subject to the professional standards of the Russian Union of Engineers and the requirements of the Federal Law on Technical Regulation (No. 184-FZ).
5. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate accurately reflects the agreed-upon scope, pricing, and terms for the Mechanical Engineer services to be performed in Russia Moscow. This document, once countersigned, shall serve as the basis for the formal Service Agreement to be executed within ten (10) business days.
For Engineering Solutions Moscow LLC (Provider)
Name: Alexei Petrov, P.Eng.
Title: Lead Mechanical Engineer / Project Director
Signature: _________________________
Date: _________________________
For OOO StroyInvest Group (Client)
Name: Dmitry Volkov
Title: Chief Procurement Officer
Signature: _________________________
Date: _________________________
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