Quotation Estimate - Mechanical Engineer Services - Switzerland Zurich
Helvetia Engineering Solutions AG
Bahnhofstrasse 142, 8001 Zurich, Switzerland
Phone: +41 44 555 0192 | Email: quotes@helvetia-eng.ch
VAT No.: CHE-123.456.789 IVA
Quotation No.: QE-2025-0847
Date Issued: 12 June 2025
Valid Until: 12 September 2025
QUOTATION ESTIMATE
Professional Mechanical Engineer Services – Switzerland Zurich
	Prepared For:
	Alpine Manufacturing Group AG, Industriestrasse 27, 8005 Zurich, Switzerland

	Attention:
	Dr. Markus Keller, Head of Production Engineering

	Project Reference:
	AMG-2025-REV-003 – Production Line Redesign & Thermal System Optimization

	Service Location:
	Switzerland Zurich – Client Facility, Industriestrasse 27, 8005 Zurich

	Prepared By:
	Ing. Stefan Brandt, Senior Mechanical Engineer, Helvetia Engineering Solutions AG


1. Scope of Work – Mechanical Engineer Services
This Quotation Estimate is issued by Helvetia Engineering Solutions AG to provide comprehensive Mechanical Engineer consulting and design services for the Alpine Manufacturing Group AG facility located in Switzerland Zurich. The scope encompasses the full redesign of the existing production line, thermal management system optimization, structural integrity assessment, and the delivery of complete engineering documentation in compliance with Swiss and European standards (SIA, EN, and ISO 9001:2015).
The Mechanical Engineer team assigned to this project will operate on-site in Switzerland Zurich for the duration of the engagement, ensuring direct collaboration with the client's internal production and quality assurance departments. All deliverables will adhere to the regulatory framework governing mechanical engineering practice in the Canton of Zurich and the broader Swiss Confederation.
2. Itemized Cost Breakdown
	Ref.
	Description of Service
	Quantity
	Unit Rate (CHF)
	Amount (CHF)
	Duration

	01
	Initial site survey and feasibility assessment at the Switzerland Zurich facility, including as-built documentation review and thermal imaging of existing systems
	1 lot
	4,800.00
	4,800.00
	3 days

	02
	Mechanical design and CAD modelling of redesigned production line components (SolidWorks / CATIA), including tolerance analysis and FEA simulation
	120 hrs
	185.00
	22,200.00
	6 weeks

	03
	Thermal system optimization: heat exchanger redesign, fluid dynamics analysis (CFD), and energy efficiency improvement plan
	80 hrs
	195.00
	15,600.00
	4 weeks

	04
	Structural integrity assessment and load-bearing verification of existing framework per SIA 263 and Eurocode 3, with written engineering report
	1 lot
	7,500.00
	7,500.00
	2 weeks

	05
	Preparation of complete technical documentation package: assembly drawings, BOM, maintenance manuals, and Swiss regulatory compliance certificates
	1 lot
	6,200.00
	6,200.00
	3 weeks

	06
	On-site supervision of fabrication and installation at the Switzerland Zurich plant, including daily progress reports and punch-list management
	25 days
	1,100.00
	27,500.00
	5 weeks

	07
	Commissioning support, performance testing, and final handover documentation review with client engineering team
	5 days
	1,200.00
	6,000.00
	1 week

	08
	Post-commissioning warranty period: remote and on-call support for the Mechanical Engineer design deliverables
	6 months
	3,500.00
	3,500.00
	6 months

	Subtotal
	CHF 93,300.00
	

	VAT (7.7% – Swiss standard rate)
	CHF 7,184.10
	

	TOTAL AMOUNT DUE
	CHF 100,484.10
	


3. Payment Terms
· 30% advance payment (CHF 30,145.23) upon written acceptance of this Quotation Estimate and signing of the service agreement.
· 40% milestone payment (CHF 40,193.64) upon completion and client approval of all design deliverables (Items 02, 03, 04, and 05).
· 30% final payment (CHF 30,145.23) upon successful commissioning, handover, and issuance of the final completion certificate.
· All payments to be made via bank transfer to: Helvetia Engineering Solutions AG, UBS AG, IBAN: CH93 0023 0456 7800 3890 7, BIC: UBSWCHZH80A, Zurich, Switzerland.
· Invoices are payable within 30 days of the invoice date. Late payments shall accrue interest at the Swiss statutory rate (currently 5% per annum).
4. Terms and Conditions
· This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on material cost fluctuations and resource availability in the Switzerland Zurich market.
· All Mechanical Engineer services shall be performed in accordance with the Swiss Code of Obligations (OR), applicable SIA norms, and the professional code of conduct of the Swiss Association of Engineers and Natural Scientists (SIA/ASCO).
· The Mechanical Engineer team shall maintain full professional liability insurance (minimum CHF 5,000,000 per occurrence) throughout the project duration. A certificate of insurance shall be provided upon request.
· Intellectual property rights for all design documents, CAD files, and engineering reports produced under this engagement shall transfer to the client upon full and final payment.
· Confidentiality: All information exchanged between the parties shall be treated as strictly confidential in accordance with Swiss data protection law (nDSG / FADP). A mutual NDA is available upon request.
· Force majeure events, including but not limited to natural disasters, pandemics, or government-mandated work stoppages in the Canton of Zurich, shall extend the project timeline proportionally without penalty to either party.
· Disputes arising from this Quotation Estimate or the resulting service agreement shall be resolved by the competent courts of Zurich, Switzerland, or by arbitration under the Swiss Rules of Arbitration administered by the Swiss Arbitration Centre.
· This Quotation Estimate does not constitute a binding contract until both parties have signed and returned the acceptance section below.
5. Assumptions and Exclusions
· Client shall provide timely access to the Switzerland Zurich facility, including all necessary safety equipment and site induction for the Mechanical Engineer team.
· Costs for third-party laboratory testing, material procurement, and fabrication are excluded from this Quotation Estimate and shall be quoted separately.
· Any scope changes exceeding 10% of the original work description will require a formal change order and revised Quotation Estimate prior to execution.
· Travel and accommodation costs for the Mechanical Engineer team are included for the Switzerland Zurich site. Travel to locations outside the Canton of Zurich will be billed at cost.
6. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for Mechanical Engineer services to be delivered at the Switzerland Zurich facility, and authorizes Helvetia Engineering Solutions AG to commence work in accordance with the terms stated herein.
For Helvetia Engineering Solutions AG
Ing. Stefan Brandt
Senior Mechanical Engineer
Date: ______________________
For Alpine Manufacturing Group AG
Dr. Markus Keller
Head of Production Engineering
Date: ______________________
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