Quotation Estimate - Mechatronics Engineer Services - Canada Montreal
ProTech Mechatronics Solutions Inc.
4520 Boulevard Industriel, Suite 310
Montreal, Quebec H4A 1B2, Canada
Tel: +1 (514) 555-0187 | Email: quotes@protechmech.ca
QST No: 123456789QST0001
QUOTATION ESTIMATE
Reference: QTE-2025-0487
Date: June 12, 2025
Valid Until: July 12, 2025
Client Information
Company: Nova Automation Systems Ltd.
Address: 890 Rue Sainte-Catherine Est, Montreal, QC H2L 2C4, Canada
Contact Person: Mr. David Tremblay, Operations Director
Email: d.tremblay@novaautomation.ca
Project Location: Canada Montreal – Industrial Zone, Laval
Project Duration: 14 weeks (estimated)
Quotation Estimate Type: Fixed-Price with Milestone Billing
Currency: Canadian Dollars (CAD)
Scope of Work – Mechatronics Engineer Services
This Quotation Estimate is issued by ProTech Mechatronics Solutions Inc. to provide comprehensive Mechatronics Engineer consulting and implementation services for Nova Automation Systems Ltd. The project will be executed in Canada Montreal and its surrounding industrial corridors. The scope encompasses the design, integration, programming, and commissioning of automated production lines incorporating mechanical systems, embedded electronics, industrial control systems, and software interfaces. Our senior Mechatronics Engineer team will be deployed on-site in Montreal to ensure seamless coordination with your existing operations and to comply with all applicable Canadian and Quebec provincial regulations governing industrial automation and workplace safety.
Detailed Cost Breakdown
	#
	Description of Services
	Quantity
	Unit Rate (CAD)
	Subtotal (CAD)
	Duration

	1
	Senior Mechatronics Engineer – System Design & Architecture (on-site, Montreal)
	120 hrs
	$145.00
	$17,400.00
	Weeks 1–3

	2
	Mechatronics Engineer – PLC/SCADA Programming & HMI Development
	160 hrs
	$130.00
	$20,800.00
	Weeks 3–7

	3
	Mechatronics Engineer – Mechanical Integration & Actuator Calibration
	100 hrs
	$125.00
	$12,500.00
	Weeks 5–9

	4
	Embedded Systems & Sensor Network Deployment (Canada Montreal site)
	80 hrs
	$135.00
	$10,800.00
	Weeks 7–10

	5
	Software Integration, API Development & Data Logging Platform
	120 hrs
	$140.00
	$16,800.00
	Weeks 9–12

	6
	System Commissioning, Testing & Performance Validation
	60 hrs
	$150.00
	$9,000.00
	Weeks 12–14

	7
	Documentation, Operator Training & Handover (Montreal facility)
	40 hrs
	$120.00
	$4,800.00
	Week 14

	8
	Project Management & Quality Assurance Oversight
	56 hrs
	$155.00
	$8,680.00
	Weeks 1–14

	9
	Travel, Accommodation & Local Transport within Canada Montreal region
	Flat
	$1.00
	$3,200.00
	Full duration

	10
	Specialized Tooling, Diagnostic Equipment & Consumables
	Flat
	$1.00
	$5,500.00
	As required

	Subtotal
	$109,480.00
	

	QST (Quebec Sales Tax) – 9.975%
	$10,920.62
	

	GST (Goods and Services Tax) – 5%
	$5,474.00
	

	TOTAL ESTIMATED COST (CAD)
	$125,874.62
	


Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing and availability of the Mechatronics Engineer team may be subject to revision.
· Payment terms: 30% deposit upon acceptance of this quotation, 40% upon completion of Week 7 milestone, and 30% upon final commissioning and acceptance in Canada Montreal.
· All invoices are payable within thirty (30) days of the invoice date. Late payments shall accrue interest at 1.5% per month as per Quebec commercial law.
· The Mechatronics Engineer personnel assigned to this project are fully insured under Canadian provincial liability and workers' compensation frameworks applicable in Quebec.
· Any changes to the scope of work must be documented in a formal Change Order signed by both parties before additional work commences. Revised costs will be reflected in a supplementary Quotation Estimate.
· Intellectual property developed specifically for Nova Automation Systems Ltd. under this engagement shall transfer to the client upon full payment. General methodologies, templates, and pre-existing tools remain the property of ProTech Mechatronics Solutions Inc.
· Warranty: A twelve-month warranty on all integrated systems and programming is provided from the date of final acceptance. This warranty covers defects in workmanship and software but excludes damage caused by misuse, unauthorized modifications, or force majeure events.
· This agreement is governed by the laws of the Province of Quebec and the federal laws of Canada applicable therein. Any disputes shall be resolved through arbitration in Montreal, Canada, in accordance with the rules of the ADR Institute of Canada.
· ProTech Mechatronics Solutions Inc. reserves the right to substitute equivalent Mechatronics Engineer personnel of equal or greater qualification without prior notice, provided the client is informed within 48 hours.
Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes ProTech Mechatronics Solutions Inc. to commence the Mechatronics Engineer services as described herein at the project site in Canada Montreal.
For ProTech Mechatronics Solutions Inc.:
Name: Sarah Beauchamp, P.Eng.
Title: Principal Mechatronics Engineer
Date: _________________________
For Nova Automation Systems Ltd.:
Name: David Tremblay
Title: Operations Director
Date: _________________________
This Quotation Estimate document was prepared by ProTech Mechatronics Solutions Inc., a corporation registered in the Province of Quebec, Canada. All rates are quoted in Canadian Dollars (CAD) and are inclusive of the Mechatronics Engineer professional expertise, on-site presence in Canada Montreal, and standard project management overhead. This document does not constitute a binding contract until countersigned by both parties. For questions regarding this estimate, please contact our Montreal office at +1 (514) 555-0187.
